## 0) ReadMe and Contents
SHOC 2.0 (UNOFFICIAL)¦ UKRI Budget vs Actuals Project Dashboard
Illustrative UKRI/ESRC fEC project tracker ¦ Created by Alexander Pymm as a Proof of Concept for the RUSI OCP Project Officer Role
Workbook purpose and Readme
Project | Strategic Hub for Organised Crime Research 2.0 (SHOC 2.0) | WHAT IS THIS TOOL? In short, this workbook allows for real-time tracking of project costs against funder budgets, breaking down spend by category and forecasting areas of over and underspend (Variance Analysis). It also has capabilities to automate the import of new monthly transaction data from the accompanying .csv template, if enabled (see Tab 4).
Lead Institution | Royal United Services Institute (RUSI) - Organised Crime and Policing
Funder | Illustrative UKRI/ESRC award | WHERE IS THIS DATA FROM? The Budget is a purely hypothetical example based around a typical full Economic Costing (fEC) model, alongside an 80% fEC UKRI contribution rate. The Budget is comprised of 3 Work Packages, each centered around a regional hub relevant to the OCP's recent engagement work: London (UK/Europe); Nairobi (/East Africa); and Bogota (Colombia/Latin America). Like the original SHOC project, promised outputs relate chiefly to engagement activities, such as workshops, conferences and panels, alongside broader collaborative opportunities.
Project start | 2026-04-01
Project end | 2029-03-31 | IMPORTED TRANSACTIONS ARE ONLY ADDED TO THE LEDGER ONCE VERIFIED AGAINST CORRESPONDING BUDGET ITEMS A new batch remains excluded until its Refresh Log status is explicitly changed to 'APPROVED.'
Reporting currency | GBP
Contents and Navigation
Budget-vs-Actuals Dashboard | Project overview: Budget, cost to date, variance, commitments and forecast, broken down by Work Package and cost category.
Variance Detail | Which Budget line is driving a variance, and by how much.
Forecast Bridge | The forecast for each budget line by Project Completion.
Monthly Processes
Monthly Update | A step-by-step guide for updating the Dashboard with new monthly transactions.
Refresh Log | Provides a record of when new records have been added to the Dashboard, and which files/sources were used.
Key Records
Actuals Ledger | Records all confirmed (personally verified) transactions contributing to the Directly Incurred costs on the project (e.g. Conference material, travel expenses and reimbursements etc.)
Allocations | Allocated Costs recorded against the project Budget. Includes allocated staff, estates and indirect costs (separate from directly incurred transaction/invoice costs).
Commitments Forecast | Open purchase orders and contracts (money committed but not yet spent)
Back-end & Validation
Budget Baseline | The version of the Budget approved by the funder. The baseline reference against future project pending.
Budget Changes | Dated, approved changes to the original budget
Model Checks | A series of validity checks to check against common compliance issues or trechnical errors in the Excel file.
Mappings
Monthly Transaction Updates: Step-by-Step Process
1 | Open and review the dashboard for currency | After saving the Dashboard somewhere appropriate, it is recommended to check a few things to make sure you get the most out of the Dashboard: i) check the 'reporting cut-off' and 'last approved refresh' dates to make sure your data is up-to-date; and ii) check the model status indicator for existing errors.
2 | Create a staged batch | Add a 'STAGED' row on Refresh Log, alongside: i) a unique Batch ID; ii) an expected row count; and iii) a source control total.
3 | Bring in transactions [manual/offline approach] | Paste values into the blue input columns on the Actuals Ledger. Background route: follow the Monthly Update sheet to configure the optional Power Query staging import, then refresh it explicitly.
4 | Validate | Resolve every staging/ledger issue: schema, dates, amount, unique ID, mapping, evidence and reversal link. Reconcile rows and value to the source total.
5 | Approve | Only after review, change the batch status from STAGED to APPROVED. The dashboard will then include the batch.
6 | Update exposure | Update Allocations and Commitments separately. Review Forecast at Completion and the Checks sheet.
7 | Close and save | Set the Dashboard cut-off to the reviewed month-end, confirm PASS, record reviewer/source notes and save the monthly state.
Dashboard Terms
Term | Definition | Included in realised/recognised cost? | Control treatment
Original Budget | Frozen accepted Budget at 100% fEC, with UKRI and RUSI shares retained. | No: comparator | Never overwritten
Approved Budget | Original Budget plus any subsequent authorised changes. | No: comparator | Changes recorded separately
Confirmed DI Costs | Confirmed, auditable project-identifiable transaction at booked GBP value. | Yes | Evidence, dates, mapping and duplicate tests
Confirmed DA Costs | Recorded DA staff, estate or indirect management allocation. Often not charged against the project like DI costs (e.g by invoice or Tx) | Yes, shown separately | Allocation basis and source required
Committed Costs | Payments liable for payment but not yet realised. (e.g. open purchase orders, contracts or other future exposures) | No | Separate ledger. Status must be Open
Phased Budget | Approved Budget distributed using the Budget timing profile. | No: comparator | Reconciles to approved Budget
Forecast at Completion | Confirmed costs + open commitments + uncommitted ETC. | Forecast only | Bridges by Budget item
NOTE: The 80/20 fEC funder contribution split and given estate/indirect proxy values are used here for the sake of simplicity. Budget items elligible for exceptions (funded at 100% fEC) and RUSI's specific IRO rate basis may both differ significantly from these assumptions.

## 1) Budget-Actuals Dashboard
SHOC 2.0 ¦ Budget vs Actuals Dashboard
Illustrative UKRI/ESRC fEC project
Illustrative portfolio data ¦ As of 31 Aug 2026 ¦ Last approved refresh 01 Sep 2026 09:00 ¦ Model status PASS
Reporting cut-off |  | 2026-08-31 |  | Period view |  | Cumulative | Funding basis |  | 100% fEC |  | PASS
Work Package |  | All |  | fEC Heading |  | Directly Incurred | fEC Subheading |  | All
Phased Budget |  |  | Confirmed Cost |  |  | Variance to phased |  | Open Commitments |  |  | Forecast at Completion
12805.5583 |  |  | 13751.2 |  |  | -945.6417 |  | 27200 |  |  | 157100.02
Selected-period approved Budget |  |  | Realised and verified DI + DA costs |  |  | Budget minus confirmed; timing is not automatically favourable |  | Future comittments (excluded from actuals) |  |  | Forecast is £2,900 above approved Budget
DI measure
Confirmed DI Costs |  |  | 13751.2
Remaining DI Budget |  |  | 140448.82
Budget consumed |  |  | 8.918%
Selected-period position by Work Package | [6 empty] | Selected-period position by fEC Heading
Work Package | Selected-period Budget | Recognised cost | Variance | Open commitments | Forecast at Completion | Full approved Budget | fEC Heading | Selected-period Budget | Recognised cost | Variance | Open commitments | Forecast at Completion | Full approved Budget
WP1 | 15804.2708 | 16853.15 | -1048.8792 | 16350 | 153817.23 | 152117.23 | Directly Allocated | 10948.2833 | 10882.64 | 65.6433 | 0 | 82553.88 | 82553.88
WP2 | 8401.3125 | 8380.3 | 21.0125 | 5300 | 76939.45 | 76489.45 | Directly Incurred | 12805.5583 | 13751.2 | -945.6417 | 27200 | 157100.02 | 154200.02
WP3 | 10569.6667 | 10355.67 | 213.9967 | 5550 | 92851.6 | 92101.6 | Indirect | 11021.4083 | 10955.28 | 66.1283 | 0 | 83954.38 | 83954.38
Total | 34775.25 | 35589.12 | -813.87 | 27200 | 323608.28 | 320708.28 | Total | 34775.25 | 35589.12 | -813.87 | 27200 | 323608.28 | 320708.28
Management reading: recognised cost is £13,751 against cumulative phased Budget of £12,806 and simple pro-rata of £21,417. Open commitments are shown separately.

## 2) Variance Detail
Variance and exposure detail
Budget-item drill-down using the Dashboard reporting cut-off, period view and funding basis
Current view: Cumulative ¦ 100% fEC ¦ cut-off 31 Aug 2026 ¦ WP All ¦ heading Directly Incurred ¦ subheading All
Budget Item ID | Description | Work Package | fEC Heading | fEC Subheading | Reporting Category | In Selected Scope? | Period Budget | Period Recognised | Variance £ | Variance % | Open Commitments | FAC Variance
WP1_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | No | 1635.4167 | 1625.59 | 9.8267 | 0.6009% | 0 | 0
WP1_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | No | 1809.375 | 1798.53 | 10.845 | 0.5994% | 0 | 0
WP1_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | No | 1856.25 | 1845.11 | 11.14 | 0.6001% | 0 | 0
WP1_TRAVEL | RUSI - UK rail, local travel and subsistence Budget | WP1 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | Yes | 1041.6667 | 1356.2 | -314.5333 | -30.2% | 0 | 0
WP1_CONF | RUSI - five-day flagship London conferences (launch and close) | WP1 | Directly Incurred | Other Directly Incurred | Conferences | Yes | 0 | 0 | 0 |  | 14700 | -1800
WP1_WORKSHOP | RUSI - UK national and regional workshops | WP1 | Directly Incurred | Other Directly Incurred | Workshops | Yes | 1666.6667 | 2150 | -483.3333 | -29% | 1200 | 0
WP1_PANEL | RUSI - hybrid panels and practitioner roundtables | WP1 | Directly Incurred | Other Directly Incurred | Panels & Roundtables | Yes | 625 | 790 | -165 | -26.4% | 0 | 0
WP1_COMMS | RUSI - knowledge products and digital communications | WP1 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | Yes | 416.6667 | 575 | -158.3333 | -38% | 450 | 100
WP1_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP1 | Indirect | Indirect | Indirect Costs | No | 5989.8958 | 5953.96 | 35.9358 | 0.5999% | 0 | 0
WP1_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP1 | Directly Allocated | Estates | Estate Costs | No | 763.3333 | 758.76 | 4.5733 | 0.5991% | 0 | 0
WP2_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | No | 490.625 | 487.69 | 2.935 | 0.5982% | 0 | 0
WP2_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | No | 603.125 | 599.52 | 3.605 | 0.5977% | 0 | 0
WP2_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | No | 618.75 | 615.04 | 3.71 | 0.5996% | 0 | 0
WP2_TRAVEL | RUSI - London-team and East Africa stakeholder travel/subsistence | WP2 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | Yes | 1666.6667 | 1665 | 1.6667 | 0.1% | 1850 | -600
WP2_CONSULT | RUSI - Nairobi-based regional network broker consultant | WP2 | Directly Incurred | Other Directly Incurred | Regional Consultancy | Yes | 1750 | 1750 | 0 | 0% | 2450 | 0
WP2_CONF | RUSI - five-day Nairobi regional conference | WP2 | Directly Incurred | Other Directly Incurred | Conferences | Yes | 0 | 0 | 0 |  | 0 | 0
WP2_WORKSHOP | RUSI - East Africa practitioner-policy-academic workshops | WP2 | Directly Incurred | Other Directly Incurred | Workshops | Yes | 833.3333 | 825 | 8.3333 | 1% | 1000 | 0
WP2_COMMS | RUSI - participant materials and regional communications | WP2 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | Yes | 277.7792 | 290 | -12.2208 | -4.399% | 0 | 150
WP2_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP2 | Indirect | Indirect | Indirect Costs | No | 1916.7667 | 1905.26 | 11.5067 | 0.6003% | 0 | 0
WP2_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP2 | Directly Allocated | Estates | Estate Costs | No | 244.2667 | 242.79 | 1.4767 | 0.6045% | 0 | 0
WP3_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | No | 1308.3333 | 1300.49 | 7.8433 | 0.5995% | 0 | 0
WP3_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | No | 603.125 | 599.52 | 3.605 | 0.5977% | 0 | 0
WP3_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | No | 618.75 | 615.04 | 3.71 | 0.5996% | 0 | 0
WP3_TRAVEL | RUSI - London-team and Latin America stakeholder travel/subsistence | WP3 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | Yes | 1666.6667 | 1390 | 276.6667 | 16.6% | 2100 | -900
WP3_CONSULT | RUSI - Latin America-based regional network broker consultant | WP3 | Directly Incurred | Other Directly Incurred | Regional Consultancy | Yes | 1750 | 1750 | 0 | 0% | 2450 | 0
WP3_CONF | RUSI - five-day Latin America hub conference (hub to be confirmed) | WP3 | Directly Incurred | Other Directly Incurred | Conferences | Yes | 0 | 0 | 0 |  | 0 | 0
WP3_WORKSHOP | RUSI - Latin America practitioner-policy-academic workshops | WP3 | Directly Incurred | Other Directly Incurred | Workshops | Yes | 833.3333 | 865 | -31.6667 | -3.8% | 1000 | 0
WP3_COMMS | RUSI - Spanish/Portuguese materials and regional communications | WP3 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | Yes | 277.7792 | 345 | -67.2208 | -24.2% | 0 | 150
WP3_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP3 | Indirect | Indirect | Indirect Costs | No | 3114.7458 | 3096.06 | 18.6858 | 0.5999% | 0 | 0
WP3_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP3 | Directly Allocated | Estates | Estate Costs | No | 396.9333 | 394.56 | 2.3733 | 0.5979% | 0 | 0
Interpretation: positive variance is remaining headroom and negative variance is overspend/exposure. Neither is automatically favourable or unfavourable: timing, delivery progress, eligibility and evidence must be reviewed together.

## 3) Forecast Bridge
Item-level Forecast at Completion bridge
Budget breakdown by each line item and current spend against. Confirmed (Realised costs) + Committed (costs liable to pay but unrealised) + Unspent (unrealised costs) = 100% fCE* *At the time of the Dashboard cut-off and based on costs being verified against the project
Forecast at Completion should never overwrites the approved Budget. Only us the blue Forecast Adjustment column as an input (use it to record an expected committment, anticipated risk or saving etc.) and review monthly. Everything else is forecasted from the baseline budget, confirmedf cost ledgers and the commitment register.
Budget Item ID | Description | Work Package | fEC Heading | fEC Subheading | Approved Budget | Spend to Date | Open Commitments | Forecast Adjustment | Uncommitted ETC | Forecast at Completion | Variance to Budget | Funding Rate | FAC UKRI | FAC RUSI | Variance UKRI | Variance RUSI | Notes
WP1_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP1 | Directly Allocated | Staff | 14915 | 1625.59 | 0 | 0 | 13289.41 | 14915 | 0 | 80% | 11932 | 2983 | 0 | 0 | Base ETC follows remaining approved Budget.
WP1_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP1 | Directly Allocated | Staff | 13027.5 | 1798.53 | 0 | 0 | 11228.97 | 13027.5 | 0 | 80% | 10422 | 2605.5 | 0 | 0 | Base ETC follows remaining approved Budget.
WP1_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP1 | Directly Allocated | Staff | 13365 | 1845.11 | 0 | 0 | 11519.89 | 13365 | 0 | 80% | 10692 | 2673 | 0 | 0 | Base ETC follows remaining approved Budget.
WP1_TRAVEL | RUSI - UK rail, local travel and subsistence Budget | WP1 | Directly Incurred | Travel & Subsistence | 7500 | 1356.2 | 0 | 0 | 6143.8 | 7500 | 0 | 80% | 6000 | 1500 | 0 | 0 | Base ETC follows remaining approved Budget.
WP1_CONF | RUSI - five-day flagship London conferences (launch and close) | WP1 | Directly Incurred | Other Directly Incurred | 30000 | 0 | 14700 | 1800 | 17100 | 31800 | -1800 | 80% | 25440 | 6360 | -1440 | -360 | Illustrative risk/saving adjustment; review monthly.
WP1_WORKSHOP | RUSI - UK national and regional workshops | WP1 | Directly Incurred | Other Directly Incurred | 12000 | 2150 | 1200 | 0 | 8650 | 12000 | 0 | 80% | 9600 | 2400 | 0 | 0 | Base ETC follows remaining approved Budget.
WP1_PANEL | RUSI - hybrid panels and practitioner roundtables | WP1 | Directly Incurred | Other Directly Incurred | 4500 | 790 | 0 | 0 | 3710 | 4500 | 0 | 80% | 3600 | 900 | 0 | 0 | Base ETC follows remaining approved Budget.
WP1_COMMS | RUSI - knowledge products and digital communications | WP1 | Directly Incurred | Other Directly Incurred | 3000 | 575 | 450 | -100 | 1875 | 2900 | 100 | 80% | 2320 | 580 | 80 | 20 | Illustrative risk/saving adjustment; review monthly.
WP1_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP1 | Indirect | Indirect | 47727.49 | 5953.96 | 0 | 0 | 41773.53 | 47727.49 | 0 | 80% | 38181.992 | 9545.498 | 0 | 0 | Base ETC follows remaining approved Budget.
WP1_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP1 | Directly Allocated | Estates | 6082.24 | 758.76 | 0 | 0 | 5323.48 | 6082.24 | 0 | 80% | 4865.792 | 1216.448 | 0 | 0 | Base ETC follows remaining approved Budget.
WP2_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP2 | Directly Allocated | Staff | 3532.5 | 487.69 | 0 | 0 | 3044.81 | 3532.5 | 0 | 80% | 2826 | 706.5 | 0 | 0 | Base ETC follows remaining approved Budget.
WP2_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP2 | Directly Allocated | Staff | 4342.5 | 599.52 | 0 | 0 | 3742.98 | 4342.5 | 0 | 80% | 3474 | 868.5 | 0 | 0 | Base ETC follows remaining approved Budget.
WP2_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP2 | Directly Allocated | Staff | 4455 | 615.04 | 0 | 0 | 3839.96 | 4455 | 0 | 80% | 3564 | 891 | 0 | 0 | Base ETC follows remaining approved Budget.
WP2_TRAVEL | RUSI - London-team and East Africa stakeholder travel/subsistence | WP2 | Directly Incurred | Travel & Subsistence | 12000 | 1665 | 1850 | 600 | 9085 | 12600 | -600 | 80% | 10080 | 2520 | -480 | -120 | Illustrative risk/saving adjustment; review monthly.
WP2_CONSULT | RUSI - Nairobi-based regional network broker consultant | WP2 | Directly Incurred | Other Directly Incurred | 12600 | 1750 | 2450 | 0 | 8400 | 12600 | 0 | 80% | 10080 | 2520 | 0 | 0 | Base ETC follows remaining approved Budget.
WP2_CONF | RUSI - five-day Nairobi regional conference | WP2 | Directly Incurred | Other Directly Incurred | 16000 | 0 | 0 | 0 | 16000 | 16000 | 0 | 80% | 12800 | 3200 | 0 | 0 | Base ETC follows remaining approved Budget.
WP2_WORKSHOP | RUSI - East Africa practitioner-policy-academic workshops | WP2 | Directly Incurred | Other Directly Incurred | 6000 | 825 | 1000 | 0 | 4175 | 6000 | 0 | 80% | 4800 | 1200 | 0 | 0 | Base ETC follows remaining approved Budget.
WP2_COMMS | RUSI - participant materials and regional communications | WP2 | Directly Incurred | Other Directly Incurred | 2000.01 | 290 | 0 | -150 | 1560.01 | 1850.01 | 150 | 80% | 1480.008 | 370.002 | 120 | 30 | Illustrative risk/saving adjustment; review monthly.
WP2_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP2 | Indirect | Indirect | 13800.72 | 1905.26 | 0 | 0 | 11895.46 | 13800.72 | 0 | 80% | 11040.576 | 2760.144 | 0 | 0 | Base ETC follows remaining approved Budget.
WP2_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP2 | Directly Allocated | Estates | 1758.72 | 242.79 | 0 | 0 | 1515.93 | 1758.72 | 0 | 80% | 1406.976 | 351.744 | 0 | 0 | Base ETC follows remaining approved Budget.
WP3_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP3 | Directly Allocated | Staff | 9420 | 1300.49 | 0 | 0 | 8119.51 | 9420 | 0 | 80% | 7536 | 1884 | 0 | 0 | Base ETC follows remaining approved Budget.
WP3_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP3 | Directly Allocated | Staff | 4342.5 | 599.52 | 0 | 0 | 3742.98 | 4342.5 | 0 | 80% | 3474 | 868.5 | 0 | 0 | Base ETC follows remaining approved Budget.
WP3_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP3 | Directly Allocated | Staff | 4455 | 615.04 | 0 | 0 | 3839.96 | 4455 | 0 | 80% | 3564 | 891 | 0 | 0 | Base ETC follows remaining approved Budget.
WP3_TRAVEL | RUSI - London-team and Latin America stakeholder travel/subsistence | WP3 | Directly Incurred | Travel & Subsistence | 12000 | 1390 | 2100 | 900 | 9410 | 12900 | -900 | 80% | 10320 | 2580 | -720 | -180 | Illustrative risk/saving adjustment; review monthly.
WP3_CONSULT | RUSI - Latin America-based regional network broker consultant | WP3 | Directly Incurred | Other Directly Incurred | 12600 | 1750 | 2450 | 0 | 8400 | 12600 | 0 | 80% | 10080 | 2520 | 0 | 0 | Base ETC follows remaining approved Budget.
WP3_CONF | RUSI - five-day Latin America hub conference (hub to be confirmed) | WP3 | Directly Incurred | Other Directly Incurred | 16000 | 0 | 0 | 0 | 16000 | 16000 | 0 | 80% | 12800 | 3200 | 0 | 0 | Base ETC follows remaining approved Budget.
WP3_WORKSHOP | RUSI - Latin America practitioner-policy-academic workshops | WP3 | Directly Incurred | Other Directly Incurred | 6000 | 865 | 1000 | 0 | 4135 | 6000 | 0 | 80% | 4800 | 1200 | 0 | 0 | Base ETC follows remaining approved Budget.
WP3_COMMS | RUSI - Spanish/Portuguese materials and regional communications | WP3 | Directly Incurred | Other Directly Incurred | 2000.01 | 345 | 0 | -150 | 1505.01 | 1850.01 | 150 | 80% | 1480.008 | 370.002 | 120 | 30 | Illustrative risk/saving adjustment; review monthly.
WP3_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP3 | Indirect | Indirect | 22426.17 | 3096.06 | 0 | 0 | 19330.11 | 22426.17 | 0 | 80% | 17940.936 | 4485.234 | 0 | 0 | Base ETC follows remaining approved Budget.
WP3_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP3 | Directly Allocated | Estates | 2857.92 | 394.56 | 0 | 0 | 2463.36 | 2857.92 | 0 | 80% | 2286.336 | 571.584 | 0 | 0 | Base ETC follows remaining approved Budget.

## 4) Monthly Update
Monthly update centre
[Optional] Instructions for automated transaction import process (in Power Query)
1. Configure a staged import (blue cells)
Parameter | Value |  | Staging control | Value
Source CSV path | SHOC2_transaction_import_template.csv |  | Loaded rows | 0
Staged Batch ID | STAGED-2026-09 |  | Loaded amount | 0
Source control total |  |  | Control difference
Staged reporting cut-off | 2026-08-31 |  | Rows READY | 0
Query behaviour | Manual refresh only; never refresh on open |  | Rows with issues | 0
|  |  | Promotion | Manual after review
2. Explicit refresh, review and promotion
Step | Action |  | What success looks like
1 | Export a cumulative or monthly-delta CSV using the schema shown below. |  | Dates and Amount GBP are true values; every transaction has a stable ID.
2 | Enter the full CSV path, unique Batch ID, source control total and cut-off above. |  | The inputs remain visible and auditable.
3 | In Excel: Data → Refresh All, or refresh only SHOC2_Transaction_Import. |  | The staging table is populated; the saved dashboard does not change.
4 | Filter Import Status and fix all non-READY rows at source or through an authorised mapping. |  | READY rows equal the source row count and the amount reconciles to the control total.
5 | Copy staging columns A:K and paste values into the blue A:K columns of Actuals Ledger. |  | Ledger Row Status is OK for every pasted record.
6 | Add/check the matching Refresh Log row as STAGED; compare rows and amount; document reviewer and notes. |  | Difference is zero and no ledger exception remains.
7 | Change Refresh Log Status to APPROVED, update Dashboard cut-off, verify Checks PASS, and save. |  | The new batch appears across dashboard, detail and controls.
Expected CSV headers: Transaction ID ¦ Accounting Date ¦ Incurred Date ¦ Description ¦ Amount GBP ¦ Budget Item ID ¦ Evidence Ref ¦ Source Ref ¦ Reversal Of ¦ Notes. The query adds the staged Batch ID and Import Status.
3. One-time setup: create the optional Power Query staging import
For ease of use immediately from the download link on my website, the workbook doesn't contain any queries pre-stored, so as to minimise the scope for potential compatibility issues associated with external connections, organisational privacy permissions, or similar. The manual route (set out above) achieves the same result without this functionality, and is broadly recommended for demo purposes. To enable automated transaction imports, follow the below steps and Save the file.
Step | Follow these steps in Excel
PQ1 | Save the accompanying template .CSV (that shipped alongside this workbook somewhere stable, then put its full path in cell B7 above.
PQ2 | Data → Get Data → From File → From Text/CSV. Select that CSV. Click Transform Data (not Load).
PQ3 | In the editor, rename the query to SHOC2_Transaction_Import.
PQ4 | Set column types: Transaction ID, Description, Budget Item ID, Evidence Ref, Source Ref, Reversal Of and Notes to Text; Accounting Date and Incurred Date to Date; Amount GBP to Decimal Number.
PQ5 | Add Column → Custom Column, name it Batch ID, formula: = Excel.CurrentWorkbook(){[Name="StagedBatchID"]}[Content]{0}[Column1]
PQ6 | Add Column → Custom Column, name it Import Status, formula: = if [Transaction ID] = null then "MISSING ID" else if [Amount GBP] = null then "MISSING AMOUNT" else if [Incurred Date] = null then "MISSING DATE" else if [Budget Item ID] = null then "UNMAPPED" else "READY"
PQ7 | Before closing: select cell B8, and in the Name Box (left of the formula bar) type StagedBatchID and press Enter.
PQ8 | Home → Close & Load To… → Table → Existing worksheet → =$A$48 on this sheet. Click OK.
PQ9 | Right-click the query in Queries & Connections → Properties. UNTICK "Refresh data when opening the file" and UNTICK "Enable background refresh". Tick "Refresh this connection on Refresh All". OK.
PQ10 | Save the workbook. Test it: close, reopen with connections disabled, and confirm the Dashboard is unchanged and still reads PASS.
4. Staging output area - review only; do not type into a refresh output
Load the query to cell A48 of this sheet (step PQ8). Until then this area is intentionally empty and the workbook is complete without it. The staging controls above read rows 49-548.
Transaction ID | Batch ID | Accounting Date | Incurred Date | Description | Amount GBP | Budget Item ID | Evidence Ref | Source Ref | Reversal Of | Notes | Import Status

## 5) Refresh Log
Refresh and approval log
Audit gate for actuals, allocations and commitments; only APPROVED batches feed reporting
Status value determines whether a newly imported transaction (batch) is added to ledger of actual costs. Enter 'STAGED' while still reviewing. Resolve ledger exceptions, record reviewer/notes, then change to APPROVED.
Batch ID | Data Type | Source File/System | Cut-off | Refresh Timestamp | Status | Expected Rows | Loaded Rows | Source Control £ | Loaded Amount £ | Difference £ | Reviewer | Notes
DEMO-2026-08 | Actuals | ILLUSTRATIVE_GL_2026-08.csv | 2026-08-31 | 2026-09-01 09:00 | APPROVED | 56 | 56 | 13751.2 | 13751.2 | 0 | Portfolio reviewer | Hypothetical cumulative transaction extract through 31 August 2026.
ALLOC-2026-08 | Allocations | ILLUSTRATIVE_ALLOC_SCHEDULE_2026-08 | 2026-08-31 | 2026-09-01 09:00 | APPROVED | 75 | 75 | 21837.92 | 21837.92 | 0 | Portfolio reviewer | Illustrative allocation postings; not DI evidence.
COMMIT-2026-08 | Commitments | ILLUSTRATIVE_COMMITMENT_REGISTER_2026-08 | 2026-08-31 | 2026-09-01 09:00 | APPROVED | 10 | 10 | 27200 | 27200 | 0 | Portfolio reviewer | Hypothetical open commitments as at 31 August 2026.

## 6) Actuals Ledger - DI Costs
Accepted DI transaction ledger
One transaction/source per row. Blue columns are pasted/imported values from previous batches. Adjacent formulas map and validate against standardised fCE headings
Only accepted Directly Incurred transactions belong here. DA staff, estates and indirect charges are held on the separate Allocations sheet. Negative values require a valid Reversal Of transaction ID.
Transaction ID | Batch ID | Accounting Date | Incurred Date | Description | Amount GBP | Budget Item ID | Evidence Ref | Source Ref | Reversal Of | Notes | Batch Approved | Work Package | fEC Heading | fEC Subheading | Funding Rate | Row Status | Included GBP | Included UKRI | Included RUSI
DEMO-2026-04-001 | DEMO-2026-08 | 2026-04-30 | 2026-04-12 | UK rail and local travel for network scoping | 212.4 | WP1_TRAVEL | EVID-202604-001 | ILLUSTRATIVE_GL_2026-08.csv |  | Hypothetical portfolio transaction; not RUSI accounting data. | YES | WP1 | Directly Incurred | Travel & Subsistence | 80% | OK | 212.4 | 169.92 | 42.48
DEMO-2026-04-002 | DEMO-2026-08 | 2026-04-30 | 2026-04-18 | Digital briefing template and launch communications | 185 | WP1_COMMS | EVID-202604-002 | ILLUSTRATIVE_GL_2026-08.csv |  | Hypothetical portfolio transaction; not RUSI accounting data. | YES | WP1 | Directly Incurred | Other Directly Incurred | 80% | OK | 185 | 148 | 37
DEMO-2026-04-003 | DEMO-2026-08 | 2026-04-30 | 2026-04-22 | Nairobi network broker - one consultant day | 350 | WP2_CONSULT | EVID-202604-003 | ILLUSTRATIVE_GL_2026-08.csv |  | Hypothetical portfolio transaction; not RUSI accounting data. | YES | WP2 | Directly Incurred | Other Directly Incurred | 80% | OK | 350 | 280 | 70
DEMO-2026-04-004 | DEMO-2026-08 | 2026-04-30 | 2026-04-24 | Regional stakeholder local travel | 145 | WP2_TRAVEL | EVID-202604-004 | ILLUSTRATIVE_GL_2026-08.csv |  | Hypothetical portfolio transaction; not RUSI accounting data. | YES | WP2 | Directly Incurred | Travel & Subsistence | 80% | OK | 145 | 116 | 29
DEMO-2026-04-005 | DEMO-2026-08 | 2026-04-30 | 2026-04-26 | Participant briefing materials | 75 | WP2_COMMS | EVID-202604-005 | ILLUSTRATIVE_GL_2026-08.csv |  | Hypothetical portfolio transaction; not RUSI accounting data. | YES | WP2 | Directly Incurred | Other Directly Incurred | 80% | OK | 75 | 60 | 15
DEMO-2026-04-006 | DEMO-2026-08 | 2026-04-30 | 2026-04-21 | Latin America network broker - one consultant day | 350 | WP3_CONSULT | EVID-202604-006 | ILLUSTRATIVE_GL_2026-08.csv |  | Hypothetical portfolio transaction; not RUSI accounting data. | YES | WP3 | Directly Incurred | Other Directly Incurred | 80% | OK | 350 | 280 | 70
DEMO-2026-04-007 | DEMO-2026-08 | 2026-04-30 | 2026-04-27 | Spanish-language stakeholder materials | 95 | WP3_COMMS | EVID-202604-007 | ILLUSTRATIVE_GL_2026-08.csv |  | Hypothetical portfolio transaction; not RUSI accounting data. | YES | WP3 | Directly Incurred | Other Directly Incurred | 80% | OK | 95 | 76 | 19
DEMO-2026-05-008 | DEMO-2026-08 | 2026-05-31 | 2026-05-06 | UK stakeholder rail travel and subsistence | 318.2 | WP1_TRAVEL | EVID-202605-008 | ILLUSTRATIVE_GL_2026-08.csv |  | Hypothetical portfolio transaction; not RUSI accounting data. | YES | WP1 | Directly Incurred | Travel & Subsistence | 80% | OK | 318.2 | 254.56 | 63.64
DEMO-2026-05-009 | DEMO-2026-08 | 2026-05-31 | 2026-05-11 | UK workshop room hire and catering | 620 | WP1_WORKSHOP | EVID-202605-009 | ILLUSTRATIVE_GL_2026-08.csv |  | Hypothetical portfolio transaction; not RUSI accounting data. | YES | WP1 | Directly Incurred | Other Directly Incurred | 80% | OK | 620 | 496 | 124
DEMO-2026-05-010 | DEMO-2026-08 | 2026-05-31 | 2026-05-14 | Hybrid panel technical support | 240 | WP1_PANEL | EVID-202605-010 | ILLUSTRATIVE_GL_2026-08.csv |  | Hypothetical portfolio transaction; not RUSI accounting data. | YES | WP1 | Directly Incurred | Other Directly Incurred | 80% | OK | 240 | 192 | 48
DEMO-2026-05-011 | DEMO-2026-08 | 2026-05-31 | 2026-05-18 | Digital event materials | 110 | WP1_COMMS | EVID-202605-011 | ILLUSTRATIVE_GL_2026-08.csv |  | Hypothetical portfolio transaction; not RUSI accounting data. | YES | WP1 | Directly Incurred | Other Directly Incurred | 80% | OK | 110 | 88 | 22
DEMO-2026-05-012 | DEMO-2026-08 | 2026-05-31 | 2026-05-20 | Nairobi network broker - one consultant day | 350 | WP2_CONSULT | EVID-202605-012 | ILLUSTRATIVE_GL_2026-08.csv |  | Hypothetical portfolio transaction; not RUSI accounting data. | YES | WP2 | Directly Incurred | Other Directly Incurred | 80% | OK | 350 | 280 | 70
DEMO-2026-05-013 | DEMO-2026-08 | 2026-05-31 | 2026-05-22 | East Africa stakeholder local travel | 285 | WP2_TRAVEL | EVID-202605-013 | ILLUSTRATIVE_GL_2026-08.csv |  | Hypothetical portfolio transaction; not RUSI accounting data. | YES | WP2 | Directly Incurred | Travel & Subsistence | 80% | OK | 285 | 228 | 57
DEMO-2026-05-014 | DEMO-2026-08 | 2026-05-31 | 2026-05-25 | Workshop venue scoping and facilitation | 190 | WP2_WORKSHOP | EVID-202605-014 | ILLUSTRATIVE_GL_2026-08.csv |  | Hypothetical portfolio transaction; not RUSI accounting data. | YES | WP2 | Directly Incurred | Other Directly Incurred | 80% | OK | 190 | 152 | 38
DEMO-2026-05-015 | DEMO-2026-08 | 2026-05-31 | 2026-05-26 | Regional participant materials | 55 | WP2_COMMS | EVID-202605-015 | ILLUSTRATIVE_GL_2026-08.csv |  | Hypothetical portfolio transaction; not RUSI accounting data. | YES | WP2 | Directly Incurred | Other Directly Incurred | 80% | OK | 55 | 44 | 11
DEMO-2026-05-016 | DEMO-2026-08 | 2026-05-31 | 2026-05-19 | Latin America network broker - one consultant day | 350 | WP3_CONSULT | EVID-202605-016 | ILLUSTRATIVE_GL_2026-08.csv |  | Hypothetical portfolio transaction; not RUSI accounting data. | YES | WP3 | Directly Incurred | Other Directly Incurred | 80% | OK | 350 | 280 | 70
DEMO-2026-05-017 | DEMO-2026-08 | 2026-05-31 | 2026-05-21 | Regional stakeholder local travel | 160 | WP3_TRAVEL | EVID-202605-017 | ILLUSTRATIVE_GL_2026-08.csv |  | Hypothetical portfolio transaction; not RUSI accounting data. | YES | WP3 | Directly Incurred | Travel & Subsistence | 80% | OK | 160 | 128 | 32
DEMO-2026-05-018 | DEMO-2026-08 | 2026-05-31 | 2026-05-24 | Workshop planning session costs | 220 | WP3_WORKSHOP | EVID-202605-018 | ILLUSTRATIVE_GL_2026-08.csv |  | Hypothetical portfolio transaction; not RUSI accounting data. | YES | WP3 | Directly Incurred | Other Directly Incurred | 80% | OK | 220 | 176 | 44
DEMO-2026-05-019 | DEMO-2026-08 | 2026-05-31 | 2026-05-27 | Bilingual participant materials | 60 | WP3_COMMS | EVID-202605-019 | ILLUSTRATIVE_GL_2026-08.csv |  | Hypothetical portfolio transaction; not RUSI accounting data. | YES | WP3 | Directly Incurred | Other Directly Incurred | 80% | OK | 60 | 48 | 12
DEMO-2026-06-020 | DEMO-2026-08 | 2026-06-30 | 2026-06-07 | UK regional network rail travel | 275.6 | WP1_TRAVEL | EVID-202606-020 | ILLUSTRATIVE_GL_2026-08.csv |  | Hypothetical portfolio transaction; not RUSI accounting data. | YES | WP1 | Directly Incurred | Travel & Subsistence | 80% | OK | 275.6 | 220.48 | 55.12
DEMO-2026-06-021 | DEMO-2026-08 | 2026-06-30 | 2026-06-10 | UK practitioner workshop costs | 540 | WP1_WORKSHOP | EVID-202606-021 | ILLUSTRATIVE_GL_2026-08.csv |  | Hypothetical portfolio transaction; not RUSI accounting data. | YES | WP1 | Directly Incurred | Other Directly Incurred | 80% | OK | 540 | 432 | 108
DEMO-2026-06-022 | DEMO-2026-08 | 2026-06-30 | 2026-06-13 | Roundtable audio-visual support | 185 | WP1_PANEL | EVID-202606-022 | ILLUSTRATIVE_GL_2026-08.csv |  | Hypothetical portfolio transaction; not RUSI accounting data. | YES | WP1 | Directly Incurred | Other Directly Incurred | 80% | OK | 185 | 148 | 37
DEMO-2026-06-023 | DEMO-2026-08 | 2026-06-30 | 2026-06-16 | Knowledge product layout support | 90 | WP1_COMMS | EVID-202606-023 | ILLUSTRATIVE_GL_2026-08.csv |  | Hypothetical portfolio transaction; not RUSI accounting data. | YES | WP1 | Directly Incurred | Other Directly Incurred | 80% | OK | 90 | 72 | 18
DEMO-2026-06-024 | DEMO-2026-08 | 2026-06-30 | 2026-06-18 | Nairobi network broker - one consultant day | 350 | WP2_CONSULT | EVID-202606-024 | ILLUSTRATIVE_GL_2026-08.csv |  | Hypothetical portfolio transaction; not RUSI accounting data. | YES | WP2 | Directly Incurred | Other Directly Incurred | 80% | OK | 350 | 280 | 70
DEMO-2026-06-025 | DEMO-2026-08 | 2026-06-30 | 2026-06-20 | East Africa partner meeting travel | 410 | WP2_TRAVEL | EVID-202606-025 | ILLUSTRATIVE_GL_2026-08.csv |  | Hypothetical portfolio transaction; not RUSI accounting data. | YES | WP2 | Directly Incurred | Travel & Subsistence | 80% | OK | 410 | 328 | 82
DEMO-2026-06-026 | DEMO-2026-08 | 2026-06-30 | 2026-06-23 | Workshop facilitation materials | 230 | WP2_WORKSHOP | EVID-202606-026 | ILLUSTRATIVE_GL_2026-08.csv |  | Hypothetical portfolio transaction; not RUSI accounting data. | YES | WP2 | Directly Incurred | Other Directly Incurred | 80% | OK | 230 | 184 | 46
DEMO-2026-06-027 | DEMO-2026-08 | 2026-06-30 | 2026-06-25 | Regional communications support | 48 | WP2_COMMS | EVID-202606-027 | ILLUSTRATIVE_GL_2026-08.csv |  | Hypothetical portfolio transaction; not RUSI accounting data. | YES | WP2 | Directly Incurred | Other Directly Incurred | 80% | OK | 48 | 38.4 | 9.6
DEMO-2026-06-028 | DEMO-2026-08 | 2026-06-30 | 2026-06-17 | Latin America network broker - one consultant day | 350 | WP3_CONSULT | EVID-202606-028 | ILLUSTRATIVE_GL_2026-08.csv |  | Hypothetical portfolio transaction; not RUSI accounting data. | YES | WP3 | Directly Incurred | Other Directly Incurred | 80% | OK | 350 | 280 | 70
DEMO-2026-06-029 | DEMO-2026-08 | 2026-06-30 | 2026-06-21 | Latin America partner meeting travel | 330 | WP3_TRAVEL | EVID-202606-029 | ILLUSTRATIVE_GL_2026-08.csv |  | Hypothetical portfolio transaction; not RUSI accounting data. | YES | WP3 | Directly Incurred | Travel & Subsistence | 80% | OK | 330 | 264 | 66
DEMO-2026-06-030 | DEMO-2026-08 | 2026-06-30 | 2026-06-24 | Workshop planning and materials | 210 | WP3_WORKSHOP | EVID-202606-030 | ILLUSTRATIVE_GL_2026-08.csv |  | Hypothetical portfolio transaction; not RUSI accounting data. | YES | WP3 | Directly Incurred | Other Directly Incurred | 80% | OK | 210 | 168 | 42
DEMO-2026-06-031 | DEMO-2026-08 | 2026-06-30 | 2026-06-27 | Translation and digital materials | 70 | WP3_COMMS | EVID-202606-031 | ILLUSTRATIVE_GL_2026-08.csv |  | Hypothetical portfolio transaction; not RUSI accounting data. | YES | WP3 | Directly Incurred | Other Directly Incurred | 80% | OK | 70 | 56 | 14
DEMO-2026-07-032 | DEMO-2026-08 | 2026-07-31 | 2026-07-06 | UK stakeholder engagement travel | 295 | WP1_TRAVEL | EVID-202607-032 | ILLUSTRATIVE_GL_2026-08.csv |  | Hypothetical portfolio transaction; not RUSI accounting data. | YES | WP1 | Directly Incurred | Travel & Subsistence | 80% | OK | 295 | 236 | 59
DEMO-2026-07-033 | DEMO-2026-08 | 2026-07-31 | 2026-07-09 | Regional workshop delivery costs | 480 | WP1_WORKSHOP | EVID-202607-033 | ILLUSTRATIVE_GL_2026-08.csv |  | Hypothetical portfolio transaction; not RUSI accounting data. | YES | WP1 | Directly Incurred | Other Directly Incurred | 80% | OK | 480 | 384 | 96
DEMO-2026-07-034 | DEMO-2026-08 | 2026-07-31 | 2026-07-12 | Practitioner roundtable support | 160 | WP1_PANEL | EVID-202607-034 | ILLUSTRATIVE_GL_2026-08.csv |  | Hypothetical portfolio transaction; not RUSI accounting data. | YES | WP1 | Directly Incurred | Other Directly Incurred | 80% | OK | 160 | 128 | 32
DEMO-2026-07-035 | DEMO-2026-08 | 2026-07-31 | 2026-07-15 | Knowledge product graphics | 75 | WP1_COMMS | EVID-202607-035 | ILLUSTRATIVE_GL_2026-08.csv |  | Hypothetical portfolio transaction; not RUSI accounting data. | YES | WP1 | Directly Incurred | Other Directly Incurred | 80% | OK | 75 | 60 | 15
DEMO-2026-07-036 | DEMO-2026-08 | 2026-07-31 | 2026-07-17 | Nairobi network broker - one consultant day | 350 | WP2_CONSULT | EVID-202607-036 | ILLUSTRATIVE_GL_2026-08.csv |  | Hypothetical portfolio transaction; not RUSI accounting data. | YES | WP2 | Directly Incurred | Other Directly Incurred | 80% | OK | 350 | 280 | 70
DEMO-2026-07-037 | DEMO-2026-08 | 2026-07-31 | 2026-07-20 | East Africa stakeholder travel | 390 | WP2_TRAVEL | EVID-202607-037 | ILLUSTRATIVE_GL_2026-08.csv |  | Hypothetical portfolio transaction; not RUSI accounting data. | YES | WP2 | Directly Incurred | Travel & Subsistence | 80% | OK | 390 | 312 | 78
DEMO-2026-07-038 | DEMO-2026-08 | 2026-07-31 | 2026-07-23 | Workshop preparation costs | 165 | WP2_WORKSHOP | EVID-202607-038 | ILLUSTRATIVE_GL_2026-08.csv |  | Hypothetical portfolio transaction; not RUSI accounting data. | YES | WP2 | Directly Incurred | Other Directly Incurred | 80% | OK | 165 | 132 | 33
DEMO-2026-07-039 | DEMO-2026-08 | 2026-07-31 | 2026-07-25 | Regional communications materials | 52 | WP2_COMMS | EVID-202607-039 | ILLUSTRATIVE_GL_2026-08.csv |  | Hypothetical portfolio transaction; not RUSI accounting data. | YES | WP2 | Directly Incurred | Other Directly Incurred | 80% | OK | 52 | 41.6 | 10.4
DEMO-2026-07-040 | DEMO-2026-08 | 2026-07-31 | 2026-07-18 | Latin America network broker - one consultant day | 350 | WP3_CONSULT | EVID-202607-040 | ILLUSTRATIVE_GL_2026-08.csv |  | Hypothetical portfolio transaction; not RUSI accounting data. | YES | WP3 | Directly Incurred | Other Directly Incurred | 80% | OK | 350 | 280 | 70
DEMO-2026-07-041 | DEMO-2026-08 | 2026-07-31 | 2026-07-21 | Latin America stakeholder travel | 420 | WP3_TRAVEL | EVID-202607-041 | ILLUSTRATIVE_GL_2026-08.csv |  | Hypothetical portfolio transaction; not RUSI accounting data. | YES | WP3 | Directly Incurred | Travel & Subsistence | 80% | OK | 420 | 336 | 84
DEMO-2026-07-042 | DEMO-2026-08 | 2026-07-31 | 2026-07-24 | Workshop preparation costs | 175 | WP3_WORKSHOP | EVID-202607-042 | ILLUSTRATIVE_GL_2026-08.csv |  | Hypothetical portfolio transaction; not RUSI accounting data. | YES | WP3 | Directly Incurred | Other Directly Incurred | 80% | OK | 175 | 140 | 35
DEMO-2026-07-043 | DEMO-2026-08 | 2026-07-31 | 2026-07-27 | Bilingual communications materials | 55 | WP3_COMMS | EVID-202607-043 | ILLUSTRATIVE_GL_2026-08.csv |  | Hypothetical portfolio transaction; not RUSI accounting data. | YES | WP3 | Directly Incurred | Other Directly Incurred | 80% | OK | 55 | 44 | 11
DEMO-2026-08-044 | DEMO-2026-08 | 2026-08-31 | 2026-08-05 | UK network engagement travel | 340 | WP1_TRAVEL | EVID-202608-044 | ILLUSTRATIVE_GL_2026-08.csv |  | Hypothetical portfolio transaction; not RUSI accounting data. | YES | WP1 | Directly Incurred | Travel & Subsistence | 80% | OK | 340 | 272 | 68
DEMO-2026-08-045 | DEMO-2026-08 | 2026-08-31 | 2026-08-09 | UK workshop delivery costs | 510 | WP1_WORKSHOP | EVID-202608-045 | ILLUSTRATIVE_GL_2026-08.csv |  | Hypothetical portfolio transaction; not RUSI accounting data. | YES | WP1 | Directly Incurred | Other Directly Incurred | 80% | OK | 510 | 408 | 102
DEMO-2026-08-046 | DEMO-2026-08 | 2026-08-31 | 2026-08-12 | Hybrid practitioner panel support | 205 | WP1_PANEL | EVID-202608-046 | ILLUSTRATIVE_GL_2026-08.csv |  | Hypothetical portfolio transaction; not RUSI accounting data. | YES | WP1 | Directly Incurred | Other Directly Incurred | 80% | OK | 205 | 164 | 41
DEMO-2026-08-047 | DEMO-2026-08 | 2026-08-31 | 2026-08-15 | Launch knowledge product design | 115 | WP1_COMMS | EVID-202608-047 | ILLUSTRATIVE_GL_2026-08.csv |  | Hypothetical portfolio transaction; not RUSI accounting data. | YES | WP1 | Directly Incurred | Other Directly Incurred | 80% | OK | 115 | 92 | 23
DEMO-2026-08-048 | DEMO-2026-08 | 2026-08-31 | 2026-08-17 | Nairobi network broker - one consultant day | 350 | WP2_CONSULT | EVID-202608-048 | ILLUSTRATIVE_GL_2026-08.csv |  | Hypothetical portfolio transaction; not RUSI accounting data. | YES | WP2 | Directly Incurred | Other Directly Incurred | 80% | OK | 350 | 280 | 70
DEMO-2026-08-049 | DEMO-2026-08 | 2026-08-31 | 2026-08-20 | East Africa partner travel and subsistence | 435 | WP2_TRAVEL | EVID-202608-049 | ILLUSTRATIVE_GL_2026-08.csv |  | Hypothetical portfolio transaction; not RUSI accounting data. | YES | WP2 | Directly Incurred | Travel & Subsistence | 80% | OK | 435 | 348 | 87
DEMO-2026-08-050 | DEMO-2026-08 | 2026-08-31 | 2026-08-23 | Workshop planning and facilitation | 240 | WP2_WORKSHOP | EVID-202608-050 | ILLUSTRATIVE_GL_2026-08.csv |  | Hypothetical portfolio transaction; not RUSI accounting data. | YES | WP2 | Directly Incurred | Other Directly Incurred | 80% | OK | 240 | 192 | 48
DEMO-2026-08-051 | DEMO-2026-08 | 2026-08-31 | 2026-08-25 | Participant communications materials | 60 | WP2_COMMS | EVID-202608-051 | ILLUSTRATIVE_GL_2026-08.csv |  | Hypothetical portfolio transaction; not RUSI accounting data. | YES | WP2 | Directly Incurred | Other Directly Incurred | 80% | OK | 60 | 48 | 12
DEMO-2026-08-052 | DEMO-2026-08 | 2026-08-31 | 2026-08-18 | Latin America network broker - one consultant day | 350 | WP3_CONSULT | EVID-202608-052 | ILLUSTRATIVE_GL_2026-08.csv |  | Hypothetical portfolio transaction; not RUSI accounting data. | YES | WP3 | Directly Incurred | Other Directly Incurred | 80% | OK | 350 | 280 | 70
DEMO-2026-08-053 | DEMO-2026-08 | 2026-08-31 | 2026-08-21 | Latin America partner travel and subsistence | 480 | WP3_TRAVEL | EVID-202608-053 | ILLUSTRATIVE_GL_2026-08.csv |  | Hypothetical portfolio transaction; not RUSI accounting data. | YES | WP3 | Directly Incurred | Travel & Subsistence | 80% | OK | 480 | 384 | 96
DEMO-2026-08-054 | DEMO-2026-08 | 2026-08-31 | 2026-08-24 | Workshop planning and facilitation | 260 | WP3_WORKSHOP | EVID-202608-054 | ILLUSTRATIVE_GL_2026-08.csv |  | Hypothetical portfolio transaction; not RUSI accounting data. | YES | WP3 | Directly Incurred | Other Directly Incurred | 80% | OK | 260 | 208 | 52
DEMO-2026-08-055 | DEMO-2026-08 | 2026-08-31 | 2026-08-27 | Translation and digital materials | 65 | WP3_COMMS | EVID-202608-055 | ILLUSTRATIVE_GL_2026-08.csv |  | Hypothetical portfolio transaction; not RUSI accounting data. | YES | WP3 | Directly Incurred | Other Directly Incurred | 80% | OK | 65 | 52 | 13
DEMO-2026-08-056 | DEMO-2026-08 | 2026-08-31 | 2026-08-29 | Rail ticket refund/credit note | -85 | WP1_TRAVEL | CRN-202608-056 | ILLUSTRATIVE_GL_2026-08.csv | DEMO-2026-05-008 | Hypothetical portfolio transaction; not RUSI accounting data. | YES | WP1 | Directly Incurred | Travel & Subsistence | 80% | OK | -85 | -68 | -17

## 7) Allocations - DA Costs
Recognised allocation ledger
Directly Allocated (DA) staff, estates and indirect management costs.
The below are arbitrary transaction records produced for the purposes of this model demonstration.
Allocation ID | Batch ID | Period End | Budget Item ID | Amount GBP | Allocation Basis | Source Ref | Notes | Batch Approved | Work Package | fEC Heading | fEC Subheading | Funding Rate | Row Status | Included GBP | Included UKRI | Included RUSI
ALLOC-202604-WP1_S01 | ALLOC-2026-08 | 2026-04-30 | WP1_S01 | 317.27 | Illustrative monthly management allocation; not DI transaction evidence | ILLUSTRATIVE_ALLOC_SCHEDULE_2026-08 | Applied at 97% of the phased monthly amount for demonstration. | YES | WP1 | Directly Allocated | Staff | 80% | OK | 317.27 | 253.816 | 63.454
ALLOC-202605-WP1_S01 | ALLOC-2026-08 | 2026-05-31 | WP1_S01 | 327.08 | Illustrative monthly management allocation; not DI transaction evidence | ILLUSTRATIVE_ALLOC_SCHEDULE_2026-08 | Applied at 100% of the phased monthly amount for demonstration. | YES | WP1 | Directly Allocated | Staff | 80% | OK | 327.08 | 261.664 | 65.416
ALLOC-202606-WP1_S01 | ALLOC-2026-08 | 2026-06-30 | WP1_S01 | 323.81 | Illustrative monthly management allocation; not DI transaction evidence | ILLUSTRATIVE_ALLOC_SCHEDULE_2026-08 | Applied at 99% of the phased monthly amount for demonstration. | YES | WP1 | Directly Allocated | Staff | 80% | OK | 323.81 | 259.048 | 64.762
ALLOC-202607-WP1_S01 | ALLOC-2026-08 | 2026-07-31 | WP1_S01 | 330.35 | Illustrative monthly management allocation; not DI transaction evidence | ILLUSTRATIVE_ALLOC_SCHEDULE_2026-08 | Applied at 101% of the phased monthly amount for demonstration. | YES | WP1 | Directly Allocated | Staff | 80% | OK | 330.35 | 264.28 | 66.07
ALLOC-202608-WP1_S01 | ALLOC-2026-08 | 2026-08-31 | WP1_S01 | 327.08 | Illustrative monthly management allocation; not DI transaction evidence | ILLUSTRATIVE_ALLOC_SCHEDULE_2026-08 | Applied at 100% of the phased monthly amount for demonstration. | YES | WP1 | Directly Allocated | Staff | 80% | OK | 327.08 | 261.664 | 65.416
ALLOC-202604-WP1_S02 | ALLOC-2026-08 | 2026-04-30 | WP1_S02 | 351.02 | Illustrative monthly management allocation; not DI transaction evidence | ILLUSTRATIVE_ALLOC_SCHEDULE_2026-08 | Applied at 97% of the phased monthly amount for demonstration. | YES | WP1 | Directly Allocated | Staff | 80% | OK | 351.02 | 280.816 | 70.204
ALLOC-202605-WP1_S02 | ALLOC-2026-08 | 2026-05-31 | WP1_S02 | 361.88 | Illustrative monthly management allocation; not DI transaction evidence | ILLUSTRATIVE_ALLOC_SCHEDULE_2026-08 | Applied at 100% of the phased monthly amount for demonstration. | YES | WP1 | Directly Allocated | Staff | 80% | OK | 361.88 | 289.504 | 72.376
ALLOC-202606-WP1_S02 | ALLOC-2026-08 | 2026-06-30 | WP1_S02 | 358.26 | Illustrative monthly management allocation; not DI transaction evidence | ILLUSTRATIVE_ALLOC_SCHEDULE_2026-08 | Applied at 99% of the phased monthly amount for demonstration. | YES | WP1 | Directly Allocated | Staff | 80% | OK | 358.26 | 286.608 | 71.652
ALLOC-202607-WP1_S02 | ALLOC-2026-08 | 2026-07-31 | WP1_S02 | 365.49 | Illustrative monthly management allocation; not DI transaction evidence | ILLUSTRATIVE_ALLOC_SCHEDULE_2026-08 | Applied at 101% of the phased monthly amount for demonstration. | YES | WP1 | Directly Allocated | Staff | 80% | OK | 365.49 | 292.392 | 73.098
ALLOC-202608-WP1_S02 | ALLOC-2026-08 | 2026-08-31 | WP1_S02 | 361.88 | Illustrative monthly management allocation; not DI transaction evidence | ILLUSTRATIVE_ALLOC_SCHEDULE_2026-08 | Applied at 100% of the phased monthly amount for demonstration. | YES | WP1 | Directly Allocated | Staff | 80% | OK | 361.88 | 289.504 | 72.376
ALLOC-202604-WP1_S03 | ALLOC-2026-08 | 2026-04-30 | WP1_S03 | 360.11 | Illustrative monthly management allocation; not DI transaction evidence | ILLUSTRATIVE_ALLOC_SCHEDULE_2026-08 | Applied at 97% of the phased monthly amount for demonstration. | YES | WP1 | Directly Allocated | Staff | 80% | OK | 360.11 | 288.088 | 72.022
ALLOC-202605-WP1_S03 | ALLOC-2026-08 | 2026-05-31 | WP1_S03 | 371.25 | Illustrative monthly management allocation; not DI transaction evidence | ILLUSTRATIVE_ALLOC_SCHEDULE_2026-08 | Applied at 100% of the phased monthly amount for demonstration. | YES | WP1 | Directly Allocated | Staff | 80% | OK | 371.25 | 297 | 74.25
ALLOC-202606-WP1_S03 | ALLOC-2026-08 | 2026-06-30 | WP1_S03 | 367.54 | Illustrative monthly management allocation; not DI transaction evidence | ILLUSTRATIVE_ALLOC_SCHEDULE_2026-08 | Applied at 99% of the phased monthly amount for demonstration. | YES | WP1 | Directly Allocated | Staff | 80% | OK | 367.54 | 294.032 | 73.508
ALLOC-202607-WP1_S03 | ALLOC-2026-08 | 2026-07-31 | WP1_S03 | 374.96 | Illustrative monthly management allocation; not DI transaction evidence | ILLUSTRATIVE_ALLOC_SCHEDULE_2026-08 | Applied at 101% of the phased monthly amount for demonstration. | YES | WP1 | Directly Allocated | Staff | 80% | OK | 374.96 | 299.968 | 74.992
ALLOC-202608-WP1_S03 | ALLOC-2026-08 | 2026-08-31 | WP1_S03 | 371.25 | Illustrative monthly management allocation; not DI transaction evidence | ILLUSTRATIVE_ALLOC_SCHEDULE_2026-08 | Applied at 100% of the phased monthly amount for demonstration. | YES | WP1 | Directly Allocated | Staff | 80% | OK | 371.25 | 297 | 74.25
ALLOC-202604-WP1_IND | ALLOC-2026-08 | 2026-04-30 | WP1_IND | 1162.04 | Illustrative monthly management allocation; not DI transaction evidence | ILLUSTRATIVE_ALLOC_SCHEDULE_2026-08 | Applied at 97% of the phased monthly amount for demonstration. | YES | WP1 | Indirect | Indirect | 80% | OK | 1162.04 | 929.632 | 232.408
ALLOC-202605-WP1_IND | ALLOC-2026-08 | 2026-05-31 | WP1_IND | 1197.98 | Illustrative monthly management allocation; not DI transaction evidence | ILLUSTRATIVE_ALLOC_SCHEDULE_2026-08 | Applied at 100% of the phased monthly amount for demonstration. | YES | WP1 | Indirect | Indirect | 80% | OK | 1197.98 | 958.384 | 239.596
ALLOC-202606-WP1_IND | ALLOC-2026-08 | 2026-06-30 | WP1_IND | 1186 | Illustrative monthly management allocation; not DI transaction evidence | ILLUSTRATIVE_ALLOC_SCHEDULE_2026-08 | Applied at 99% of the phased monthly amount for demonstration. | YES | WP1 | Indirect | Indirect | 80% | OK | 1186 | 948.8 | 237.2
ALLOC-202607-WP1_IND | ALLOC-2026-08 | 2026-07-31 | WP1_IND | 1209.96 | Illustrative monthly management allocation; not DI transaction evidence | ILLUSTRATIVE_ALLOC_SCHEDULE_2026-08 | Applied at 101% of the phased monthly amount for demonstration. | YES | WP1 | Indirect | Indirect | 80% | OK | 1209.96 | 967.968 | 241.992
ALLOC-202608-WP1_IND | ALLOC-2026-08 | 2026-08-31 | WP1_IND | 1197.98 | Illustrative monthly management allocation; not DI transaction evidence | ILLUSTRATIVE_ALLOC_SCHEDULE_2026-08 | Applied at 100% of the phased monthly amount for demonstration. | YES | WP1 | Indirect | Indirect | 80% | OK | 1197.98 | 958.384 | 239.596
ALLOC-202604-WP1_EST | ALLOC-2026-08 | 2026-04-30 | WP1_EST | 148.09 | Illustrative monthly management allocation; not DI transaction evidence | ILLUSTRATIVE_ALLOC_SCHEDULE_2026-08 | Applied at 97% of the phased monthly amount for demonstration. | YES | WP1 | Directly Allocated | Estates | 80% | OK | 148.09 | 118.472 | 29.618
ALLOC-202605-WP1_EST | ALLOC-2026-08 | 2026-05-31 | WP1_EST | 152.67 | Illustrative monthly management allocation; not DI transaction evidence | ILLUSTRATIVE_ALLOC_SCHEDULE_2026-08 | Applied at 100% of the phased monthly amount for demonstration. | YES | WP1 | Directly Allocated | Estates | 80% | OK | 152.67 | 122.136 | 30.534
ALLOC-202606-WP1_EST | ALLOC-2026-08 | 2026-06-30 | WP1_EST | 151.14 | Illustrative monthly management allocation; not DI transaction evidence | ILLUSTRATIVE_ALLOC_SCHEDULE_2026-08 | Applied at 99% of the phased monthly amount for demonstration. | YES | WP1 | Directly Allocated | Estates | 80% | OK | 151.14 | 120.912 | 30.228
ALLOC-202607-WP1_EST | ALLOC-2026-08 | 2026-07-31 | WP1_EST | 154.19 | Illustrative monthly management allocation; not DI transaction evidence | ILLUSTRATIVE_ALLOC_SCHEDULE_2026-08 | Applied at 101% of the phased monthly amount for demonstration. | YES | WP1 | Directly Allocated | Estates | 80% | OK | 154.19 | 123.352 | 30.838
ALLOC-202608-WP1_EST | ALLOC-2026-08 | 2026-08-31 | WP1_EST | 152.67 | Illustrative monthly management allocation; not DI transaction evidence | ILLUSTRATIVE_ALLOC_SCHEDULE_2026-08 | Applied at 100% of the phased monthly amount for demonstration. | YES | WP1 | Directly Allocated | Estates | 80% | OK | 152.67 | 122.136 | 30.534
ALLOC-202604-WP2_S01 | ALLOC-2026-08 | 2026-04-30 | WP2_S01 | 95.18 | Illustrative monthly management allocation; not DI transaction evidence | ILLUSTRATIVE_ALLOC_SCHEDULE_2026-08 | Applied at 97% of the phased monthly amount for demonstration. | YES | WP2 | Directly Allocated | Staff | 80% | OK | 95.18 | 76.144 | 19.036
ALLOC-202605-WP2_S01 | ALLOC-2026-08 | 2026-05-31 | WP2_S01 | 98.13 | Illustrative monthly management allocation; not DI transaction evidence | ILLUSTRATIVE_ALLOC_SCHEDULE_2026-08 | Applied at 100% of the phased monthly amount for demonstration. | YES | WP2 | Directly Allocated | Staff | 80% | OK | 98.13 | 78.504 | 19.626
ALLOC-202606-WP2_S01 | ALLOC-2026-08 | 2026-06-30 | WP2_S01 | 97.14 | Illustrative monthly management allocation; not DI transaction evidence | ILLUSTRATIVE_ALLOC_SCHEDULE_2026-08 | Applied at 99% of the phased monthly amount for demonstration. | YES | WP2 | Directly Allocated | Staff | 80% | OK | 97.14 | 77.712 | 19.428
ALLOC-202607-WP2_S01 | ALLOC-2026-08 | 2026-07-31 | WP2_S01 | 99.11 | Illustrative monthly management allocation; not DI transaction evidence | ILLUSTRATIVE_ALLOC_SCHEDULE_2026-08 | Applied at 101% of the phased monthly amount for demonstration. | YES | WP2 | Directly Allocated | Staff | 80% | OK | 99.11 | 79.288 | 19.822
ALLOC-202608-WP2_S01 | ALLOC-2026-08 | 2026-08-31 | WP2_S01 | 98.13 | Illustrative monthly management allocation; not DI transaction evidence | ILLUSTRATIVE_ALLOC_SCHEDULE_2026-08 | Applied at 100% of the phased monthly amount for demonstration. | YES | WP2 | Directly Allocated | Staff | 80% | OK | 98.13 | 78.504 | 19.626
ALLOC-202604-WP2_S02 | ALLOC-2026-08 | 2026-04-30 | WP2_S02 | 117.01 | Illustrative monthly management allocation; not DI transaction evidence | ILLUSTRATIVE_ALLOC_SCHEDULE_2026-08 | Applied at 97% of the phased monthly amount for demonstration. | YES | WP2 | Directly Allocated | Staff | 80% | OK | 117.01 | 93.608 | 23.402
ALLOC-202605-WP2_S02 | ALLOC-2026-08 | 2026-05-31 | WP2_S02 | 120.63 | Illustrative monthly management allocation; not DI transaction evidence | ILLUSTRATIVE_ALLOC_SCHEDULE_2026-08 | Applied at 100% of the phased monthly amount for demonstration. | YES | WP2 | Directly Allocated | Staff | 80% | OK | 120.63 | 96.504 | 24.126
ALLOC-202606-WP2_S02 | ALLOC-2026-08 | 2026-06-30 | WP2_S02 | 119.42 | Illustrative monthly management allocation; not DI transaction evidence | ILLUSTRATIVE_ALLOC_SCHEDULE_2026-08 | Applied at 99% of the phased monthly amount for demonstration. | YES | WP2 | Directly Allocated | Staff | 80% | OK | 119.42 | 95.536 | 23.884
ALLOC-202607-WP2_S02 | ALLOC-2026-08 | 2026-07-31 | WP2_S02 | 121.83 | Illustrative monthly management allocation; not DI transaction evidence | ILLUSTRATIVE_ALLOC_SCHEDULE_2026-08 | Applied at 101% of the phased monthly amount for demonstration. | YES | WP2 | Directly Allocated | Staff | 80% | OK | 121.83 | 97.464 | 24.366
ALLOC-202608-WP2_S02 | ALLOC-2026-08 | 2026-08-31 | WP2_S02 | 120.63 | Illustrative monthly management allocation; not DI transaction evidence | ILLUSTRATIVE_ALLOC_SCHEDULE_2026-08 | Applied at 100% of the phased monthly amount for demonstration. | YES | WP2 | Directly Allocated | Staff | 80% | OK | 120.63 | 96.504 | 24.126
ALLOC-202604-WP2_S03 | ALLOC-2026-08 | 2026-04-30 | WP2_S03 | 120.04 | Illustrative monthly management allocation; not DI transaction evidence | ILLUSTRATIVE_ALLOC_SCHEDULE_2026-08 | Applied at 97% of the phased monthly amount for demonstration. | YES | WP2 | Directly Allocated | Staff | 80% | OK | 120.04 | 96.032 | 24.008
ALLOC-202605-WP2_S03 | ALLOC-2026-08 | 2026-05-31 | WP2_S03 | 123.75 | Illustrative monthly management allocation; not DI transaction evidence | ILLUSTRATIVE_ALLOC_SCHEDULE_2026-08 | Applied at 100% of the phased monthly amount for demonstration. | YES | WP2 | Directly Allocated | Staff | 80% | OK | 123.75 | 99 | 24.75
ALLOC-202606-WP2_S03 | ALLOC-2026-08 | 2026-06-30 | WP2_S03 | 122.51 | Illustrative monthly management allocation; not DI transaction evidence | ILLUSTRATIVE_ALLOC_SCHEDULE_2026-08 | Applied at 99% of the phased monthly amount for demonstration. | YES | WP2 | Directly Allocated | Staff | 80% | OK | 122.51 | 98.008 | 24.502
ALLOC-202607-WP2_S03 | ALLOC-2026-08 | 2026-07-31 | WP2_S03 | 124.99 | Illustrative monthly management allocation; not DI transaction evidence | ILLUSTRATIVE_ALLOC_SCHEDULE_2026-08 | Applied at 101% of the phased monthly amount for demonstration. | YES | WP2 | Directly Allocated | Staff | 80% | OK | 124.99 | 99.992 | 24.998
ALLOC-202608-WP2_S03 | ALLOC-2026-08 | 2026-08-31 | WP2_S03 | 123.75 | Illustrative monthly management allocation; not DI transaction evidence | ILLUSTRATIVE_ALLOC_SCHEDULE_2026-08 | Applied at 100% of the phased monthly amount for demonstration. | YES | WP2 | Directly Allocated | Staff | 80% | OK | 123.75 | 99 | 24.75
ALLOC-202604-WP2_IND | ALLOC-2026-08 | 2026-04-30 | WP2_IND | 371.85 | Illustrative monthly management allocation; not DI transaction evidence | ILLUSTRATIVE_ALLOC_SCHEDULE_2026-08 | Applied at 97% of the phased monthly amount for demonstration. | YES | WP2 | Indirect | Indirect | 80% | OK | 371.85 | 297.48 | 74.37
ALLOC-202605-WP2_IND | ALLOC-2026-08 | 2026-05-31 | WP2_IND | 383.35 | Illustrative monthly management allocation; not DI transaction evidence | ILLUSTRATIVE_ALLOC_SCHEDULE_2026-08 | Applied at 100% of the phased monthly amount for demonstration. | YES | WP2 | Indirect | Indirect | 80% | OK | 383.35 | 306.68 | 76.67
ALLOC-202606-WP2_IND | ALLOC-2026-08 | 2026-06-30 | WP2_IND | 379.52 | Illustrative monthly management allocation; not DI transaction evidence | ILLUSTRATIVE_ALLOC_SCHEDULE_2026-08 | Applied at 99% of the phased monthly amount for demonstration. | YES | WP2 | Indirect | Indirect | 80% | OK | 379.52 | 303.616 | 75.904
ALLOC-202607-WP2_IND | ALLOC-2026-08 | 2026-07-31 | WP2_IND | 387.19 | Illustrative monthly management allocation; not DI transaction evidence | ILLUSTRATIVE_ALLOC_SCHEDULE_2026-08 | Applied at 101% of the phased monthly amount for demonstration. | YES | WP2 | Indirect | Indirect | 80% | OK | 387.19 | 309.752 | 77.438
ALLOC-202608-WP2_IND | ALLOC-2026-08 | 2026-08-31 | WP2_IND | 383.35 | Illustrative monthly management allocation; not DI transaction evidence | ILLUSTRATIVE_ALLOC_SCHEDULE_2026-08 | Applied at 100% of the phased monthly amount for demonstration. | YES | WP2 | Indirect | Indirect | 80% | OK | 383.35 | 306.68 | 76.67
ALLOC-202604-WP2_EST | ALLOC-2026-08 | 2026-04-30 | WP2_EST | 47.39 | Illustrative monthly management allocation; not DI transaction evidence | ILLUSTRATIVE_ALLOC_SCHEDULE_2026-08 | Applied at 97% of the phased monthly amount for demonstration. | YES | WP2 | Directly Allocated | Estates | 80% | OK | 47.39 | 37.912 | 9.478
ALLOC-202605-WP2_EST | ALLOC-2026-08 | 2026-05-31 | WP2_EST | 48.85 | Illustrative monthly management allocation; not DI transaction evidence | ILLUSTRATIVE_ALLOC_SCHEDULE_2026-08 | Applied at 100% of the phased monthly amount for demonstration. | YES | WP2 | Directly Allocated | Estates | 80% | OK | 48.85 | 39.08 | 9.77
ALLOC-202606-WP2_EST | ALLOC-2026-08 | 2026-06-30 | WP2_EST | 48.36 | Illustrative monthly management allocation; not DI transaction evidence | ILLUSTRATIVE_ALLOC_SCHEDULE_2026-08 | Applied at 99% of the phased monthly amount for demonstration. | YES | WP2 | Directly Allocated | Estates | 80% | OK | 48.36 | 38.688 | 9.672
ALLOC-202607-WP2_EST | ALLOC-2026-08 | 2026-07-31 | WP2_EST | 49.34 | Illustrative monthly management allocation; not DI transaction evidence | ILLUSTRATIVE_ALLOC_SCHEDULE_2026-08 | Applied at 101% of the phased monthly amount for demonstration. | YES | WP2 | Directly Allocated | Estates | 80% | OK | 49.34 | 39.472 | 9.868
ALLOC-202608-WP2_EST | ALLOC-2026-08 | 2026-08-31 | WP2_EST | 48.85 | Illustrative monthly management allocation; not DI transaction evidence | ILLUSTRATIVE_ALLOC_SCHEDULE_2026-08 | Applied at 100% of the phased monthly amount for demonstration. | YES | WP2 | Directly Allocated | Estates | 80% | OK | 48.85 | 39.08 | 9.77
ALLOC-202604-WP3_S01 | ALLOC-2026-08 | 2026-04-30 | WP3_S01 | 253.82 | Illustrative monthly management allocation; not DI transaction evidence | ILLUSTRATIVE_ALLOC_SCHEDULE_2026-08 | Applied at 97% of the phased monthly amount for demonstration. | YES | WP3 | Directly Allocated | Staff | 80% | OK | 253.82 | 203.056 | 50.764
ALLOC-202605-WP3_S01 | ALLOC-2026-08 | 2026-05-31 | WP3_S01 | 261.67 | Illustrative monthly management allocation; not DI transaction evidence | ILLUSTRATIVE_ALLOC_SCHEDULE_2026-08 | Applied at 100% of the phased monthly amount for demonstration. | YES | WP3 | Directly Allocated | Staff | 80% | OK | 261.67 | 209.336 | 52.334
ALLOC-202606-WP3_S01 | ALLOC-2026-08 | 2026-06-30 | WP3_S01 | 259.05 | Illustrative monthly management allocation; not DI transaction evidence | ILLUSTRATIVE_ALLOC_SCHEDULE_2026-08 | Applied at 99% of the phased monthly amount for demonstration. | YES | WP3 | Directly Allocated | Staff | 80% | OK | 259.05 | 207.24 | 51.81
ALLOC-202607-WP3_S01 | ALLOC-2026-08 | 2026-07-31 | WP3_S01 | 264.28 | Illustrative monthly management allocation; not DI transaction evidence | ILLUSTRATIVE_ALLOC_SCHEDULE_2026-08 | Applied at 101% of the phased monthly amount for demonstration. | YES | WP3 | Directly Allocated | Staff | 80% | OK | 264.28 | 211.424 | 52.856
ALLOC-202608-WP3_S01 | ALLOC-2026-08 | 2026-08-31 | WP3_S01 | 261.67 | Illustrative monthly management allocation; not DI transaction evidence | ILLUSTRATIVE_ALLOC_SCHEDULE_2026-08 | Applied at 100% of the phased monthly amount for demonstration. | YES | WP3 | Directly Allocated | Staff | 80% | OK | 261.67 | 209.336 | 52.334
ALLOC-202604-WP3_S02 | ALLOC-2026-08 | 2026-04-30 | WP3_S02 | 117.01 | Illustrative monthly management allocation; not DI transaction evidence | ILLUSTRATIVE_ALLOC_SCHEDULE_2026-08 | Applied at 97% of the phased monthly amount for demonstration. | YES | WP3 | Directly Allocated | Staff | 80% | OK | 117.01 | 93.608 | 23.402
ALLOC-202605-WP3_S02 | ALLOC-2026-08 | 2026-05-31 | WP3_S02 | 120.63 | Illustrative monthly management allocation; not DI transaction evidence | ILLUSTRATIVE_ALLOC_SCHEDULE_2026-08 | Applied at 100% of the phased monthly amount for demonstration. | YES | WP3 | Directly Allocated | Staff | 80% | OK | 120.63 | 96.504 | 24.126
ALLOC-202606-WP3_S02 | ALLOC-2026-08 | 2026-06-30 | WP3_S02 | 119.42 | Illustrative monthly management allocation; not DI transaction evidence | ILLUSTRATIVE_ALLOC_SCHEDULE_2026-08 | Applied at 99% of the phased monthly amount for demonstration. | YES | WP3 | Directly Allocated | Staff | 80% | OK | 119.42 | 95.536 | 23.884
ALLOC-202607-WP3_S02 | ALLOC-2026-08 | 2026-07-31 | WP3_S02 | 121.83 | Illustrative monthly management allocation; not DI transaction evidence | ILLUSTRATIVE_ALLOC_SCHEDULE_2026-08 | Applied at 101% of the phased monthly amount for demonstration. | YES | WP3 | Directly Allocated | Staff | 80% | OK | 121.83 | 97.464 | 24.366
ALLOC-202608-WP3_S02 | ALLOC-2026-08 | 2026-08-31 | WP3_S02 | 120.63 | Illustrative monthly management allocation; not DI transaction evidence | ILLUSTRATIVE_ALLOC_SCHEDULE_2026-08 | Applied at 100% of the phased monthly amount for demonstration. | YES | WP3 | Directly Allocated | Staff | 80% | OK | 120.63 | 96.504 | 24.126
ALLOC-202604-WP3_S03 | ALLOC-2026-08 | 2026-04-30 | WP3_S03 | 120.04 | Illustrative monthly management allocation; not DI transaction evidence | ILLUSTRATIVE_ALLOC_SCHEDULE_2026-08 | Applied at 97% of the phased monthly amount for demonstration. | YES | WP3 | Directly Allocated | Staff | 80% | OK | 120.04 | 96.032 | 24.008
ALLOC-202605-WP3_S03 | ALLOC-2026-08 | 2026-05-31 | WP3_S03 | 123.75 | Illustrative monthly management allocation; not DI transaction evidence | ILLUSTRATIVE_ALLOC_SCHEDULE_2026-08 | Applied at 100% of the phased monthly amount for demonstration. | YES | WP3 | Directly Allocated | Staff | 80% | OK | 123.75 | 99 | 24.75
ALLOC-202606-WP3_S03 | ALLOC-2026-08 | 2026-06-30 | WP3_S03 | 122.51 | Illustrative monthly management allocation; not DI transaction evidence | ILLUSTRATIVE_ALLOC_SCHEDULE_2026-08 | Applied at 99% of the phased monthly amount for demonstration. | YES | WP3 | Directly Allocated | Staff | 80% | OK | 122.51 | 98.008 | 24.502
ALLOC-202607-WP3_S03 | ALLOC-2026-08 | 2026-07-31 | WP3_S03 | 124.99 | Illustrative monthly management allocation; not DI transaction evidence | ILLUSTRATIVE_ALLOC_SCHEDULE_2026-08 | Applied at 101% of the phased monthly amount for demonstration. | YES | WP3 | Directly Allocated | Staff | 80% | OK | 124.99 | 99.992 | 24.998
ALLOC-202608-WP3_S03 | ALLOC-2026-08 | 2026-08-31 | WP3_S03 | 123.75 | Illustrative monthly management allocation; not DI transaction evidence | ILLUSTRATIVE_ALLOC_SCHEDULE_2026-08 | Applied at 100% of the phased monthly amount for demonstration. | YES | WP3 | Directly Allocated | Staff | 80% | OK | 123.75 | 99 | 24.75
ALLOC-202604-WP3_IND | ALLOC-2026-08 | 2026-04-30 | WP3_IND | 604.26 | Illustrative monthly management allocation; not DI transaction evidence | ILLUSTRATIVE_ALLOC_SCHEDULE_2026-08 | Applied at 97% of the phased monthly amount for demonstration. | YES | WP3 | Indirect | Indirect | 80% | OK | 604.26 | 483.408 | 120.852
ALLOC-202605-WP3_IND | ALLOC-2026-08 | 2026-05-31 | WP3_IND | 622.95 | Illustrative monthly management allocation; not DI transaction evidence | ILLUSTRATIVE_ALLOC_SCHEDULE_2026-08 | Applied at 100% of the phased monthly amount for demonstration. | YES | WP3 | Indirect | Indirect | 80% | OK | 622.95 | 498.36 | 124.59
ALLOC-202606-WP3_IND | ALLOC-2026-08 | 2026-06-30 | WP3_IND | 616.72 | Illustrative monthly management allocation; not DI transaction evidence | ILLUSTRATIVE_ALLOC_SCHEDULE_2026-08 | Applied at 99% of the phased monthly amount for demonstration. | YES | WP3 | Indirect | Indirect | 80% | OK | 616.72 | 493.376 | 123.344
ALLOC-202607-WP3_IND | ALLOC-2026-08 | 2026-07-31 | WP3_IND | 629.18 | Illustrative monthly management allocation; not DI transaction evidence | ILLUSTRATIVE_ALLOC_SCHEDULE_2026-08 | Applied at 101% of the phased monthly amount for demonstration. | YES | WP3 | Indirect | Indirect | 80% | OK | 629.18 | 503.344 | 125.836
ALLOC-202608-WP3_IND | ALLOC-2026-08 | 2026-08-31 | WP3_IND | 622.95 | Illustrative monthly management allocation; not DI transaction evidence | ILLUSTRATIVE_ALLOC_SCHEDULE_2026-08 | Applied at 100% of the phased monthly amount for demonstration. | YES | WP3 | Indirect | Indirect | 80% | OK | 622.95 | 498.36 | 124.59
ALLOC-202604-WP3_EST | ALLOC-2026-08 | 2026-04-30 | WP3_EST | 77.01 | Illustrative monthly management allocation; not DI transaction evidence | ILLUSTRATIVE_ALLOC_SCHEDULE_2026-08 | Applied at 97% of the phased monthly amount for demonstration. | YES | WP3 | Directly Allocated | Estates | 80% | OK | 77.01 | 61.608 | 15.402
ALLOC-202605-WP3_EST | ALLOC-2026-08 | 2026-05-31 | WP3_EST | 79.39 | Illustrative monthly management allocation; not DI transaction evidence | ILLUSTRATIVE_ALLOC_SCHEDULE_2026-08 | Applied at 100% of the phased monthly amount for demonstration. | YES | WP3 | Directly Allocated | Estates | 80% | OK | 79.39 | 63.512 | 15.878
ALLOC-202606-WP3_EST | ALLOC-2026-08 | 2026-06-30 | WP3_EST | 78.59 | Illustrative monthly management allocation; not DI transaction evidence | ILLUSTRATIVE_ALLOC_SCHEDULE_2026-08 | Applied at 99% of the phased monthly amount for demonstration. | YES | WP3 | Directly Allocated | Estates | 80% | OK | 78.59 | 62.872 | 15.718
ALLOC-202607-WP3_EST | ALLOC-2026-08 | 2026-07-31 | WP3_EST | 80.18 | Illustrative monthly management allocation; not DI transaction evidence | ILLUSTRATIVE_ALLOC_SCHEDULE_2026-08 | Applied at 101% of the phased monthly amount for demonstration. | YES | WP3 | Directly Allocated | Estates | 80% | OK | 80.18 | 64.144 | 16.036
ALLOC-202608-WP3_EST | ALLOC-2026-08 | 2026-08-31 | WP3_EST | 79.39 | Illustrative monthly management allocation; not DI transaction evidence | ILLUSTRATIVE_ALLOC_SCHEDULE_2026-08 | Applied at 100% of the phased monthly amount for demonstration. | YES | WP3 | Directly Allocated | Estates | 80% | OK | 79.39 | 63.512 | 15.878

## 8) Commitments Forecast
Commitments and forecast exposure
Open commitments = Costs liable for but not yet unrealised. Forecast at Completion bridges recognised cost, commitments and ETC
The seeded commitments are hypothetical. Included GBP is limited to valid, approved OPEN commitments. Closed or cancelled records remain visible but contribute zero.
Commitment ID | Batch ID | Status | Commitment Date | Expected Incurred Date | Description | Amount GBP | Budget Item ID | PO/Contract Ref | Notes | Batch Approved | Work Package | fEC Heading | fEC Subheading | Funding Rate | Row Status | Included GBP | Included UKRI | Included RUSI
CMT-001 | COMMIT-2026-08 | Open | 2026-08-10 | 2026-09-30 | London launch conference venue, catering and production | 13800 | WP1_CONF | PO-DEMO-1001 | Hypothetical open exposure; not realised expenditure. | YES | WP1 | Directly Incurred | Other Directly Incurred | 80% | OK | 13800 | 11040 | 2760
CMT-002 | COMMIT-2026-08 | Open | 2026-08-12 | 2026-09-30 | Launch conference speaker travel and accommodation | 900 | WP1_CONF | PO-DEMO-1002 | Hypothetical open exposure; not realised expenditure. | YES | WP1 | Directly Incurred | Other Directly Incurred | 80% | OK | 900 | 720 | 180
CMT-003 | COMMIT-2026-08 | Open | 2026-08-15 | 2026-11-15 | UK regional workshop series | 1200 | WP1_WORKSHOP | PO-DEMO-1003 | Hypothetical open exposure; not realised expenditure. | YES | WP1 | Directly Incurred | Other Directly Incurred | 80% | OK | 1200 | 960 | 240
CMT-004 | COMMIT-2026-08 | Open | 2026-08-18 | 2027-03-31 | Nairobi network broker remaining FY contract | 2450 | WP2_CONSULT | CON-DEMO-2001 | Hypothetical open exposure; not realised expenditure. | YES | WP2 | Directly Incurred | Other Directly Incurred | 80% | OK | 2450 | 1960 | 490
CMT-005 | COMMIT-2026-08 | Open | 2026-08-18 | 2027-03-31 | Latin America network broker remaining FY contract | 2450 | WP3_CONSULT | CON-DEMO-3001 | Hypothetical open exposure; not realised expenditure. | YES | WP3 | Directly Incurred | Other Directly Incurred | 80% | OK | 2450 | 1960 | 490
CMT-006 | COMMIT-2026-08 | Open | 2026-08-20 | 2026-10-31 | East Africa scoping visit | 1850 | WP2_TRAVEL | PO-DEMO-2002 | Hypothetical open exposure; not realised expenditure. | YES | WP2 | Directly Incurred | Travel & Subsistence | 80% | OK | 1850 | 1480 | 370
CMT-007 | COMMIT-2026-08 | Open | 2026-08-20 | 2026-11-30 | Latin America partner meeting | 2100 | WP3_TRAVEL | PO-DEMO-3002 | Hypothetical open exposure; not realised expenditure. | YES | WP3 | Directly Incurred | Travel & Subsistence | 80% | OK | 2100 | 1680 | 420
CMT-008 | COMMIT-2026-08 | Open | 2026-08-22 | 2026-12-15 | East Africa practitioner workshop | 1000 | WP2_WORKSHOP | PO-DEMO-2003 | Hypothetical open exposure; not realised expenditure. | YES | WP2 | Directly Incurred | Other Directly Incurred | 80% | OK | 1000 | 800 | 200
CMT-009 | COMMIT-2026-08 | Open | 2026-08-22 | 2027-02-15 | Latin America practitioner workshop | 1000 | WP3_WORKSHOP | PO-DEMO-3003 | Hypothetical open exposure; not realised expenditure. | YES | WP3 | Directly Incurred | Other Directly Incurred | 80% | OK | 1000 | 800 | 200
CMT-010 | COMMIT-2026-08 | Open | 2026-08-25 | 2026-10-15 | Launch communications production | 450 | WP1_COMMS | PO-DEMO-1004 | Hypothetical open exposure; not realised expenditure. | YES | WP1 | Directly Incurred | Other Directly Incurred | 80% | OK | 450 | 360 | 90

## 9) Budget Baseline
Frozen Budget baseline and approved profile
One Budget Item × month record; original fEC, UKRI and RUSI bases are preserved
Approved Budget = (Original Budget) + (Approved amendments). This example contains no such amendments
Budget Record ID | Budget Item ID | Description | Work Package | fEC Heading | fEC Subheading | Reporting Category | Period End | Financial Year | Phasing Method | Funding Rate | Original Budget 100% fEC | Original UKRI | Original RUSI | Approved Change 100% | Approved Budget 100% | Approved UKRI | Approved RUSI
WP1_S01-202604 | WP1_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | 2026-04-30 | 2026/27 | Straight-line | 80% | 327.0833 | 261.6667 | 65.4167 | 0 | 327.0833 | 261.6667 | 65.4167
WP1_S01-202605 | WP1_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | 2026-05-31 | 2026/27 | Straight-line | 80% | 327.0833 | 261.6667 | 65.4167 | 0 | 327.0833 | 261.6667 | 65.4167
WP1_S01-202606 | WP1_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | 2026-06-30 | 2026/27 | Straight-line | 80% | 327.0833 | 261.6667 | 65.4167 | 0 | 327.0833 | 261.6667 | 65.4167
WP1_S01-202607 | WP1_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | 2026-07-31 | 2026/27 | Straight-line | 80% | 327.0833 | 261.6667 | 65.4167 | 0 | 327.0833 | 261.6667 | 65.4167
WP1_S01-202608 | WP1_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | 2026-08-31 | 2026/27 | Straight-line | 80% | 327.0833 | 261.6667 | 65.4167 | 0 | 327.0833 | 261.6667 | 65.4167
WP1_S01-202609 | WP1_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | 2026-09-30 | 2026/27 | Straight-line | 80% | 327.0833 | 261.6667 | 65.4167 | 0 | 327.0833 | 261.6667 | 65.4167
WP1_S01-202610 | WP1_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | 2026-10-31 | 2026/27 | Straight-line | 80% | 327.0833 | 261.6667 | 65.4167 | 0 | 327.0833 | 261.6667 | 65.4167
WP1_S01-202611 | WP1_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | 2026-11-30 | 2026/27 | Straight-line | 80% | 327.0833 | 261.6667 | 65.4167 | 0 | 327.0833 | 261.6667 | 65.4167
WP1_S01-202612 | WP1_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | 2026-12-31 | 2026/27 | Straight-line | 80% | 327.0833 | 261.6667 | 65.4167 | 0 | 327.0833 | 261.6667 | 65.4167
WP1_S01-202701 | WP1_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | 2027-01-31 | 2026/27 | Straight-line | 80% | 327.0833 | 261.6667 | 65.4167 | 0 | 327.0833 | 261.6667 | 65.4167
WP1_S01-202702 | WP1_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | 2027-02-28 | 2026/27 | Straight-line | 80% | 327.0833 | 261.6667 | 65.4167 | 0 | 327.0833 | 261.6667 | 65.4167
WP1_S01-202703 | WP1_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | 2027-03-31 | 2026/27 | Straight-line | 80% | 327.0833 | 261.6667 | 65.4167 | 0 | 327.0833 | 261.6667 | 65.4167
WP1_S01-202704 | WP1_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | 2027-04-30 | 2027/28 | Straight-line | 80% | 457.9167 | 366.3333 | 91.5833 | 0 | 457.9167 | 366.3333 | 91.5833
WP1_S01-202705 | WP1_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | 2027-05-31 | 2027/28 | Straight-line | 80% | 457.9167 | 366.3333 | 91.5833 | 0 | 457.9167 | 366.3333 | 91.5833
WP1_S01-202706 | WP1_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | 2027-06-30 | 2027/28 | Straight-line | 80% | 457.9167 | 366.3333 | 91.5833 | 0 | 457.9167 | 366.3333 | 91.5833
WP1_S01-202707 | WP1_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | 2027-07-31 | 2027/28 | Straight-line | 80% | 457.9167 | 366.3333 | 91.5833 | 0 | 457.9167 | 366.3333 | 91.5833
WP1_S01-202708 | WP1_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | 2027-08-31 | 2027/28 | Straight-line | 80% | 457.9167 | 366.3333 | 91.5833 | 0 | 457.9167 | 366.3333 | 91.5833
WP1_S01-202709 | WP1_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | 2027-09-30 | 2027/28 | Straight-line | 80% | 457.9167 | 366.3333 | 91.5833 | 0 | 457.9167 | 366.3333 | 91.5833
WP1_S01-202710 | WP1_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | 2027-10-31 | 2027/28 | Straight-line | 80% | 457.9167 | 366.3333 | 91.5833 | 0 | 457.9167 | 366.3333 | 91.5833
WP1_S01-202711 | WP1_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | 2027-11-30 | 2027/28 | Straight-line | 80% | 457.9167 | 366.3333 | 91.5833 | 0 | 457.9167 | 366.3333 | 91.5833
WP1_S01-202712 | WP1_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | 2027-12-31 | 2027/28 | Straight-line | 80% | 457.9167 | 366.3333 | 91.5833 | 0 | 457.9167 | 366.3333 | 91.5833
WP1_S01-202801 | WP1_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | 2028-01-31 | 2027/28 | Straight-line | 80% | 457.9167 | 366.3333 | 91.5833 | 0 | 457.9167 | 366.3333 | 91.5833
WP1_S01-202802 | WP1_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | 2028-02-29 | 2027/28 | Straight-line | 80% | 457.9167 | 366.3333 | 91.5833 | 0 | 457.9167 | 366.3333 | 91.5833
WP1_S01-202803 | WP1_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | 2028-03-31 | 2027/28 | Straight-line | 80% | 457.9167 | 366.3333 | 91.5833 | 0 | 457.9167 | 366.3333 | 91.5833
WP1_S01-202804 | WP1_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | 2028-04-30 | 2028/29 | Straight-line | 80% | 457.9167 | 366.3333 | 91.5833 | 0 | 457.9167 | 366.3333 | 91.5833
WP1_S01-202805 | WP1_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | 2028-05-31 | 2028/29 | Straight-line | 80% | 457.9167 | 366.3333 | 91.5833 | 0 | 457.9167 | 366.3333 | 91.5833
WP1_S01-202806 | WP1_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | 2028-06-30 | 2028/29 | Straight-line | 80% | 457.9167 | 366.3333 | 91.5833 | 0 | 457.9167 | 366.3333 | 91.5833
WP1_S01-202807 | WP1_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | 2028-07-31 | 2028/29 | Straight-line | 80% | 457.9167 | 366.3333 | 91.5833 | 0 | 457.9167 | 366.3333 | 91.5833
WP1_S01-202808 | WP1_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | 2028-08-31 | 2028/29 | Straight-line | 80% | 457.9167 | 366.3333 | 91.5833 | 0 | 457.9167 | 366.3333 | 91.5833
WP1_S01-202809 | WP1_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | 2028-09-30 | 2028/29 | Straight-line | 80% | 457.9167 | 366.3333 | 91.5833 | 0 | 457.9167 | 366.3333 | 91.5833
WP1_S01-202810 | WP1_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | 2028-10-31 | 2028/29 | Straight-line | 80% | 457.9167 | 366.3333 | 91.5833 | 0 | 457.9167 | 366.3333 | 91.5833
WP1_S01-202811 | WP1_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | 2028-11-30 | 2028/29 | Straight-line | 80% | 457.9167 | 366.3333 | 91.5833 | 0 | 457.9167 | 366.3333 | 91.5833
WP1_S01-202812 | WP1_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | 2028-12-31 | 2028/29 | Straight-line | 80% | 457.9167 | 366.3333 | 91.5833 | 0 | 457.9167 | 366.3333 | 91.5833
WP1_S01-202901 | WP1_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | 2029-01-31 | 2028/29 | Straight-line | 80% | 457.9167 | 366.3333 | 91.5833 | 0 | 457.9167 | 366.3333 | 91.5833
WP1_S01-202902 | WP1_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | 2029-02-28 | 2028/29 | Straight-line | 80% | 457.9167 | 366.3333 | 91.5833 | 0 | 457.9167 | 366.3333 | 91.5833
WP1_S01-202903 | WP1_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | 2029-03-31 | 2028/29 | Straight-line | 80% | 457.9167 | 366.3333 | 91.5833 | 0 | 457.9167 | 366.3333 | 91.5833
WP1_S02-202604 | WP1_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | 2026-04-30 | 2026/27 | Straight-line | 80% | 361.875 | 289.5 | 72.375 | 0 | 361.875 | 289.5 | 72.375
WP1_S02-202605 | WP1_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | 2026-05-31 | 2026/27 | Straight-line | 80% | 361.875 | 289.5 | 72.375 | 0 | 361.875 | 289.5 | 72.375
WP1_S02-202606 | WP1_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | 2026-06-30 | 2026/27 | Straight-line | 80% | 361.875 | 289.5 | 72.375 | 0 | 361.875 | 289.5 | 72.375
WP1_S02-202607 | WP1_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | 2026-07-31 | 2026/27 | Straight-line | 80% | 361.875 | 289.5 | 72.375 | 0 | 361.875 | 289.5 | 72.375
WP1_S02-202608 | WP1_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | 2026-08-31 | 2026/27 | Straight-line | 80% | 361.875 | 289.5 | 72.375 | 0 | 361.875 | 289.5 | 72.375
WP1_S02-202609 | WP1_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | 2026-09-30 | 2026/27 | Straight-line | 80% | 361.875 | 289.5 | 72.375 | 0 | 361.875 | 289.5 | 72.375
WP1_S02-202610 | WP1_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | 2026-10-31 | 2026/27 | Straight-line | 80% | 361.875 | 289.5 | 72.375 | 0 | 361.875 | 289.5 | 72.375
WP1_S02-202611 | WP1_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | 2026-11-30 | 2026/27 | Straight-line | 80% | 361.875 | 289.5 | 72.375 | 0 | 361.875 | 289.5 | 72.375
WP1_S02-202612 | WP1_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | 2026-12-31 | 2026/27 | Straight-line | 80% | 361.875 | 289.5 | 72.375 | 0 | 361.875 | 289.5 | 72.375
WP1_S02-202701 | WP1_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | 2027-01-31 | 2026/27 | Straight-line | 80% | 361.875 | 289.5 | 72.375 | 0 | 361.875 | 289.5 | 72.375
WP1_S02-202702 | WP1_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | 2027-02-28 | 2026/27 | Straight-line | 80% | 361.875 | 289.5 | 72.375 | 0 | 361.875 | 289.5 | 72.375
WP1_S02-202703 | WP1_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | 2027-03-31 | 2026/27 | Straight-line | 80% | 361.875 | 289.5 | 72.375 | 0 | 361.875 | 289.5 | 72.375
WP1_S02-202704 | WP1_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | 2027-04-30 | 2027/28 | Straight-line | 80% | 361.875 | 289.5 | 72.375 | 0 | 361.875 | 289.5 | 72.375
WP1_S02-202705 | WP1_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | 2027-05-31 | 2027/28 | Straight-line | 80% | 361.875 | 289.5 | 72.375 | 0 | 361.875 | 289.5 | 72.375
WP1_S02-202706 | WP1_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | 2027-06-30 | 2027/28 | Straight-line | 80% | 361.875 | 289.5 | 72.375 | 0 | 361.875 | 289.5 | 72.375
WP1_S02-202707 | WP1_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | 2027-07-31 | 2027/28 | Straight-line | 80% | 361.875 | 289.5 | 72.375 | 0 | 361.875 | 289.5 | 72.375
WP1_S02-202708 | WP1_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | 2027-08-31 | 2027/28 | Straight-line | 80% | 361.875 | 289.5 | 72.375 | 0 | 361.875 | 289.5 | 72.375
WP1_S02-202709 | WP1_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | 2027-09-30 | 2027/28 | Straight-line | 80% | 361.875 | 289.5 | 72.375 | 0 | 361.875 | 289.5 | 72.375
WP1_S02-202710 | WP1_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | 2027-10-31 | 2027/28 | Straight-line | 80% | 361.875 | 289.5 | 72.375 | 0 | 361.875 | 289.5 | 72.375
WP1_S02-202711 | WP1_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | 2027-11-30 | 2027/28 | Straight-line | 80% | 361.875 | 289.5 | 72.375 | 0 | 361.875 | 289.5 | 72.375
WP1_S02-202712 | WP1_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | 2027-12-31 | 2027/28 | Straight-line | 80% | 361.875 | 289.5 | 72.375 | 0 | 361.875 | 289.5 | 72.375
WP1_S02-202801 | WP1_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | 2028-01-31 | 2027/28 | Straight-line | 80% | 361.875 | 289.5 | 72.375 | 0 | 361.875 | 289.5 | 72.375
WP1_S02-202802 | WP1_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | 2028-02-29 | 2027/28 | Straight-line | 80% | 361.875 | 289.5 | 72.375 | 0 | 361.875 | 289.5 | 72.375
WP1_S02-202803 | WP1_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | 2028-03-31 | 2027/28 | Straight-line | 80% | 361.875 | 289.5 | 72.375 | 0 | 361.875 | 289.5 | 72.375
WP1_S02-202804 | WP1_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | 2028-04-30 | 2028/29 | Straight-line | 80% | 361.875 | 289.5 | 72.375 | 0 | 361.875 | 289.5 | 72.375
WP1_S02-202805 | WP1_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | 2028-05-31 | 2028/29 | Straight-line | 80% | 361.875 | 289.5 | 72.375 | 0 | 361.875 | 289.5 | 72.375
WP1_S02-202806 | WP1_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | 2028-06-30 | 2028/29 | Straight-line | 80% | 361.875 | 289.5 | 72.375 | 0 | 361.875 | 289.5 | 72.375
WP1_S02-202807 | WP1_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | 2028-07-31 | 2028/29 | Straight-line | 80% | 361.875 | 289.5 | 72.375 | 0 | 361.875 | 289.5 | 72.375
WP1_S02-202808 | WP1_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | 2028-08-31 | 2028/29 | Straight-line | 80% | 361.875 | 289.5 | 72.375 | 0 | 361.875 | 289.5 | 72.375
WP1_S02-202809 | WP1_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | 2028-09-30 | 2028/29 | Straight-line | 80% | 361.875 | 289.5 | 72.375 | 0 | 361.875 | 289.5 | 72.375
WP1_S02-202810 | WP1_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | 2028-10-31 | 2028/29 | Straight-line | 80% | 361.875 | 289.5 | 72.375 | 0 | 361.875 | 289.5 | 72.375
WP1_S02-202811 | WP1_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | 2028-11-30 | 2028/29 | Straight-line | 80% | 361.875 | 289.5 | 72.375 | 0 | 361.875 | 289.5 | 72.375
WP1_S02-202812 | WP1_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | 2028-12-31 | 2028/29 | Straight-line | 80% | 361.875 | 289.5 | 72.375 | 0 | 361.875 | 289.5 | 72.375
WP1_S02-202901 | WP1_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | 2029-01-31 | 2028/29 | Straight-line | 80% | 361.875 | 289.5 | 72.375 | 0 | 361.875 | 289.5 | 72.375
WP1_S02-202902 | WP1_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | 2029-02-28 | 2028/29 | Straight-line | 80% | 361.875 | 289.5 | 72.375 | 0 | 361.875 | 289.5 | 72.375
WP1_S02-202903 | WP1_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | 2029-03-31 | 2028/29 | Straight-line | 80% | 361.875 | 289.5 | 72.375 | 0 | 361.875 | 289.5 | 72.375
WP1_S03-202604 | WP1_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | 2026-04-30 | 2026/27 | Straight-line | 80% | 371.25 | 297 | 74.25 | 0 | 371.25 | 297 | 74.25
WP1_S03-202605 | WP1_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | 2026-05-31 | 2026/27 | Straight-line | 80% | 371.25 | 297 | 74.25 | 0 | 371.25 | 297 | 74.25
WP1_S03-202606 | WP1_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | 2026-06-30 | 2026/27 | Straight-line | 80% | 371.25 | 297 | 74.25 | 0 | 371.25 | 297 | 74.25
WP1_S03-202607 | WP1_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | 2026-07-31 | 2026/27 | Straight-line | 80% | 371.25 | 297 | 74.25 | 0 | 371.25 | 297 | 74.25
WP1_S03-202608 | WP1_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | 2026-08-31 | 2026/27 | Straight-line | 80% | 371.25 | 297 | 74.25 | 0 | 371.25 | 297 | 74.25
WP1_S03-202609 | WP1_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | 2026-09-30 | 2026/27 | Straight-line | 80% | 371.25 | 297 | 74.25 | 0 | 371.25 | 297 | 74.25
WP1_S03-202610 | WP1_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | 2026-10-31 | 2026/27 | Straight-line | 80% | 371.25 | 297 | 74.25 | 0 | 371.25 | 297 | 74.25
WP1_S03-202611 | WP1_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | 2026-11-30 | 2026/27 | Straight-line | 80% | 371.25 | 297 | 74.25 | 0 | 371.25 | 297 | 74.25
WP1_S03-202612 | WP1_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | 2026-12-31 | 2026/27 | Straight-line | 80% | 371.25 | 297 | 74.25 | 0 | 371.25 | 297 | 74.25
WP1_S03-202701 | WP1_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | 2027-01-31 | 2026/27 | Straight-line | 80% | 371.25 | 297 | 74.25 | 0 | 371.25 | 297 | 74.25
WP1_S03-202702 | WP1_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | 2027-02-28 | 2026/27 | Straight-line | 80% | 371.25 | 297 | 74.25 | 0 | 371.25 | 297 | 74.25
WP1_S03-202703 | WP1_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | 2027-03-31 | 2026/27 | Straight-line | 80% | 371.25 | 297 | 74.25 | 0 | 371.25 | 297 | 74.25
WP1_S03-202704 | WP1_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | 2027-04-30 | 2027/28 | Straight-line | 80% | 371.25 | 297 | 74.25 | 0 | 371.25 | 297 | 74.25
WP1_S03-202705 | WP1_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | 2027-05-31 | 2027/28 | Straight-line | 80% | 371.25 | 297 | 74.25 | 0 | 371.25 | 297 | 74.25
WP1_S03-202706 | WP1_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | 2027-06-30 | 2027/28 | Straight-line | 80% | 371.25 | 297 | 74.25 | 0 | 371.25 | 297 | 74.25
WP1_S03-202707 | WP1_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | 2027-07-31 | 2027/28 | Straight-line | 80% | 371.25 | 297 | 74.25 | 0 | 371.25 | 297 | 74.25
WP1_S03-202708 | WP1_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | 2027-08-31 | 2027/28 | Straight-line | 80% | 371.25 | 297 | 74.25 | 0 | 371.25 | 297 | 74.25
WP1_S03-202709 | WP1_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | 2027-09-30 | 2027/28 | Straight-line | 80% | 371.25 | 297 | 74.25 | 0 | 371.25 | 297 | 74.25
WP1_S03-202710 | WP1_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | 2027-10-31 | 2027/28 | Straight-line | 80% | 371.25 | 297 | 74.25 | 0 | 371.25 | 297 | 74.25
WP1_S03-202711 | WP1_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | 2027-11-30 | 2027/28 | Straight-line | 80% | 371.25 | 297 | 74.25 | 0 | 371.25 | 297 | 74.25
WP1_S03-202712 | WP1_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | 2027-12-31 | 2027/28 | Straight-line | 80% | 371.25 | 297 | 74.25 | 0 | 371.25 | 297 | 74.25
WP1_S03-202801 | WP1_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | 2028-01-31 | 2027/28 | Straight-line | 80% | 371.25 | 297 | 74.25 | 0 | 371.25 | 297 | 74.25
WP1_S03-202802 | WP1_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | 2028-02-29 | 2027/28 | Straight-line | 80% | 371.25 | 297 | 74.25 | 0 | 371.25 | 297 | 74.25
WP1_S03-202803 | WP1_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | 2028-03-31 | 2027/28 | Straight-line | 80% | 371.25 | 297 | 74.25 | 0 | 371.25 | 297 | 74.25
WP1_S03-202804 | WP1_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | 2028-04-30 | 2028/29 | Straight-line | 80% | 371.25 | 297 | 74.25 | 0 | 371.25 | 297 | 74.25
WP1_S03-202805 | WP1_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | 2028-05-31 | 2028/29 | Straight-line | 80% | 371.25 | 297 | 74.25 | 0 | 371.25 | 297 | 74.25
WP1_S03-202806 | WP1_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | 2028-06-30 | 2028/29 | Straight-line | 80% | 371.25 | 297 | 74.25 | 0 | 371.25 | 297 | 74.25
WP1_S03-202807 | WP1_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | 2028-07-31 | 2028/29 | Straight-line | 80% | 371.25 | 297 | 74.25 | 0 | 371.25 | 297 | 74.25
WP1_S03-202808 | WP1_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | 2028-08-31 | 2028/29 | Straight-line | 80% | 371.25 | 297 | 74.25 | 0 | 371.25 | 297 | 74.25
WP1_S03-202809 | WP1_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | 2028-09-30 | 2028/29 | Straight-line | 80% | 371.25 | 297 | 74.25 | 0 | 371.25 | 297 | 74.25
WP1_S03-202810 | WP1_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | 2028-10-31 | 2028/29 | Straight-line | 80% | 371.25 | 297 | 74.25 | 0 | 371.25 | 297 | 74.25
WP1_S03-202811 | WP1_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | 2028-11-30 | 2028/29 | Straight-line | 80% | 371.25 | 297 | 74.25 | 0 | 371.25 | 297 | 74.25
WP1_S03-202812 | WP1_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | 2028-12-31 | 2028/29 | Straight-line | 80% | 371.25 | 297 | 74.25 | 0 | 371.25 | 297 | 74.25
WP1_S03-202901 | WP1_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | 2029-01-31 | 2028/29 | Straight-line | 80% | 371.25 | 297 | 74.25 | 0 | 371.25 | 297 | 74.25
WP1_S03-202902 | WP1_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | 2029-02-28 | 2028/29 | Straight-line | 80% | 371.25 | 297 | 74.25 | 0 | 371.25 | 297 | 74.25
WP1_S03-202903 | WP1_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | 2029-03-31 | 2028/29 | Straight-line | 80% | 371.25 | 297 | 74.25 | 0 | 371.25 | 297 | 74.25
WP1_TRAVEL-202604 | WP1_TRAVEL | RUSI - UK rail, local travel and subsistence Budget | WP1 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | 2026-04-30 | 2026/27 | Straight-line | 80% | 208.3333 | 166.6667 | 41.6667 | 0 | 208.3333 | 166.6667 | 41.6667
WP1_TRAVEL-202605 | WP1_TRAVEL | RUSI - UK rail, local travel and subsistence Budget | WP1 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | 2026-05-31 | 2026/27 | Straight-line | 80% | 208.3333 | 166.6667 | 41.6667 | 0 | 208.3333 | 166.6667 | 41.6667
WP1_TRAVEL-202606 | WP1_TRAVEL | RUSI - UK rail, local travel and subsistence Budget | WP1 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | 2026-06-30 | 2026/27 | Straight-line | 80% | 208.3333 | 166.6667 | 41.6667 | 0 | 208.3333 | 166.6667 | 41.6667
WP1_TRAVEL-202607 | WP1_TRAVEL | RUSI - UK rail, local travel and subsistence Budget | WP1 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | 2026-07-31 | 2026/27 | Straight-line | 80% | 208.3333 | 166.6667 | 41.6667 | 0 | 208.3333 | 166.6667 | 41.6667
WP1_TRAVEL-202608 | WP1_TRAVEL | RUSI - UK rail, local travel and subsistence Budget | WP1 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | 2026-08-31 | 2026/27 | Straight-line | 80% | 208.3333 | 166.6667 | 41.6667 | 0 | 208.3333 | 166.6667 | 41.6667
WP1_TRAVEL-202609 | WP1_TRAVEL | RUSI - UK rail, local travel and subsistence Budget | WP1 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | 2026-09-30 | 2026/27 | Straight-line | 80% | 208.3333 | 166.6667 | 41.6667 | 0 | 208.3333 | 166.6667 | 41.6667
WP1_TRAVEL-202610 | WP1_TRAVEL | RUSI - UK rail, local travel and subsistence Budget | WP1 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | 2026-10-31 | 2026/27 | Straight-line | 80% | 208.3333 | 166.6667 | 41.6667 | 0 | 208.3333 | 166.6667 | 41.6667
WP1_TRAVEL-202611 | WP1_TRAVEL | RUSI - UK rail, local travel and subsistence Budget | WP1 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | 2026-11-30 | 2026/27 | Straight-line | 80% | 208.3333 | 166.6667 | 41.6667 | 0 | 208.3333 | 166.6667 | 41.6667
WP1_TRAVEL-202612 | WP1_TRAVEL | RUSI - UK rail, local travel and subsistence Budget | WP1 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | 2026-12-31 | 2026/27 | Straight-line | 80% | 208.3333 | 166.6667 | 41.6667 | 0 | 208.3333 | 166.6667 | 41.6667
WP1_TRAVEL-202701 | WP1_TRAVEL | RUSI - UK rail, local travel and subsistence Budget | WP1 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | 2027-01-31 | 2026/27 | Straight-line | 80% | 208.3333 | 166.6667 | 41.6667 | 0 | 208.3333 | 166.6667 | 41.6667
WP1_TRAVEL-202702 | WP1_TRAVEL | RUSI - UK rail, local travel and subsistence Budget | WP1 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | 2027-02-28 | 2026/27 | Straight-line | 80% | 208.3333 | 166.6667 | 41.6667 | 0 | 208.3333 | 166.6667 | 41.6667
WP1_TRAVEL-202703 | WP1_TRAVEL | RUSI - UK rail, local travel and subsistence Budget | WP1 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | 2027-03-31 | 2026/27 | Straight-line | 80% | 208.3333 | 166.6667 | 41.6667 | 0 | 208.3333 | 166.6667 | 41.6667
WP1_TRAVEL-202704 | WP1_TRAVEL | RUSI - UK rail, local travel and subsistence Budget | WP1 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | 2027-04-30 | 2027/28 | Straight-line | 80% | 208.3333 | 166.6667 | 41.6667 | 0 | 208.3333 | 166.6667 | 41.6667
WP1_TRAVEL-202705 | WP1_TRAVEL | RUSI - UK rail, local travel and subsistence Budget | WP1 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | 2027-05-31 | 2027/28 | Straight-line | 80% | 208.3333 | 166.6667 | 41.6667 | 0 | 208.3333 | 166.6667 | 41.6667
WP1_TRAVEL-202706 | WP1_TRAVEL | RUSI - UK rail, local travel and subsistence Budget | WP1 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | 2027-06-30 | 2027/28 | Straight-line | 80% | 208.3333 | 166.6667 | 41.6667 | 0 | 208.3333 | 166.6667 | 41.6667
WP1_TRAVEL-202707 | WP1_TRAVEL | RUSI - UK rail, local travel and subsistence Budget | WP1 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | 2027-07-31 | 2027/28 | Straight-line | 80% | 208.3333 | 166.6667 | 41.6667 | 0 | 208.3333 | 166.6667 | 41.6667
WP1_TRAVEL-202708 | WP1_TRAVEL | RUSI - UK rail, local travel and subsistence Budget | WP1 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | 2027-08-31 | 2027/28 | Straight-line | 80% | 208.3333 | 166.6667 | 41.6667 | 0 | 208.3333 | 166.6667 | 41.6667
WP1_TRAVEL-202709 | WP1_TRAVEL | RUSI - UK rail, local travel and subsistence Budget | WP1 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | 2027-09-30 | 2027/28 | Straight-line | 80% | 208.3333 | 166.6667 | 41.6667 | 0 | 208.3333 | 166.6667 | 41.6667
WP1_TRAVEL-202710 | WP1_TRAVEL | RUSI - UK rail, local travel and subsistence Budget | WP1 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | 2027-10-31 | 2027/28 | Straight-line | 80% | 208.3333 | 166.6667 | 41.6667 | 0 | 208.3333 | 166.6667 | 41.6667
WP1_TRAVEL-202711 | WP1_TRAVEL | RUSI - UK rail, local travel and subsistence Budget | WP1 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | 2027-11-30 | 2027/28 | Straight-line | 80% | 208.3333 | 166.6667 | 41.6667 | 0 | 208.3333 | 166.6667 | 41.6667
WP1_TRAVEL-202712 | WP1_TRAVEL | RUSI - UK rail, local travel and subsistence Budget | WP1 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | 2027-12-31 | 2027/28 | Straight-line | 80% | 208.3333 | 166.6667 | 41.6667 | 0 | 208.3333 | 166.6667 | 41.6667
WP1_TRAVEL-202801 | WP1_TRAVEL | RUSI - UK rail, local travel and subsistence Budget | WP1 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | 2028-01-31 | 2027/28 | Straight-line | 80% | 208.3333 | 166.6667 | 41.6667 | 0 | 208.3333 | 166.6667 | 41.6667
WP1_TRAVEL-202802 | WP1_TRAVEL | RUSI - UK rail, local travel and subsistence Budget | WP1 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | 2028-02-29 | 2027/28 | Straight-line | 80% | 208.3333 | 166.6667 | 41.6667 | 0 | 208.3333 | 166.6667 | 41.6667
WP1_TRAVEL-202803 | WP1_TRAVEL | RUSI - UK rail, local travel and subsistence Budget | WP1 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | 2028-03-31 | 2027/28 | Straight-line | 80% | 208.3333 | 166.6667 | 41.6667 | 0 | 208.3333 | 166.6667 | 41.6667
WP1_TRAVEL-202804 | WP1_TRAVEL | RUSI - UK rail, local travel and subsistence Budget | WP1 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | 2028-04-30 | 2028/29 | Straight-line | 80% | 208.3333 | 166.6667 | 41.6667 | 0 | 208.3333 | 166.6667 | 41.6667
WP1_TRAVEL-202805 | WP1_TRAVEL | RUSI - UK rail, local travel and subsistence Budget | WP1 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | 2028-05-31 | 2028/29 | Straight-line | 80% | 208.3333 | 166.6667 | 41.6667 | 0 | 208.3333 | 166.6667 | 41.6667
WP1_TRAVEL-202806 | WP1_TRAVEL | RUSI - UK rail, local travel and subsistence Budget | WP1 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | 2028-06-30 | 2028/29 | Straight-line | 80% | 208.3333 | 166.6667 | 41.6667 | 0 | 208.3333 | 166.6667 | 41.6667
WP1_TRAVEL-202807 | WP1_TRAVEL | RUSI - UK rail, local travel and subsistence Budget | WP1 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | 2028-07-31 | 2028/29 | Straight-line | 80% | 208.3333 | 166.6667 | 41.6667 | 0 | 208.3333 | 166.6667 | 41.6667
WP1_TRAVEL-202808 | WP1_TRAVEL | RUSI - UK rail, local travel and subsistence Budget | WP1 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | 2028-08-31 | 2028/29 | Straight-line | 80% | 208.3333 | 166.6667 | 41.6667 | 0 | 208.3333 | 166.6667 | 41.6667
WP1_TRAVEL-202809 | WP1_TRAVEL | RUSI - UK rail, local travel and subsistence Budget | WP1 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | 2028-09-30 | 2028/29 | Straight-line | 80% | 208.3333 | 166.6667 | 41.6667 | 0 | 208.3333 | 166.6667 | 41.6667
WP1_TRAVEL-202810 | WP1_TRAVEL | RUSI - UK rail, local travel and subsistence Budget | WP1 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | 2028-10-31 | 2028/29 | Straight-line | 80% | 208.3333 | 166.6667 | 41.6667 | 0 | 208.3333 | 166.6667 | 41.6667
WP1_TRAVEL-202811 | WP1_TRAVEL | RUSI - UK rail, local travel and subsistence Budget | WP1 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | 2028-11-30 | 2028/29 | Straight-line | 80% | 208.3333 | 166.6667 | 41.6667 | 0 | 208.3333 | 166.6667 | 41.6667
WP1_TRAVEL-202812 | WP1_TRAVEL | RUSI - UK rail, local travel and subsistence Budget | WP1 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | 2028-12-31 | 2028/29 | Straight-line | 80% | 208.3333 | 166.6667 | 41.6667 | 0 | 208.3333 | 166.6667 | 41.6667
WP1_TRAVEL-202901 | WP1_TRAVEL | RUSI - UK rail, local travel and subsistence Budget | WP1 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | 2029-01-31 | 2028/29 | Straight-line | 80% | 208.3333 | 166.6667 | 41.6667 | 0 | 208.3333 | 166.6667 | 41.6667
WP1_TRAVEL-202902 | WP1_TRAVEL | RUSI - UK rail, local travel and subsistence Budget | WP1 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | 2029-02-28 | 2028/29 | Straight-line | 80% | 208.3333 | 166.6667 | 41.6667 | 0 | 208.3333 | 166.6667 | 41.6667
WP1_TRAVEL-202903 | WP1_TRAVEL | RUSI - UK rail, local travel and subsistence Budget | WP1 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | 2029-03-31 | 2028/29 | Straight-line | 80% | 208.3333 | 166.6667 | 41.6667 | 0 | 208.3333 | 166.6667 | 41.6667
WP1_CONF-202604 | WP1_CONF | RUSI - five-day flagship London conferences (launch and close) | WP1 | Directly Incurred | Other Directly Incurred | Conferences | 2026-04-30 | 2026/27 | Event month | 80% | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP1_CONF-202605 | WP1_CONF | RUSI - five-day flagship London conferences (launch and close) | WP1 | Directly Incurred | Other Directly Incurred | Conferences | 2026-05-31 | 2026/27 | Event month | 80% | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP1_CONF-202606 | WP1_CONF | RUSI - five-day flagship London conferences (launch and close) | WP1 | Directly Incurred | Other Directly Incurred | Conferences | 2026-06-30 | 2026/27 | Event month | 80% | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP1_CONF-202607 | WP1_CONF | RUSI - five-day flagship London conferences (launch and close) | WP1 | Directly Incurred | Other Directly Incurred | Conferences | 2026-07-31 | 2026/27 | Event month | 80% | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP1_CONF-202608 | WP1_CONF | RUSI - five-day flagship London conferences (launch and close) | WP1 | Directly Incurred | Other Directly Incurred | Conferences | 2026-08-31 | 2026/27 | Event month | 80% | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP1_CONF-202609 | WP1_CONF | RUSI - five-day flagship London conferences (launch and close) | WP1 | Directly Incurred | Other Directly Incurred | Conferences | 2026-09-30 | 2026/27 | Event month | 80% | 15000 | 12000 | 3000 | 0 | 15000 | 12000 | 3000
WP1_CONF-202610 | WP1_CONF | RUSI - five-day flagship London conferences (launch and close) | WP1 | Directly Incurred | Other Directly Incurred | Conferences | 2026-10-31 | 2026/27 | Event month | 80% | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP1_CONF-202611 | WP1_CONF | RUSI - five-day flagship London conferences (launch and close) | WP1 | Directly Incurred | Other Directly Incurred | Conferences | 2026-11-30 | 2026/27 | Event month | 80% | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP1_CONF-202612 | WP1_CONF | RUSI - five-day flagship London conferences (launch and close) | WP1 | Directly Incurred | Other Directly Incurred | Conferences | 2026-12-31 | 2026/27 | Event month | 80% | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP1_CONF-202701 | WP1_CONF | RUSI - five-day flagship London conferences (launch and close) | WP1 | Directly Incurred | Other Directly Incurred | Conferences | 2027-01-31 | 2026/27 | Event month | 80% | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP1_CONF-202702 | WP1_CONF | RUSI - five-day flagship London conferences (launch and close) | WP1 | Directly Incurred | Other Directly Incurred | Conferences | 2027-02-28 | 2026/27 | Event month | 80% | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP1_CONF-202703 | WP1_CONF | RUSI - five-day flagship London conferences (launch and close) | WP1 | Directly Incurred | Other Directly Incurred | Conferences | 2027-03-31 | 2026/27 | Event month | 80% | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP1_CONF-202704 | WP1_CONF | RUSI - five-day flagship London conferences (launch and close) | WP1 | Directly Incurred | Other Directly Incurred | Conferences | 2027-04-30 | 2027/28 | Event month | 80% | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP1_CONF-202705 | WP1_CONF | RUSI - five-day flagship London conferences (launch and close) | WP1 | Directly Incurred | Other Directly Incurred | Conferences | 2027-05-31 | 2027/28 | Event month | 80% | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP1_CONF-202706 | WP1_CONF | RUSI - five-day flagship London conferences (launch and close) | WP1 | Directly Incurred | Other Directly Incurred | Conferences | 2027-06-30 | 2027/28 | Event month | 80% | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP1_CONF-202707 | WP1_CONF | RUSI - five-day flagship London conferences (launch and close) | WP1 | Directly Incurred | Other Directly Incurred | Conferences | 2027-07-31 | 2027/28 | Event month | 80% | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP1_CONF-202708 | WP1_CONF | RUSI - five-day flagship London conferences (launch and close) | WP1 | Directly Incurred | Other Directly Incurred | Conferences | 2027-08-31 | 2027/28 | Event month | 80% | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP1_CONF-202709 | WP1_CONF | RUSI - five-day flagship London conferences (launch and close) | WP1 | Directly Incurred | Other Directly Incurred | Conferences | 2027-09-30 | 2027/28 | Event month | 80% | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP1_CONF-202710 | WP1_CONF | RUSI - five-day flagship London conferences (launch and close) | WP1 | Directly Incurred | Other Directly Incurred | Conferences | 2027-10-31 | 2027/28 | Event month | 80% | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP1_CONF-202711 | WP1_CONF | RUSI - five-day flagship London conferences (launch and close) | WP1 | Directly Incurred | Other Directly Incurred | Conferences | 2027-11-30 | 2027/28 | Event month | 80% | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP1_CONF-202712 | WP1_CONF | RUSI - five-day flagship London conferences (launch and close) | WP1 | Directly Incurred | Other Directly Incurred | Conferences | 2027-12-31 | 2027/28 | Event month | 80% | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP1_CONF-202801 | WP1_CONF | RUSI - five-day flagship London conferences (launch and close) | WP1 | Directly Incurred | Other Directly Incurred | Conferences | 2028-01-31 | 2027/28 | Event month | 80% | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP1_CONF-202802 | WP1_CONF | RUSI - five-day flagship London conferences (launch and close) | WP1 | Directly Incurred | Other Directly Incurred | Conferences | 2028-02-29 | 2027/28 | Event month | 80% | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP1_CONF-202803 | WP1_CONF | RUSI - five-day flagship London conferences (launch and close) | WP1 | Directly Incurred | Other Directly Incurred | Conferences | 2028-03-31 | 2027/28 | Event month | 80% | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP1_CONF-202804 | WP1_CONF | RUSI - five-day flagship London conferences (launch and close) | WP1 | Directly Incurred | Other Directly Incurred | Conferences | 2028-04-30 | 2028/29 | Event month | 80% | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP1_CONF-202805 | WP1_CONF | RUSI - five-day flagship London conferences (launch and close) | WP1 | Directly Incurred | Other Directly Incurred | Conferences | 2028-05-31 | 2028/29 | Event month | 80% | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP1_CONF-202806 | WP1_CONF | RUSI - five-day flagship London conferences (launch and close) | WP1 | Directly Incurred | Other Directly Incurred | Conferences | 2028-06-30 | 2028/29 | Event month | 80% | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP1_CONF-202807 | WP1_CONF | RUSI - five-day flagship London conferences (launch and close) | WP1 | Directly Incurred | Other Directly Incurred | Conferences | 2028-07-31 | 2028/29 | Event month | 80% | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP1_CONF-202808 | WP1_CONF | RUSI - five-day flagship London conferences (launch and close) | WP1 | Directly Incurred | Other Directly Incurred | Conferences | 2028-08-31 | 2028/29 | Event month | 80% | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP1_CONF-202809 | WP1_CONF | RUSI - five-day flagship London conferences (launch and close) | WP1 | Directly Incurred | Other Directly Incurred | Conferences | 2028-09-30 | 2028/29 | Event month | 80% | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP1_CONF-202810 | WP1_CONF | RUSI - five-day flagship London conferences (launch and close) | WP1 | Directly Incurred | Other Directly Incurred | Conferences | 2028-10-31 | 2028/29 | Event month | 80% | 15000 | 12000 | 3000 | 0 | 15000 | 12000 | 3000
WP1_CONF-202811 | WP1_CONF | RUSI - five-day flagship London conferences (launch and close) | WP1 | Directly Incurred | Other Directly Incurred | Conferences | 2028-11-30 | 2028/29 | Event month | 80% | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP1_CONF-202812 | WP1_CONF | RUSI - five-day flagship London conferences (launch and close) | WP1 | Directly Incurred | Other Directly Incurred | Conferences | 2028-12-31 | 2028/29 | Event month | 80% | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP1_CONF-202901 | WP1_CONF | RUSI - five-day flagship London conferences (launch and close) | WP1 | Directly Incurred | Other Directly Incurred | Conferences | 2029-01-31 | 2028/29 | Event month | 80% | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP1_CONF-202902 | WP1_CONF | RUSI - five-day flagship London conferences (launch and close) | WP1 | Directly Incurred | Other Directly Incurred | Conferences | 2029-02-28 | 2028/29 | Event month | 80% | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP1_CONF-202903 | WP1_CONF | RUSI - five-day flagship London conferences (launch and close) | WP1 | Directly Incurred | Other Directly Incurred | Conferences | 2029-03-31 | 2028/29 | Event month | 80% | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP1_WORKSHOP-202604 | WP1_WORKSHOP | RUSI - UK national and regional workshops | WP1 | Directly Incurred | Other Directly Incurred | Workshops | 2026-04-30 | 2026/27 | Straight-line | 80% | 333.3333 | 266.6667 | 66.6667 | 0 | 333.3333 | 266.6667 | 66.6667
WP1_WORKSHOP-202605 | WP1_WORKSHOP | RUSI - UK national and regional workshops | WP1 | Directly Incurred | Other Directly Incurred | Workshops | 2026-05-31 | 2026/27 | Straight-line | 80% | 333.3333 | 266.6667 | 66.6667 | 0 | 333.3333 | 266.6667 | 66.6667
WP1_WORKSHOP-202606 | WP1_WORKSHOP | RUSI - UK national and regional workshops | WP1 | Directly Incurred | Other Directly Incurred | Workshops | 2026-06-30 | 2026/27 | Straight-line | 80% | 333.3333 | 266.6667 | 66.6667 | 0 | 333.3333 | 266.6667 | 66.6667
WP1_WORKSHOP-202607 | WP1_WORKSHOP | RUSI - UK national and regional workshops | WP1 | Directly Incurred | Other Directly Incurred | Workshops | 2026-07-31 | 2026/27 | Straight-line | 80% | 333.3333 | 266.6667 | 66.6667 | 0 | 333.3333 | 266.6667 | 66.6667
WP1_WORKSHOP-202608 | WP1_WORKSHOP | RUSI - UK national and regional workshops | WP1 | Directly Incurred | Other Directly Incurred | Workshops | 2026-08-31 | 2026/27 | Straight-line | 80% | 333.3333 | 266.6667 | 66.6667 | 0 | 333.3333 | 266.6667 | 66.6667
WP1_WORKSHOP-202609 | WP1_WORKSHOP | RUSI - UK national and regional workshops | WP1 | Directly Incurred | Other Directly Incurred | Workshops | 2026-09-30 | 2026/27 | Straight-line | 80% | 333.3333 | 266.6667 | 66.6667 | 0 | 333.3333 | 266.6667 | 66.6667
WP1_WORKSHOP-202610 | WP1_WORKSHOP | RUSI - UK national and regional workshops | WP1 | Directly Incurred | Other Directly Incurred | Workshops | 2026-10-31 | 2026/27 | Straight-line | 80% | 333.3333 | 266.6667 | 66.6667 | 0 | 333.3333 | 266.6667 | 66.6667
WP1_WORKSHOP-202611 | WP1_WORKSHOP | RUSI - UK national and regional workshops | WP1 | Directly Incurred | Other Directly Incurred | Workshops | 2026-11-30 | 2026/27 | Straight-line | 80% | 333.3333 | 266.6667 | 66.6667 | 0 | 333.3333 | 266.6667 | 66.6667
WP1_WORKSHOP-202612 | WP1_WORKSHOP | RUSI - UK national and regional workshops | WP1 | Directly Incurred | Other Directly Incurred | Workshops | 2026-12-31 | 2026/27 | Straight-line | 80% | 333.3333 | 266.6667 | 66.6667 | 0 | 333.3333 | 266.6667 | 66.6667
WP1_WORKSHOP-202701 | WP1_WORKSHOP | RUSI - UK national and regional workshops | WP1 | Directly Incurred | Other Directly Incurred | Workshops | 2027-01-31 | 2026/27 | Straight-line | 80% | 333.3333 | 266.6667 | 66.6667 | 0 | 333.3333 | 266.6667 | 66.6667
WP1_WORKSHOP-202702 | WP1_WORKSHOP | RUSI - UK national and regional workshops | WP1 | Directly Incurred | Other Directly Incurred | Workshops | 2027-02-28 | 2026/27 | Straight-line | 80% | 333.3333 | 266.6667 | 66.6667 | 0 | 333.3333 | 266.6667 | 66.6667
WP1_WORKSHOP-202703 | WP1_WORKSHOP | RUSI - UK national and regional workshops | WP1 | Directly Incurred | Other Directly Incurred | Workshops | 2027-03-31 | 2026/27 | Straight-line | 80% | 333.3333 | 266.6667 | 66.6667 | 0 | 333.3333 | 266.6667 | 66.6667
WP1_WORKSHOP-202704 | WP1_WORKSHOP | RUSI - UK national and regional workshops | WP1 | Directly Incurred | Other Directly Incurred | Workshops | 2027-04-30 | 2027/28 | Straight-line | 80% | 333.3333 | 266.6667 | 66.6667 | 0 | 333.3333 | 266.6667 | 66.6667
WP1_WORKSHOP-202705 | WP1_WORKSHOP | RUSI - UK national and regional workshops | WP1 | Directly Incurred | Other Directly Incurred | Workshops | 2027-05-31 | 2027/28 | Straight-line | 80% | 333.3333 | 266.6667 | 66.6667 | 0 | 333.3333 | 266.6667 | 66.6667
WP1_WORKSHOP-202706 | WP1_WORKSHOP | RUSI - UK national and regional workshops | WP1 | Directly Incurred | Other Directly Incurred | Workshops | 2027-06-30 | 2027/28 | Straight-line | 80% | 333.3333 | 266.6667 | 66.6667 | 0 | 333.3333 | 266.6667 | 66.6667
WP1_WORKSHOP-202707 | WP1_WORKSHOP | RUSI - UK national and regional workshops | WP1 | Directly Incurred | Other Directly Incurred | Workshops | 2027-07-31 | 2027/28 | Straight-line | 80% | 333.3333 | 266.6667 | 66.6667 | 0 | 333.3333 | 266.6667 | 66.6667
WP1_WORKSHOP-202708 | WP1_WORKSHOP | RUSI - UK national and regional workshops | WP1 | Directly Incurred | Other Directly Incurred | Workshops | 2027-08-31 | 2027/28 | Straight-line | 80% | 333.3333 | 266.6667 | 66.6667 | 0 | 333.3333 | 266.6667 | 66.6667
WP1_WORKSHOP-202709 | WP1_WORKSHOP | RUSI - UK national and regional workshops | WP1 | Directly Incurred | Other Directly Incurred | Workshops | 2027-09-30 | 2027/28 | Straight-line | 80% | 333.3333 | 266.6667 | 66.6667 | 0 | 333.3333 | 266.6667 | 66.6667
WP1_WORKSHOP-202710 | WP1_WORKSHOP | RUSI - UK national and regional workshops | WP1 | Directly Incurred | Other Directly Incurred | Workshops | 2027-10-31 | 2027/28 | Straight-line | 80% | 333.3333 | 266.6667 | 66.6667 | 0 | 333.3333 | 266.6667 | 66.6667
WP1_WORKSHOP-202711 | WP1_WORKSHOP | RUSI - UK national and regional workshops | WP1 | Directly Incurred | Other Directly Incurred | Workshops | 2027-11-30 | 2027/28 | Straight-line | 80% | 333.3333 | 266.6667 | 66.6667 | 0 | 333.3333 | 266.6667 | 66.6667
WP1_WORKSHOP-202712 | WP1_WORKSHOP | RUSI - UK national and regional workshops | WP1 | Directly Incurred | Other Directly Incurred | Workshops | 2027-12-31 | 2027/28 | Straight-line | 80% | 333.3333 | 266.6667 | 66.6667 | 0 | 333.3333 | 266.6667 | 66.6667
WP1_WORKSHOP-202801 | WP1_WORKSHOP | RUSI - UK national and regional workshops | WP1 | Directly Incurred | Other Directly Incurred | Workshops | 2028-01-31 | 2027/28 | Straight-line | 80% | 333.3333 | 266.6667 | 66.6667 | 0 | 333.3333 | 266.6667 | 66.6667
WP1_WORKSHOP-202802 | WP1_WORKSHOP | RUSI - UK national and regional workshops | WP1 | Directly Incurred | Other Directly Incurred | Workshops | 2028-02-29 | 2027/28 | Straight-line | 80% | 333.3333 | 266.6667 | 66.6667 | 0 | 333.3333 | 266.6667 | 66.6667
WP1_WORKSHOP-202803 | WP1_WORKSHOP | RUSI - UK national and regional workshops | WP1 | Directly Incurred | Other Directly Incurred | Workshops | 2028-03-31 | 2027/28 | Straight-line | 80% | 333.3333 | 266.6667 | 66.6667 | 0 | 333.3333 | 266.6667 | 66.6667
WP1_WORKSHOP-202804 | WP1_WORKSHOP | RUSI - UK national and regional workshops | WP1 | Directly Incurred | Other Directly Incurred | Workshops | 2028-04-30 | 2028/29 | Straight-line | 80% | 333.3333 | 266.6667 | 66.6667 | 0 | 333.3333 | 266.6667 | 66.6667
WP1_WORKSHOP-202805 | WP1_WORKSHOP | RUSI - UK national and regional workshops | WP1 | Directly Incurred | Other Directly Incurred | Workshops | 2028-05-31 | 2028/29 | Straight-line | 80% | 333.3333 | 266.6667 | 66.6667 | 0 | 333.3333 | 266.6667 | 66.6667
WP1_WORKSHOP-202806 | WP1_WORKSHOP | RUSI - UK national and regional workshops | WP1 | Directly Incurred | Other Directly Incurred | Workshops | 2028-06-30 | 2028/29 | Straight-line | 80% | 333.3333 | 266.6667 | 66.6667 | 0 | 333.3333 | 266.6667 | 66.6667
WP1_WORKSHOP-202807 | WP1_WORKSHOP | RUSI - UK national and regional workshops | WP1 | Directly Incurred | Other Directly Incurred | Workshops | 2028-07-31 | 2028/29 | Straight-line | 80% | 333.3333 | 266.6667 | 66.6667 | 0 | 333.3333 | 266.6667 | 66.6667
WP1_WORKSHOP-202808 | WP1_WORKSHOP | RUSI - UK national and regional workshops | WP1 | Directly Incurred | Other Directly Incurred | Workshops | 2028-08-31 | 2028/29 | Straight-line | 80% | 333.3333 | 266.6667 | 66.6667 | 0 | 333.3333 | 266.6667 | 66.6667
WP1_WORKSHOP-202809 | WP1_WORKSHOP | RUSI - UK national and regional workshops | WP1 | Directly Incurred | Other Directly Incurred | Workshops | 2028-09-30 | 2028/29 | Straight-line | 80% | 333.3333 | 266.6667 | 66.6667 | 0 | 333.3333 | 266.6667 | 66.6667
WP1_WORKSHOP-202810 | WP1_WORKSHOP | RUSI - UK national and regional workshops | WP1 | Directly Incurred | Other Directly Incurred | Workshops | 2028-10-31 | 2028/29 | Straight-line | 80% | 333.3333 | 266.6667 | 66.6667 | 0 | 333.3333 | 266.6667 | 66.6667
WP1_WORKSHOP-202811 | WP1_WORKSHOP | RUSI - UK national and regional workshops | WP1 | Directly Incurred | Other Directly Incurred | Workshops | 2028-11-30 | 2028/29 | Straight-line | 80% | 333.3333 | 266.6667 | 66.6667 | 0 | 333.3333 | 266.6667 | 66.6667
WP1_WORKSHOP-202812 | WP1_WORKSHOP | RUSI - UK national and regional workshops | WP1 | Directly Incurred | Other Directly Incurred | Workshops | 2028-12-31 | 2028/29 | Straight-line | 80% | 333.3333 | 266.6667 | 66.6667 | 0 | 333.3333 | 266.6667 | 66.6667
WP1_WORKSHOP-202901 | WP1_WORKSHOP | RUSI - UK national and regional workshops | WP1 | Directly Incurred | Other Directly Incurred | Workshops | 2029-01-31 | 2028/29 | Straight-line | 80% | 333.3333 | 266.6667 | 66.6667 | 0 | 333.3333 | 266.6667 | 66.6667
WP1_WORKSHOP-202902 | WP1_WORKSHOP | RUSI - UK national and regional workshops | WP1 | Directly Incurred | Other Directly Incurred | Workshops | 2029-02-28 | 2028/29 | Straight-line | 80% | 333.3333 | 266.6667 | 66.6667 | 0 | 333.3333 | 266.6667 | 66.6667
WP1_WORKSHOP-202903 | WP1_WORKSHOP | RUSI - UK national and regional workshops | WP1 | Directly Incurred | Other Directly Incurred | Workshops | 2029-03-31 | 2028/29 | Straight-line | 80% | 333.3333 | 266.6667 | 66.6667 | 0 | 333.3333 | 266.6667 | 66.6667
WP1_PANEL-202604 | WP1_PANEL | RUSI - hybrid panels and practitioner roundtables | WP1 | Directly Incurred | Other Directly Incurred | Panels & Roundtables | 2026-04-30 | 2026/27 | Straight-line | 80% | 125 | 100 | 25 | 0 | 125 | 100 | 25
WP1_PANEL-202605 | WP1_PANEL | RUSI - hybrid panels and practitioner roundtables | WP1 | Directly Incurred | Other Directly Incurred | Panels & Roundtables | 2026-05-31 | 2026/27 | Straight-line | 80% | 125 | 100 | 25 | 0 | 125 | 100 | 25
WP1_PANEL-202606 | WP1_PANEL | RUSI - hybrid panels and practitioner roundtables | WP1 | Directly Incurred | Other Directly Incurred | Panels & Roundtables | 2026-06-30 | 2026/27 | Straight-line | 80% | 125 | 100 | 25 | 0 | 125 | 100 | 25
WP1_PANEL-202607 | WP1_PANEL | RUSI - hybrid panels and practitioner roundtables | WP1 | Directly Incurred | Other Directly Incurred | Panels & Roundtables | 2026-07-31 | 2026/27 | Straight-line | 80% | 125 | 100 | 25 | 0 | 125 | 100 | 25
WP1_PANEL-202608 | WP1_PANEL | RUSI - hybrid panels and practitioner roundtables | WP1 | Directly Incurred | Other Directly Incurred | Panels & Roundtables | 2026-08-31 | 2026/27 | Straight-line | 80% | 125 | 100 | 25 | 0 | 125 | 100 | 25
WP1_PANEL-202609 | WP1_PANEL | RUSI - hybrid panels and practitioner roundtables | WP1 | Directly Incurred | Other Directly Incurred | Panels & Roundtables | 2026-09-30 | 2026/27 | Straight-line | 80% | 125 | 100 | 25 | 0 | 125 | 100 | 25
WP1_PANEL-202610 | WP1_PANEL | RUSI - hybrid panels and practitioner roundtables | WP1 | Directly Incurred | Other Directly Incurred | Panels & Roundtables | 2026-10-31 | 2026/27 | Straight-line | 80% | 125 | 100 | 25 | 0 | 125 | 100 | 25
WP1_PANEL-202611 | WP1_PANEL | RUSI - hybrid panels and practitioner roundtables | WP1 | Directly Incurred | Other Directly Incurred | Panels & Roundtables | 2026-11-30 | 2026/27 | Straight-line | 80% | 125 | 100 | 25 | 0 | 125 | 100 | 25
WP1_PANEL-202612 | WP1_PANEL | RUSI - hybrid panels and practitioner roundtables | WP1 | Directly Incurred | Other Directly Incurred | Panels & Roundtables | 2026-12-31 | 2026/27 | Straight-line | 80% | 125 | 100 | 25 | 0 | 125 | 100 | 25
WP1_PANEL-202701 | WP1_PANEL | RUSI - hybrid panels and practitioner roundtables | WP1 | Directly Incurred | Other Directly Incurred | Panels & Roundtables | 2027-01-31 | 2026/27 | Straight-line | 80% | 125 | 100 | 25 | 0 | 125 | 100 | 25
WP1_PANEL-202702 | WP1_PANEL | RUSI - hybrid panels and practitioner roundtables | WP1 | Directly Incurred | Other Directly Incurred | Panels & Roundtables | 2027-02-28 | 2026/27 | Straight-line | 80% | 125 | 100 | 25 | 0 | 125 | 100 | 25
WP1_PANEL-202703 | WP1_PANEL | RUSI - hybrid panels and practitioner roundtables | WP1 | Directly Incurred | Other Directly Incurred | Panels & Roundtables | 2027-03-31 | 2026/27 | Straight-line | 80% | 125 | 100 | 25 | 0 | 125 | 100 | 25
WP1_PANEL-202704 | WP1_PANEL | RUSI - hybrid panels and practitioner roundtables | WP1 | Directly Incurred | Other Directly Incurred | Panels & Roundtables | 2027-04-30 | 2027/28 | Straight-line | 80% | 125 | 100 | 25 | 0 | 125 | 100 | 25
WP1_PANEL-202705 | WP1_PANEL | RUSI - hybrid panels and practitioner roundtables | WP1 | Directly Incurred | Other Directly Incurred | Panels & Roundtables | 2027-05-31 | 2027/28 | Straight-line | 80% | 125 | 100 | 25 | 0 | 125 | 100 | 25
WP1_PANEL-202706 | WP1_PANEL | RUSI - hybrid panels and practitioner roundtables | WP1 | Directly Incurred | Other Directly Incurred | Panels & Roundtables | 2027-06-30 | 2027/28 | Straight-line | 80% | 125 | 100 | 25 | 0 | 125 | 100 | 25
WP1_PANEL-202707 | WP1_PANEL | RUSI - hybrid panels and practitioner roundtables | WP1 | Directly Incurred | Other Directly Incurred | Panels & Roundtables | 2027-07-31 | 2027/28 | Straight-line | 80% | 125 | 100 | 25 | 0 | 125 | 100 | 25
WP1_PANEL-202708 | WP1_PANEL | RUSI - hybrid panels and practitioner roundtables | WP1 | Directly Incurred | Other Directly Incurred | Panels & Roundtables | 2027-08-31 | 2027/28 | Straight-line | 80% | 125 | 100 | 25 | 0 | 125 | 100 | 25
WP1_PANEL-202709 | WP1_PANEL | RUSI - hybrid panels and practitioner roundtables | WP1 | Directly Incurred | Other Directly Incurred | Panels & Roundtables | 2027-09-30 | 2027/28 | Straight-line | 80% | 125 | 100 | 25 | 0 | 125 | 100 | 25
WP1_PANEL-202710 | WP1_PANEL | RUSI - hybrid panels and practitioner roundtables | WP1 | Directly Incurred | Other Directly Incurred | Panels & Roundtables | 2027-10-31 | 2027/28 | Straight-line | 80% | 125 | 100 | 25 | 0 | 125 | 100 | 25
WP1_PANEL-202711 | WP1_PANEL | RUSI - hybrid panels and practitioner roundtables | WP1 | Directly Incurred | Other Directly Incurred | Panels & Roundtables | 2027-11-30 | 2027/28 | Straight-line | 80% | 125 | 100 | 25 | 0 | 125 | 100 | 25
WP1_PANEL-202712 | WP1_PANEL | RUSI - hybrid panels and practitioner roundtables | WP1 | Directly Incurred | Other Directly Incurred | Panels & Roundtables | 2027-12-31 | 2027/28 | Straight-line | 80% | 125 | 100 | 25 | 0 | 125 | 100 | 25
WP1_PANEL-202801 | WP1_PANEL | RUSI - hybrid panels and practitioner roundtables | WP1 | Directly Incurred | Other Directly Incurred | Panels & Roundtables | 2028-01-31 | 2027/28 | Straight-line | 80% | 125 | 100 | 25 | 0 | 125 | 100 | 25
WP1_PANEL-202802 | WP1_PANEL | RUSI - hybrid panels and practitioner roundtables | WP1 | Directly Incurred | Other Directly Incurred | Panels & Roundtables | 2028-02-29 | 2027/28 | Straight-line | 80% | 125 | 100 | 25 | 0 | 125 | 100 | 25
WP1_PANEL-202803 | WP1_PANEL | RUSI - hybrid panels and practitioner roundtables | WP1 | Directly Incurred | Other Directly Incurred | Panels & Roundtables | 2028-03-31 | 2027/28 | Straight-line | 80% | 125 | 100 | 25 | 0 | 125 | 100 | 25
WP1_PANEL-202804 | WP1_PANEL | RUSI - hybrid panels and practitioner roundtables | WP1 | Directly Incurred | Other Directly Incurred | Panels & Roundtables | 2028-04-30 | 2028/29 | Straight-line | 80% | 125 | 100 | 25 | 0 | 125 | 100 | 25
WP1_PANEL-202805 | WP1_PANEL | RUSI - hybrid panels and practitioner roundtables | WP1 | Directly Incurred | Other Directly Incurred | Panels & Roundtables | 2028-05-31 | 2028/29 | Straight-line | 80% | 125 | 100 | 25 | 0 | 125 | 100 | 25
WP1_PANEL-202806 | WP1_PANEL | RUSI - hybrid panels and practitioner roundtables | WP1 | Directly Incurred | Other Directly Incurred | Panels & Roundtables | 2028-06-30 | 2028/29 | Straight-line | 80% | 125 | 100 | 25 | 0 | 125 | 100 | 25
WP1_PANEL-202807 | WP1_PANEL | RUSI - hybrid panels and practitioner roundtables | WP1 | Directly Incurred | Other Directly Incurred | Panels & Roundtables | 2028-07-31 | 2028/29 | Straight-line | 80% | 125 | 100 | 25 | 0 | 125 | 100 | 25
WP1_PANEL-202808 | WP1_PANEL | RUSI - hybrid panels and practitioner roundtables | WP1 | Directly Incurred | Other Directly Incurred | Panels & Roundtables | 2028-08-31 | 2028/29 | Straight-line | 80% | 125 | 100 | 25 | 0 | 125 | 100 | 25
WP1_PANEL-202809 | WP1_PANEL | RUSI - hybrid panels and practitioner roundtables | WP1 | Directly Incurred | Other Directly Incurred | Panels & Roundtables | 2028-09-30 | 2028/29 | Straight-line | 80% | 125 | 100 | 25 | 0 | 125 | 100 | 25
WP1_PANEL-202810 | WP1_PANEL | RUSI - hybrid panels and practitioner roundtables | WP1 | Directly Incurred | Other Directly Incurred | Panels & Roundtables | 2028-10-31 | 2028/29 | Straight-line | 80% | 125 | 100 | 25 | 0 | 125 | 100 | 25
WP1_PANEL-202811 | WP1_PANEL | RUSI - hybrid panels and practitioner roundtables | WP1 | Directly Incurred | Other Directly Incurred | Panels & Roundtables | 2028-11-30 | 2028/29 | Straight-line | 80% | 125 | 100 | 25 | 0 | 125 | 100 | 25
WP1_PANEL-202812 | WP1_PANEL | RUSI - hybrid panels and practitioner roundtables | WP1 | Directly Incurred | Other Directly Incurred | Panels & Roundtables | 2028-12-31 | 2028/29 | Straight-line | 80% | 125 | 100 | 25 | 0 | 125 | 100 | 25
WP1_PANEL-202901 | WP1_PANEL | RUSI - hybrid panels and practitioner roundtables | WP1 | Directly Incurred | Other Directly Incurred | Panels & Roundtables | 2029-01-31 | 2028/29 | Straight-line | 80% | 125 | 100 | 25 | 0 | 125 | 100 | 25
WP1_PANEL-202902 | WP1_PANEL | RUSI - hybrid panels and practitioner roundtables | WP1 | Directly Incurred | Other Directly Incurred | Panels & Roundtables | 2029-02-28 | 2028/29 | Straight-line | 80% | 125 | 100 | 25 | 0 | 125 | 100 | 25
WP1_PANEL-202903 | WP1_PANEL | RUSI - hybrid panels and practitioner roundtables | WP1 | Directly Incurred | Other Directly Incurred | Panels & Roundtables | 2029-03-31 | 2028/29 | Straight-line | 80% | 125 | 100 | 25 | 0 | 125 | 100 | 25
WP1_COMMS-202604 | WP1_COMMS | RUSI - knowledge products and digital communications | WP1 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | 2026-04-30 | 2026/27 | Straight-line | 80% | 83.3333 | 66.6667 | 16.6667 | 0 | 83.3333 | 66.6667 | 16.6667
WP1_COMMS-202605 | WP1_COMMS | RUSI - knowledge products and digital communications | WP1 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | 2026-05-31 | 2026/27 | Straight-line | 80% | 83.3333 | 66.6667 | 16.6667 | 0 | 83.3333 | 66.6667 | 16.6667
WP1_COMMS-202606 | WP1_COMMS | RUSI - knowledge products and digital communications | WP1 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | 2026-06-30 | 2026/27 | Straight-line | 80% | 83.3333 | 66.6667 | 16.6667 | 0 | 83.3333 | 66.6667 | 16.6667
WP1_COMMS-202607 | WP1_COMMS | RUSI - knowledge products and digital communications | WP1 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | 2026-07-31 | 2026/27 | Straight-line | 80% | 83.3333 | 66.6667 | 16.6667 | 0 | 83.3333 | 66.6667 | 16.6667
WP1_COMMS-202608 | WP1_COMMS | RUSI - knowledge products and digital communications | WP1 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | 2026-08-31 | 2026/27 | Straight-line | 80% | 83.3333 | 66.6667 | 16.6667 | 0 | 83.3333 | 66.6667 | 16.6667
WP1_COMMS-202609 | WP1_COMMS | RUSI - knowledge products and digital communications | WP1 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | 2026-09-30 | 2026/27 | Straight-line | 80% | 83.3333 | 66.6667 | 16.6667 | 0 | 83.3333 | 66.6667 | 16.6667
WP1_COMMS-202610 | WP1_COMMS | RUSI - knowledge products and digital communications | WP1 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | 2026-10-31 | 2026/27 | Straight-line | 80% | 83.3333 | 66.6667 | 16.6667 | 0 | 83.3333 | 66.6667 | 16.6667
WP1_COMMS-202611 | WP1_COMMS | RUSI - knowledge products and digital communications | WP1 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | 2026-11-30 | 2026/27 | Straight-line | 80% | 83.3333 | 66.6667 | 16.6667 | 0 | 83.3333 | 66.6667 | 16.6667
WP1_COMMS-202612 | WP1_COMMS | RUSI - knowledge products and digital communications | WP1 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | 2026-12-31 | 2026/27 | Straight-line | 80% | 83.3333 | 66.6667 | 16.6667 | 0 | 83.3333 | 66.6667 | 16.6667
WP1_COMMS-202701 | WP1_COMMS | RUSI - knowledge products and digital communications | WP1 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | 2027-01-31 | 2026/27 | Straight-line | 80% | 83.3333 | 66.6667 | 16.6667 | 0 | 83.3333 | 66.6667 | 16.6667
WP1_COMMS-202702 | WP1_COMMS | RUSI - knowledge products and digital communications | WP1 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | 2027-02-28 | 2026/27 | Straight-line | 80% | 83.3333 | 66.6667 | 16.6667 | 0 | 83.3333 | 66.6667 | 16.6667
WP1_COMMS-202703 | WP1_COMMS | RUSI - knowledge products and digital communications | WP1 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | 2027-03-31 | 2026/27 | Straight-line | 80% | 83.3333 | 66.6667 | 16.6667 | 0 | 83.3333 | 66.6667 | 16.6667
WP1_COMMS-202704 | WP1_COMMS | RUSI - knowledge products and digital communications | WP1 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | 2027-04-30 | 2027/28 | Straight-line | 80% | 83.3333 | 66.6667 | 16.6667 | 0 | 83.3333 | 66.6667 | 16.6667
WP1_COMMS-202705 | WP1_COMMS | RUSI - knowledge products and digital communications | WP1 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | 2027-05-31 | 2027/28 | Straight-line | 80% | 83.3333 | 66.6667 | 16.6667 | 0 | 83.3333 | 66.6667 | 16.6667
WP1_COMMS-202706 | WP1_COMMS | RUSI - knowledge products and digital communications | WP1 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | 2027-06-30 | 2027/28 | Straight-line | 80% | 83.3333 | 66.6667 | 16.6667 | 0 | 83.3333 | 66.6667 | 16.6667
WP1_COMMS-202707 | WP1_COMMS | RUSI - knowledge products and digital communications | WP1 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | 2027-07-31 | 2027/28 | Straight-line | 80% | 83.3333 | 66.6667 | 16.6667 | 0 | 83.3333 | 66.6667 | 16.6667
WP1_COMMS-202708 | WP1_COMMS | RUSI - knowledge products and digital communications | WP1 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | 2027-08-31 | 2027/28 | Straight-line | 80% | 83.3333 | 66.6667 | 16.6667 | 0 | 83.3333 | 66.6667 | 16.6667
WP1_COMMS-202709 | WP1_COMMS | RUSI - knowledge products and digital communications | WP1 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | 2027-09-30 | 2027/28 | Straight-line | 80% | 83.3333 | 66.6667 | 16.6667 | 0 | 83.3333 | 66.6667 | 16.6667
WP1_COMMS-202710 | WP1_COMMS | RUSI - knowledge products and digital communications | WP1 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | 2027-10-31 | 2027/28 | Straight-line | 80% | 83.3333 | 66.6667 | 16.6667 | 0 | 83.3333 | 66.6667 | 16.6667
WP1_COMMS-202711 | WP1_COMMS | RUSI - knowledge products and digital communications | WP1 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | 2027-11-30 | 2027/28 | Straight-line | 80% | 83.3333 | 66.6667 | 16.6667 | 0 | 83.3333 | 66.6667 | 16.6667
WP1_COMMS-202712 | WP1_COMMS | RUSI - knowledge products and digital communications | WP1 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | 2027-12-31 | 2027/28 | Straight-line | 80% | 83.3333 | 66.6667 | 16.6667 | 0 | 83.3333 | 66.6667 | 16.6667
WP1_COMMS-202801 | WP1_COMMS | RUSI - knowledge products and digital communications | WP1 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | 2028-01-31 | 2027/28 | Straight-line | 80% | 83.3333 | 66.6667 | 16.6667 | 0 | 83.3333 | 66.6667 | 16.6667
WP1_COMMS-202802 | WP1_COMMS | RUSI - knowledge products and digital communications | WP1 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | 2028-02-29 | 2027/28 | Straight-line | 80% | 83.3333 | 66.6667 | 16.6667 | 0 | 83.3333 | 66.6667 | 16.6667
WP1_COMMS-202803 | WP1_COMMS | RUSI - knowledge products and digital communications | WP1 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | 2028-03-31 | 2027/28 | Straight-line | 80% | 83.3333 | 66.6667 | 16.6667 | 0 | 83.3333 | 66.6667 | 16.6667
WP1_COMMS-202804 | WP1_COMMS | RUSI - knowledge products and digital communications | WP1 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | 2028-04-30 | 2028/29 | Straight-line | 80% | 83.3333 | 66.6667 | 16.6667 | 0 | 83.3333 | 66.6667 | 16.6667
WP1_COMMS-202805 | WP1_COMMS | RUSI - knowledge products and digital communications | WP1 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | 2028-05-31 | 2028/29 | Straight-line | 80% | 83.3333 | 66.6667 | 16.6667 | 0 | 83.3333 | 66.6667 | 16.6667
WP1_COMMS-202806 | WP1_COMMS | RUSI - knowledge products and digital communications | WP1 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | 2028-06-30 | 2028/29 | Straight-line | 80% | 83.3333 | 66.6667 | 16.6667 | 0 | 83.3333 | 66.6667 | 16.6667
WP1_COMMS-202807 | WP1_COMMS | RUSI - knowledge products and digital communications | WP1 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | 2028-07-31 | 2028/29 | Straight-line | 80% | 83.3333 | 66.6667 | 16.6667 | 0 | 83.3333 | 66.6667 | 16.6667
WP1_COMMS-202808 | WP1_COMMS | RUSI - knowledge products and digital communications | WP1 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | 2028-08-31 | 2028/29 | Straight-line | 80% | 83.3333 | 66.6667 | 16.6667 | 0 | 83.3333 | 66.6667 | 16.6667
WP1_COMMS-202809 | WP1_COMMS | RUSI - knowledge products and digital communications | WP1 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | 2028-09-30 | 2028/29 | Straight-line | 80% | 83.3333 | 66.6667 | 16.6667 | 0 | 83.3333 | 66.6667 | 16.6667
WP1_COMMS-202810 | WP1_COMMS | RUSI - knowledge products and digital communications | WP1 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | 2028-10-31 | 2028/29 | Straight-line | 80% | 83.3333 | 66.6667 | 16.6667 | 0 | 83.3333 | 66.6667 | 16.6667
WP1_COMMS-202811 | WP1_COMMS | RUSI - knowledge products and digital communications | WP1 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | 2028-11-30 | 2028/29 | Straight-line | 80% | 83.3333 | 66.6667 | 16.6667 | 0 | 83.3333 | 66.6667 | 16.6667
WP1_COMMS-202812 | WP1_COMMS | RUSI - knowledge products and digital communications | WP1 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | 2028-12-31 | 2028/29 | Straight-line | 80% | 83.3333 | 66.6667 | 16.6667 | 0 | 83.3333 | 66.6667 | 16.6667
WP1_COMMS-202901 | WP1_COMMS | RUSI - knowledge products and digital communications | WP1 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | 2029-01-31 | 2028/29 | Straight-line | 80% | 83.3333 | 66.6667 | 16.6667 | 0 | 83.3333 | 66.6667 | 16.6667
WP1_COMMS-202902 | WP1_COMMS | RUSI - knowledge products and digital communications | WP1 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | 2029-02-28 | 2028/29 | Straight-line | 80% | 83.3333 | 66.6667 | 16.6667 | 0 | 83.3333 | 66.6667 | 16.6667
WP1_COMMS-202903 | WP1_COMMS | RUSI - knowledge products and digital communications | WP1 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | 2029-03-31 | 2028/29 | Straight-line | 80% | 83.3333 | 66.6667 | 16.6667 | 0 | 83.3333 | 66.6667 | 16.6667
WP1_IND-202604 | WP1_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP1 | Indirect | Indirect | Indirect Costs | 2026-04-30 | 2026/27 | Straight-line | 80% | 1197.9792 | 958.3833 | 239.5958 | 0 | 1197.9792 | 958.3833 | 239.5958
WP1_IND-202605 | WP1_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP1 | Indirect | Indirect | Indirect Costs | 2026-05-31 | 2026/27 | Straight-line | 80% | 1197.9792 | 958.3833 | 239.5958 | 0 | 1197.9792 | 958.3833 | 239.5958
WP1_IND-202606 | WP1_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP1 | Indirect | Indirect | Indirect Costs | 2026-06-30 | 2026/27 | Straight-line | 80% | 1197.9792 | 958.3833 | 239.5958 | 0 | 1197.9792 | 958.3833 | 239.5958
WP1_IND-202607 | WP1_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP1 | Indirect | Indirect | Indirect Costs | 2026-07-31 | 2026/27 | Straight-line | 80% | 1197.9792 | 958.3833 | 239.5958 | 0 | 1197.9792 | 958.3833 | 239.5958
WP1_IND-202608 | WP1_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP1 | Indirect | Indirect | Indirect Costs | 2026-08-31 | 2026/27 | Straight-line | 80% | 1197.9792 | 958.3833 | 239.5958 | 0 | 1197.9792 | 958.3833 | 239.5958
WP1_IND-202609 | WP1_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP1 | Indirect | Indirect | Indirect Costs | 2026-09-30 | 2026/27 | Straight-line | 80% | 1197.9792 | 958.3833 | 239.5958 | 0 | 1197.9792 | 958.3833 | 239.5958
WP1_IND-202610 | WP1_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP1 | Indirect | Indirect | Indirect Costs | 2026-10-31 | 2026/27 | Straight-line | 80% | 1197.9792 | 958.3833 | 239.5958 | 0 | 1197.9792 | 958.3833 | 239.5958
WP1_IND-202611 | WP1_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP1 | Indirect | Indirect | Indirect Costs | 2026-11-30 | 2026/27 | Straight-line | 80% | 1197.9792 | 958.3833 | 239.5958 | 0 | 1197.9792 | 958.3833 | 239.5958
WP1_IND-202612 | WP1_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP1 | Indirect | Indirect | Indirect Costs | 2026-12-31 | 2026/27 | Straight-line | 80% | 1197.9792 | 958.3833 | 239.5958 | 0 | 1197.9792 | 958.3833 | 239.5958
WP1_IND-202701 | WP1_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP1 | Indirect | Indirect | Indirect Costs | 2027-01-31 | 2026/27 | Straight-line | 80% | 1197.9792 | 958.3833 | 239.5958 | 0 | 1197.9792 | 958.3833 | 239.5958
WP1_IND-202702 | WP1_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP1 | Indirect | Indirect | Indirect Costs | 2027-02-28 | 2026/27 | Straight-line | 80% | 1197.9792 | 958.3833 | 239.5958 | 0 | 1197.9792 | 958.3833 | 239.5958
WP1_IND-202703 | WP1_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP1 | Indirect | Indirect | Indirect Costs | 2027-03-31 | 2026/27 | Straight-line | 80% | 1197.9792 | 958.3833 | 239.5958 | 0 | 1197.9792 | 958.3833 | 239.5958
WP1_IND-202704 | WP1_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP1 | Indirect | Indirect | Indirect Costs | 2027-04-30 | 2027/28 | Straight-line | 80% | 1389.6558 | 1111.7247 | 277.9312 | 0 | 1389.6558 | 1111.7247 | 277.9312
WP1_IND-202705 | WP1_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP1 | Indirect | Indirect | Indirect Costs | 2027-05-31 | 2027/28 | Straight-line | 80% | 1389.6558 | 1111.7247 | 277.9312 | 0 | 1389.6558 | 1111.7247 | 277.9312
WP1_IND-202706 | WP1_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP1 | Indirect | Indirect | Indirect Costs | 2027-06-30 | 2027/28 | Straight-line | 80% | 1389.6558 | 1111.7247 | 277.9312 | 0 | 1389.6558 | 1111.7247 | 277.9312
WP1_IND-202707 | WP1_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP1 | Indirect | Indirect | Indirect Costs | 2027-07-31 | 2027/28 | Straight-line | 80% | 1389.6558 | 1111.7247 | 277.9312 | 0 | 1389.6558 | 1111.7247 | 277.9312
WP1_IND-202708 | WP1_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP1 | Indirect | Indirect | Indirect Costs | 2027-08-31 | 2027/28 | Straight-line | 80% | 1389.6558 | 1111.7247 | 277.9312 | 0 | 1389.6558 | 1111.7247 | 277.9312
WP1_IND-202709 | WP1_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP1 | Indirect | Indirect | Indirect Costs | 2027-09-30 | 2027/28 | Straight-line | 80% | 1389.6558 | 1111.7247 | 277.9312 | 0 | 1389.6558 | 1111.7247 | 277.9312
WP1_IND-202710 | WP1_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP1 | Indirect | Indirect | Indirect Costs | 2027-10-31 | 2027/28 | Straight-line | 80% | 1389.6558 | 1111.7247 | 277.9312 | 0 | 1389.6558 | 1111.7247 | 277.9312
WP1_IND-202711 | WP1_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP1 | Indirect | Indirect | Indirect Costs | 2027-11-30 | 2027/28 | Straight-line | 80% | 1389.6558 | 1111.7247 | 277.9312 | 0 | 1389.6558 | 1111.7247 | 277.9312
WP1_IND-202712 | WP1_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP1 | Indirect | Indirect | Indirect Costs | 2027-12-31 | 2027/28 | Straight-line | 80% | 1389.6558 | 1111.7247 | 277.9312 | 0 | 1389.6558 | 1111.7247 | 277.9312
WP1_IND-202801 | WP1_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP1 | Indirect | Indirect | Indirect Costs | 2028-01-31 | 2027/28 | Straight-line | 80% | 1389.6558 | 1111.7247 | 277.9312 | 0 | 1389.6558 | 1111.7247 | 277.9312
WP1_IND-202802 | WP1_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP1 | Indirect | Indirect | Indirect Costs | 2028-02-29 | 2027/28 | Straight-line | 80% | 1389.6558 | 1111.7247 | 277.9312 | 0 | 1389.6558 | 1111.7247 | 277.9312
WP1_IND-202803 | WP1_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP1 | Indirect | Indirect | Indirect Costs | 2028-03-31 | 2027/28 | Straight-line | 80% | 1389.6558 | 1111.7247 | 277.9312 | 0 | 1389.6558 | 1111.7247 | 277.9312
WP1_IND-202804 | WP1_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP1 | Indirect | Indirect | Indirect Costs | 2028-04-30 | 2028/29 | Straight-line | 80% | 1389.6558 | 1111.7247 | 277.9312 | 0 | 1389.6558 | 1111.7247 | 277.9312
WP1_IND-202805 | WP1_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP1 | Indirect | Indirect | Indirect Costs | 2028-05-31 | 2028/29 | Straight-line | 80% | 1389.6558 | 1111.7247 | 277.9312 | 0 | 1389.6558 | 1111.7247 | 277.9312
WP1_IND-202806 | WP1_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP1 | Indirect | Indirect | Indirect Costs | 2028-06-30 | 2028/29 | Straight-line | 80% | 1389.6558 | 1111.7247 | 277.9312 | 0 | 1389.6558 | 1111.7247 | 277.9312
WP1_IND-202807 | WP1_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP1 | Indirect | Indirect | Indirect Costs | 2028-07-31 | 2028/29 | Straight-line | 80% | 1389.6558 | 1111.7247 | 277.9312 | 0 | 1389.6558 | 1111.7247 | 277.9312
WP1_IND-202808 | WP1_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP1 | Indirect | Indirect | Indirect Costs | 2028-08-31 | 2028/29 | Straight-line | 80% | 1389.6558 | 1111.7247 | 277.9312 | 0 | 1389.6558 | 1111.7247 | 277.9312
WP1_IND-202809 | WP1_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP1 | Indirect | Indirect | Indirect Costs | 2028-09-30 | 2028/29 | Straight-line | 80% | 1389.6558 | 1111.7247 | 277.9312 | 0 | 1389.6558 | 1111.7247 | 277.9312
WP1_IND-202810 | WP1_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP1 | Indirect | Indirect | Indirect Costs | 2028-10-31 | 2028/29 | Straight-line | 80% | 1389.6558 | 1111.7247 | 277.9312 | 0 | 1389.6558 | 1111.7247 | 277.9312
WP1_IND-202811 | WP1_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP1 | Indirect | Indirect | Indirect Costs | 2028-11-30 | 2028/29 | Straight-line | 80% | 1389.6558 | 1111.7247 | 277.9312 | 0 | 1389.6558 | 1111.7247 | 277.9312
WP1_IND-202812 | WP1_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP1 | Indirect | Indirect | Indirect Costs | 2028-12-31 | 2028/29 | Straight-line | 80% | 1389.6558 | 1111.7247 | 277.9312 | 0 | 1389.6558 | 1111.7247 | 277.9312
WP1_IND-202901 | WP1_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP1 | Indirect | Indirect | Indirect Costs | 2029-01-31 | 2028/29 | Straight-line | 80% | 1389.6558 | 1111.7247 | 277.9312 | 0 | 1389.6558 | 1111.7247 | 277.9312
WP1_IND-202902 | WP1_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP1 | Indirect | Indirect | Indirect Costs | 2029-02-28 | 2028/29 | Straight-line | 80% | 1389.6558 | 1111.7247 | 277.9312 | 0 | 1389.6558 | 1111.7247 | 277.9312
WP1_IND-202903 | WP1_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP1 | Indirect | Indirect | Indirect Costs | 2029-03-31 | 2028/29 | Straight-line | 80% | 1389.6558 | 1111.7247 | 277.9312 | 0 | 1389.6558 | 1111.7247 | 277.9312
WP1_EST-202604 | WP1_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP1 | Directly Allocated | Estates | Estate Costs | 2026-04-30 | 2026/27 | Straight-line | 80% | 152.6667 | 122.1333 | 30.5333 | 0 | 152.6667 | 122.1333 | 30.5333
WP1_EST-202605 | WP1_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP1 | Directly Allocated | Estates | Estate Costs | 2026-05-31 | 2026/27 | Straight-line | 80% | 152.6667 | 122.1333 | 30.5333 | 0 | 152.6667 | 122.1333 | 30.5333
WP1_EST-202606 | WP1_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP1 | Directly Allocated | Estates | Estate Costs | 2026-06-30 | 2026/27 | Straight-line | 80% | 152.6667 | 122.1333 | 30.5333 | 0 | 152.6667 | 122.1333 | 30.5333
WP1_EST-202607 | WP1_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP1 | Directly Allocated | Estates | Estate Costs | 2026-07-31 | 2026/27 | Straight-line | 80% | 152.6667 | 122.1333 | 30.5333 | 0 | 152.6667 | 122.1333 | 30.5333
WP1_EST-202608 | WP1_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP1 | Directly Allocated | Estates | Estate Costs | 2026-08-31 | 2026/27 | Straight-line | 80% | 152.6667 | 122.1333 | 30.5333 | 0 | 152.6667 | 122.1333 | 30.5333
WP1_EST-202609 | WP1_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP1 | Directly Allocated | Estates | Estate Costs | 2026-09-30 | 2026/27 | Straight-line | 80% | 152.6667 | 122.1333 | 30.5333 | 0 | 152.6667 | 122.1333 | 30.5333
WP1_EST-202610 | WP1_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP1 | Directly Allocated | Estates | Estate Costs | 2026-10-31 | 2026/27 | Straight-line | 80% | 152.6667 | 122.1333 | 30.5333 | 0 | 152.6667 | 122.1333 | 30.5333
WP1_EST-202611 | WP1_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP1 | Directly Allocated | Estates | Estate Costs | 2026-11-30 | 2026/27 | Straight-line | 80% | 152.6667 | 122.1333 | 30.5333 | 0 | 152.6667 | 122.1333 | 30.5333
WP1_EST-202612 | WP1_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP1 | Directly Allocated | Estates | Estate Costs | 2026-12-31 | 2026/27 | Straight-line | 80% | 152.6667 | 122.1333 | 30.5333 | 0 | 152.6667 | 122.1333 | 30.5333
WP1_EST-202701 | WP1_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP1 | Directly Allocated | Estates | Estate Costs | 2027-01-31 | 2026/27 | Straight-line | 80% | 152.6667 | 122.1333 | 30.5333 | 0 | 152.6667 | 122.1333 | 30.5333
WP1_EST-202702 | WP1_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP1 | Directly Allocated | Estates | Estate Costs | 2027-02-28 | 2026/27 | Straight-line | 80% | 152.6667 | 122.1333 | 30.5333 | 0 | 152.6667 | 122.1333 | 30.5333
WP1_EST-202703 | WP1_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP1 | Directly Allocated | Estates | Estate Costs | 2027-03-31 | 2026/27 | Straight-line | 80% | 152.6667 | 122.1333 | 30.5333 | 0 | 152.6667 | 122.1333 | 30.5333
WP1_EST-202704 | WP1_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP1 | Directly Allocated | Estates | Estate Costs | 2027-04-30 | 2027/28 | Straight-line | 80% | 177.0933 | 141.6747 | 35.4187 | 0 | 177.0933 | 141.6747 | 35.4187
WP1_EST-202705 | WP1_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP1 | Directly Allocated | Estates | Estate Costs | 2027-05-31 | 2027/28 | Straight-line | 80% | 177.0933 | 141.6747 | 35.4187 | 0 | 177.0933 | 141.6747 | 35.4187
WP1_EST-202706 | WP1_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP1 | Directly Allocated | Estates | Estate Costs | 2027-06-30 | 2027/28 | Straight-line | 80% | 177.0933 | 141.6747 | 35.4187 | 0 | 177.0933 | 141.6747 | 35.4187
WP1_EST-202707 | WP1_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP1 | Directly Allocated | Estates | Estate Costs | 2027-07-31 | 2027/28 | Straight-line | 80% | 177.0933 | 141.6747 | 35.4187 | 0 | 177.0933 | 141.6747 | 35.4187
WP1_EST-202708 | WP1_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP1 | Directly Allocated | Estates | Estate Costs | 2027-08-31 | 2027/28 | Straight-line | 80% | 177.0933 | 141.6747 | 35.4187 | 0 | 177.0933 | 141.6747 | 35.4187
WP1_EST-202709 | WP1_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP1 | Directly Allocated | Estates | Estate Costs | 2027-09-30 | 2027/28 | Straight-line | 80% | 177.0933 | 141.6747 | 35.4187 | 0 | 177.0933 | 141.6747 | 35.4187
WP1_EST-202710 | WP1_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP1 | Directly Allocated | Estates | Estate Costs | 2027-10-31 | 2027/28 | Straight-line | 80% | 177.0933 | 141.6747 | 35.4187 | 0 | 177.0933 | 141.6747 | 35.4187
WP1_EST-202711 | WP1_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP1 | Directly Allocated | Estates | Estate Costs | 2027-11-30 | 2027/28 | Straight-line | 80% | 177.0933 | 141.6747 | 35.4187 | 0 | 177.0933 | 141.6747 | 35.4187
WP1_EST-202712 | WP1_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP1 | Directly Allocated | Estates | Estate Costs | 2027-12-31 | 2027/28 | Straight-line | 80% | 177.0933 | 141.6747 | 35.4187 | 0 | 177.0933 | 141.6747 | 35.4187
WP1_EST-202801 | WP1_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP1 | Directly Allocated | Estates | Estate Costs | 2028-01-31 | 2027/28 | Straight-line | 80% | 177.0933 | 141.6747 | 35.4187 | 0 | 177.0933 | 141.6747 | 35.4187
WP1_EST-202802 | WP1_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP1 | Directly Allocated | Estates | Estate Costs | 2028-02-29 | 2027/28 | Straight-line | 80% | 177.0933 | 141.6747 | 35.4187 | 0 | 177.0933 | 141.6747 | 35.4187
WP1_EST-202803 | WP1_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP1 | Directly Allocated | Estates | Estate Costs | 2028-03-31 | 2027/28 | Straight-line | 80% | 177.0933 | 141.6747 | 35.4187 | 0 | 177.0933 | 141.6747 | 35.4187
WP1_EST-202804 | WP1_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP1 | Directly Allocated | Estates | Estate Costs | 2028-04-30 | 2028/29 | Straight-line | 80% | 177.0933 | 141.6747 | 35.4187 | 0 | 177.0933 | 141.6747 | 35.4187
WP1_EST-202805 | WP1_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP1 | Directly Allocated | Estates | Estate Costs | 2028-05-31 | 2028/29 | Straight-line | 80% | 177.0933 | 141.6747 | 35.4187 | 0 | 177.0933 | 141.6747 | 35.4187
WP1_EST-202806 | WP1_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP1 | Directly Allocated | Estates | Estate Costs | 2028-06-30 | 2028/29 | Straight-line | 80% | 177.0933 | 141.6747 | 35.4187 | 0 | 177.0933 | 141.6747 | 35.4187
WP1_EST-202807 | WP1_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP1 | Directly Allocated | Estates | Estate Costs | 2028-07-31 | 2028/29 | Straight-line | 80% | 177.0933 | 141.6747 | 35.4187 | 0 | 177.0933 | 141.6747 | 35.4187
WP1_EST-202808 | WP1_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP1 | Directly Allocated | Estates | Estate Costs | 2028-08-31 | 2028/29 | Straight-line | 80% | 177.0933 | 141.6747 | 35.4187 | 0 | 177.0933 | 141.6747 | 35.4187
WP1_EST-202809 | WP1_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP1 | Directly Allocated | Estates | Estate Costs | 2028-09-30 | 2028/29 | Straight-line | 80% | 177.0933 | 141.6747 | 35.4187 | 0 | 177.0933 | 141.6747 | 35.4187
WP1_EST-202810 | WP1_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP1 | Directly Allocated | Estates | Estate Costs | 2028-10-31 | 2028/29 | Straight-line | 80% | 177.0933 | 141.6747 | 35.4187 | 0 | 177.0933 | 141.6747 | 35.4187
WP1_EST-202811 | WP1_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP1 | Directly Allocated | Estates | Estate Costs | 2028-11-30 | 2028/29 | Straight-line | 80% | 177.0933 | 141.6747 | 35.4187 | 0 | 177.0933 | 141.6747 | 35.4187
WP1_EST-202812 | WP1_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP1 | Directly Allocated | Estates | Estate Costs | 2028-12-31 | 2028/29 | Straight-line | 80% | 177.0933 | 141.6747 | 35.4187 | 0 | 177.0933 | 141.6747 | 35.4187
WP1_EST-202901 | WP1_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP1 | Directly Allocated | Estates | Estate Costs | 2029-01-31 | 2028/29 | Straight-line | 80% | 177.0933 | 141.6747 | 35.4187 | 0 | 177.0933 | 141.6747 | 35.4187
WP1_EST-202902 | WP1_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP1 | Directly Allocated | Estates | Estate Costs | 2029-02-28 | 2028/29 | Straight-line | 80% | 177.0933 | 141.6747 | 35.4187 | 0 | 177.0933 | 141.6747 | 35.4187
WP1_EST-202903 | WP1_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP1 | Directly Allocated | Estates | Estate Costs | 2029-03-31 | 2028/29 | Straight-line | 80% | 177.0933 | 141.6747 | 35.4187 | 0 | 177.0933 | 141.6747 | 35.4187
WP2_S01-202604 | WP2_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | 2026-04-30 | 2026/27 | Straight-line | 80% | 98.125 | 78.5 | 19.625 | 0 | 98.125 | 78.5 | 19.625
WP2_S01-202605 | WP2_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | 2026-05-31 | 2026/27 | Straight-line | 80% | 98.125 | 78.5 | 19.625 | 0 | 98.125 | 78.5 | 19.625
WP2_S01-202606 | WP2_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | 2026-06-30 | 2026/27 | Straight-line | 80% | 98.125 | 78.5 | 19.625 | 0 | 98.125 | 78.5 | 19.625
WP2_S01-202607 | WP2_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | 2026-07-31 | 2026/27 | Straight-line | 80% | 98.125 | 78.5 | 19.625 | 0 | 98.125 | 78.5 | 19.625
WP2_S01-202608 | WP2_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | 2026-08-31 | 2026/27 | Straight-line | 80% | 98.125 | 78.5 | 19.625 | 0 | 98.125 | 78.5 | 19.625
WP2_S01-202609 | WP2_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | 2026-09-30 | 2026/27 | Straight-line | 80% | 98.125 | 78.5 | 19.625 | 0 | 98.125 | 78.5 | 19.625
WP2_S01-202610 | WP2_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | 2026-10-31 | 2026/27 | Straight-line | 80% | 98.125 | 78.5 | 19.625 | 0 | 98.125 | 78.5 | 19.625
WP2_S01-202611 | WP2_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | 2026-11-30 | 2026/27 | Straight-line | 80% | 98.125 | 78.5 | 19.625 | 0 | 98.125 | 78.5 | 19.625
WP2_S01-202612 | WP2_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | 2026-12-31 | 2026/27 | Straight-line | 80% | 98.125 | 78.5 | 19.625 | 0 | 98.125 | 78.5 | 19.625
WP2_S01-202701 | WP2_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | 2027-01-31 | 2026/27 | Straight-line | 80% | 98.125 | 78.5 | 19.625 | 0 | 98.125 | 78.5 | 19.625
WP2_S01-202702 | WP2_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | 2027-02-28 | 2026/27 | Straight-line | 80% | 98.125 | 78.5 | 19.625 | 0 | 98.125 | 78.5 | 19.625
WP2_S01-202703 | WP2_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | 2027-03-31 | 2026/27 | Straight-line | 80% | 98.125 | 78.5 | 19.625 | 0 | 98.125 | 78.5 | 19.625
WP2_S01-202704 | WP2_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | 2027-04-30 | 2027/28 | Straight-line | 80% | 98.125 | 78.5 | 19.625 | 0 | 98.125 | 78.5 | 19.625
WP2_S01-202705 | WP2_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | 2027-05-31 | 2027/28 | Straight-line | 80% | 98.125 | 78.5 | 19.625 | 0 | 98.125 | 78.5 | 19.625
WP2_S01-202706 | WP2_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | 2027-06-30 | 2027/28 | Straight-line | 80% | 98.125 | 78.5 | 19.625 | 0 | 98.125 | 78.5 | 19.625
WP2_S01-202707 | WP2_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | 2027-07-31 | 2027/28 | Straight-line | 80% | 98.125 | 78.5 | 19.625 | 0 | 98.125 | 78.5 | 19.625
WP2_S01-202708 | WP2_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | 2027-08-31 | 2027/28 | Straight-line | 80% | 98.125 | 78.5 | 19.625 | 0 | 98.125 | 78.5 | 19.625
WP2_S01-202709 | WP2_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | 2027-09-30 | 2027/28 | Straight-line | 80% | 98.125 | 78.5 | 19.625 | 0 | 98.125 | 78.5 | 19.625
WP2_S01-202710 | WP2_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | 2027-10-31 | 2027/28 | Straight-line | 80% | 98.125 | 78.5 | 19.625 | 0 | 98.125 | 78.5 | 19.625
WP2_S01-202711 | WP2_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | 2027-11-30 | 2027/28 | Straight-line | 80% | 98.125 | 78.5 | 19.625 | 0 | 98.125 | 78.5 | 19.625
WP2_S01-202712 | WP2_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | 2027-12-31 | 2027/28 | Straight-line | 80% | 98.125 | 78.5 | 19.625 | 0 | 98.125 | 78.5 | 19.625
WP2_S01-202801 | WP2_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | 2028-01-31 | 2027/28 | Straight-line | 80% | 98.125 | 78.5 | 19.625 | 0 | 98.125 | 78.5 | 19.625
WP2_S01-202802 | WP2_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | 2028-02-29 | 2027/28 | Straight-line | 80% | 98.125 | 78.5 | 19.625 | 0 | 98.125 | 78.5 | 19.625
WP2_S01-202803 | WP2_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | 2028-03-31 | 2027/28 | Straight-line | 80% | 98.125 | 78.5 | 19.625 | 0 | 98.125 | 78.5 | 19.625
WP2_S01-202804 | WP2_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | 2028-04-30 | 2028/29 | Straight-line | 80% | 98.125 | 78.5 | 19.625 | 0 | 98.125 | 78.5 | 19.625
WP2_S01-202805 | WP2_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | 2028-05-31 | 2028/29 | Straight-line | 80% | 98.125 | 78.5 | 19.625 | 0 | 98.125 | 78.5 | 19.625
WP2_S01-202806 | WP2_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | 2028-06-30 | 2028/29 | Straight-line | 80% | 98.125 | 78.5 | 19.625 | 0 | 98.125 | 78.5 | 19.625
WP2_S01-202807 | WP2_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | 2028-07-31 | 2028/29 | Straight-line | 80% | 98.125 | 78.5 | 19.625 | 0 | 98.125 | 78.5 | 19.625
WP2_S01-202808 | WP2_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | 2028-08-31 | 2028/29 | Straight-line | 80% | 98.125 | 78.5 | 19.625 | 0 | 98.125 | 78.5 | 19.625
WP2_S01-202809 | WP2_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | 2028-09-30 | 2028/29 | Straight-line | 80% | 98.125 | 78.5 | 19.625 | 0 | 98.125 | 78.5 | 19.625
WP2_S01-202810 | WP2_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | 2028-10-31 | 2028/29 | Straight-line | 80% | 98.125 | 78.5 | 19.625 | 0 | 98.125 | 78.5 | 19.625
WP2_S01-202811 | WP2_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | 2028-11-30 | 2028/29 | Straight-line | 80% | 98.125 | 78.5 | 19.625 | 0 | 98.125 | 78.5 | 19.625
WP2_S01-202812 | WP2_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | 2028-12-31 | 2028/29 | Straight-line | 80% | 98.125 | 78.5 | 19.625 | 0 | 98.125 | 78.5 | 19.625
WP2_S01-202901 | WP2_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | 2029-01-31 | 2028/29 | Straight-line | 80% | 98.125 | 78.5 | 19.625 | 0 | 98.125 | 78.5 | 19.625
WP2_S01-202902 | WP2_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | 2029-02-28 | 2028/29 | Straight-line | 80% | 98.125 | 78.5 | 19.625 | 0 | 98.125 | 78.5 | 19.625
WP2_S01-202903 | WP2_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | 2029-03-31 | 2028/29 | Straight-line | 80% | 98.125 | 78.5 | 19.625 | 0 | 98.125 | 78.5 | 19.625
WP2_S02-202604 | WP2_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | 2026-04-30 | 2026/27 | Straight-line | 80% | 120.625 | 96.5 | 24.125 | 0 | 120.625 | 96.5 | 24.125
WP2_S02-202605 | WP2_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | 2026-05-31 | 2026/27 | Straight-line | 80% | 120.625 | 96.5 | 24.125 | 0 | 120.625 | 96.5 | 24.125
WP2_S02-202606 | WP2_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | 2026-06-30 | 2026/27 | Straight-line | 80% | 120.625 | 96.5 | 24.125 | 0 | 120.625 | 96.5 | 24.125
WP2_S02-202607 | WP2_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | 2026-07-31 | 2026/27 | Straight-line | 80% | 120.625 | 96.5 | 24.125 | 0 | 120.625 | 96.5 | 24.125
WP2_S02-202608 | WP2_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | 2026-08-31 | 2026/27 | Straight-line | 80% | 120.625 | 96.5 | 24.125 | 0 | 120.625 | 96.5 | 24.125
WP2_S02-202609 | WP2_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | 2026-09-30 | 2026/27 | Straight-line | 80% | 120.625 | 96.5 | 24.125 | 0 | 120.625 | 96.5 | 24.125
WP2_S02-202610 | WP2_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | 2026-10-31 | 2026/27 | Straight-line | 80% | 120.625 | 96.5 | 24.125 | 0 | 120.625 | 96.5 | 24.125
WP2_S02-202611 | WP2_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | 2026-11-30 | 2026/27 | Straight-line | 80% | 120.625 | 96.5 | 24.125 | 0 | 120.625 | 96.5 | 24.125
WP2_S02-202612 | WP2_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | 2026-12-31 | 2026/27 | Straight-line | 80% | 120.625 | 96.5 | 24.125 | 0 | 120.625 | 96.5 | 24.125
WP2_S02-202701 | WP2_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | 2027-01-31 | 2026/27 | Straight-line | 80% | 120.625 | 96.5 | 24.125 | 0 | 120.625 | 96.5 | 24.125
WP2_S02-202702 | WP2_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | 2027-02-28 | 2026/27 | Straight-line | 80% | 120.625 | 96.5 | 24.125 | 0 | 120.625 | 96.5 | 24.125
WP2_S02-202703 | WP2_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | 2027-03-31 | 2026/27 | Straight-line | 80% | 120.625 | 96.5 | 24.125 | 0 | 120.625 | 96.5 | 24.125
WP2_S02-202704 | WP2_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | 2027-04-30 | 2027/28 | Straight-line | 80% | 120.625 | 96.5 | 24.125 | 0 | 120.625 | 96.5 | 24.125
WP2_S02-202705 | WP2_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | 2027-05-31 | 2027/28 | Straight-line | 80% | 120.625 | 96.5 | 24.125 | 0 | 120.625 | 96.5 | 24.125
WP2_S02-202706 | WP2_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | 2027-06-30 | 2027/28 | Straight-line | 80% | 120.625 | 96.5 | 24.125 | 0 | 120.625 | 96.5 | 24.125
WP2_S02-202707 | WP2_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | 2027-07-31 | 2027/28 | Straight-line | 80% | 120.625 | 96.5 | 24.125 | 0 | 120.625 | 96.5 | 24.125
WP2_S02-202708 | WP2_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | 2027-08-31 | 2027/28 | Straight-line | 80% | 120.625 | 96.5 | 24.125 | 0 | 120.625 | 96.5 | 24.125
WP2_S02-202709 | WP2_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | 2027-09-30 | 2027/28 | Straight-line | 80% | 120.625 | 96.5 | 24.125 | 0 | 120.625 | 96.5 | 24.125
WP2_S02-202710 | WP2_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | 2027-10-31 | 2027/28 | Straight-line | 80% | 120.625 | 96.5 | 24.125 | 0 | 120.625 | 96.5 | 24.125
WP2_S02-202711 | WP2_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | 2027-11-30 | 2027/28 | Straight-line | 80% | 120.625 | 96.5 | 24.125 | 0 | 120.625 | 96.5 | 24.125
WP2_S02-202712 | WP2_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | 2027-12-31 | 2027/28 | Straight-line | 80% | 120.625 | 96.5 | 24.125 | 0 | 120.625 | 96.5 | 24.125
WP2_S02-202801 | WP2_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | 2028-01-31 | 2027/28 | Straight-line | 80% | 120.625 | 96.5 | 24.125 | 0 | 120.625 | 96.5 | 24.125
WP2_S02-202802 | WP2_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | 2028-02-29 | 2027/28 | Straight-line | 80% | 120.625 | 96.5 | 24.125 | 0 | 120.625 | 96.5 | 24.125
WP2_S02-202803 | WP2_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | 2028-03-31 | 2027/28 | Straight-line | 80% | 120.625 | 96.5 | 24.125 | 0 | 120.625 | 96.5 | 24.125
WP2_S02-202804 | WP2_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | 2028-04-30 | 2028/29 | Straight-line | 80% | 120.625 | 96.5 | 24.125 | 0 | 120.625 | 96.5 | 24.125
WP2_S02-202805 | WP2_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | 2028-05-31 | 2028/29 | Straight-line | 80% | 120.625 | 96.5 | 24.125 | 0 | 120.625 | 96.5 | 24.125
WP2_S02-202806 | WP2_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | 2028-06-30 | 2028/29 | Straight-line | 80% | 120.625 | 96.5 | 24.125 | 0 | 120.625 | 96.5 | 24.125
WP2_S02-202807 | WP2_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | 2028-07-31 | 2028/29 | Straight-line | 80% | 120.625 | 96.5 | 24.125 | 0 | 120.625 | 96.5 | 24.125
WP2_S02-202808 | WP2_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | 2028-08-31 | 2028/29 | Straight-line | 80% | 120.625 | 96.5 | 24.125 | 0 | 120.625 | 96.5 | 24.125
WP2_S02-202809 | WP2_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | 2028-09-30 | 2028/29 | Straight-line | 80% | 120.625 | 96.5 | 24.125 | 0 | 120.625 | 96.5 | 24.125
WP2_S02-202810 | WP2_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | 2028-10-31 | 2028/29 | Straight-line | 80% | 120.625 | 96.5 | 24.125 | 0 | 120.625 | 96.5 | 24.125
WP2_S02-202811 | WP2_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | 2028-11-30 | 2028/29 | Straight-line | 80% | 120.625 | 96.5 | 24.125 | 0 | 120.625 | 96.5 | 24.125
WP2_S02-202812 | WP2_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | 2028-12-31 | 2028/29 | Straight-line | 80% | 120.625 | 96.5 | 24.125 | 0 | 120.625 | 96.5 | 24.125
WP2_S02-202901 | WP2_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | 2029-01-31 | 2028/29 | Straight-line | 80% | 120.625 | 96.5 | 24.125 | 0 | 120.625 | 96.5 | 24.125
WP2_S02-202902 | WP2_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | 2029-02-28 | 2028/29 | Straight-line | 80% | 120.625 | 96.5 | 24.125 | 0 | 120.625 | 96.5 | 24.125
WP2_S02-202903 | WP2_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | 2029-03-31 | 2028/29 | Straight-line | 80% | 120.625 | 96.5 | 24.125 | 0 | 120.625 | 96.5 | 24.125
WP2_S03-202604 | WP2_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | 2026-04-30 | 2026/27 | Straight-line | 80% | 123.75 | 99 | 24.75 | 0 | 123.75 | 99 | 24.75
WP2_S03-202605 | WP2_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | 2026-05-31 | 2026/27 | Straight-line | 80% | 123.75 | 99 | 24.75 | 0 | 123.75 | 99 | 24.75
WP2_S03-202606 | WP2_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | 2026-06-30 | 2026/27 | Straight-line | 80% | 123.75 | 99 | 24.75 | 0 | 123.75 | 99 | 24.75
WP2_S03-202607 | WP2_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | 2026-07-31 | 2026/27 | Straight-line | 80% | 123.75 | 99 | 24.75 | 0 | 123.75 | 99 | 24.75
WP2_S03-202608 | WP2_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | 2026-08-31 | 2026/27 | Straight-line | 80% | 123.75 | 99 | 24.75 | 0 | 123.75 | 99 | 24.75
WP2_S03-202609 | WP2_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | 2026-09-30 | 2026/27 | Straight-line | 80% | 123.75 | 99 | 24.75 | 0 | 123.75 | 99 | 24.75
WP2_S03-202610 | WP2_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | 2026-10-31 | 2026/27 | Straight-line | 80% | 123.75 | 99 | 24.75 | 0 | 123.75 | 99 | 24.75
WP2_S03-202611 | WP2_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | 2026-11-30 | 2026/27 | Straight-line | 80% | 123.75 | 99 | 24.75 | 0 | 123.75 | 99 | 24.75
WP2_S03-202612 | WP2_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | 2026-12-31 | 2026/27 | Straight-line | 80% | 123.75 | 99 | 24.75 | 0 | 123.75 | 99 | 24.75
WP2_S03-202701 | WP2_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | 2027-01-31 | 2026/27 | Straight-line | 80% | 123.75 | 99 | 24.75 | 0 | 123.75 | 99 | 24.75
WP2_S03-202702 | WP2_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | 2027-02-28 | 2026/27 | Straight-line | 80% | 123.75 | 99 | 24.75 | 0 | 123.75 | 99 | 24.75
WP2_S03-202703 | WP2_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | 2027-03-31 | 2026/27 | Straight-line | 80% | 123.75 | 99 | 24.75 | 0 | 123.75 | 99 | 24.75
WP2_S03-202704 | WP2_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | 2027-04-30 | 2027/28 | Straight-line | 80% | 123.75 | 99 | 24.75 | 0 | 123.75 | 99 | 24.75
WP2_S03-202705 | WP2_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | 2027-05-31 | 2027/28 | Straight-line | 80% | 123.75 | 99 | 24.75 | 0 | 123.75 | 99 | 24.75
WP2_S03-202706 | WP2_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | 2027-06-30 | 2027/28 | Straight-line | 80% | 123.75 | 99 | 24.75 | 0 | 123.75 | 99 | 24.75
WP2_S03-202707 | WP2_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | 2027-07-31 | 2027/28 | Straight-line | 80% | 123.75 | 99 | 24.75 | 0 | 123.75 | 99 | 24.75
WP2_S03-202708 | WP2_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | 2027-08-31 | 2027/28 | Straight-line | 80% | 123.75 | 99 | 24.75 | 0 | 123.75 | 99 | 24.75
WP2_S03-202709 | WP2_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | 2027-09-30 | 2027/28 | Straight-line | 80% | 123.75 | 99 | 24.75 | 0 | 123.75 | 99 | 24.75
WP2_S03-202710 | WP2_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | 2027-10-31 | 2027/28 | Straight-line | 80% | 123.75 | 99 | 24.75 | 0 | 123.75 | 99 | 24.75
WP2_S03-202711 | WP2_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | 2027-11-30 | 2027/28 | Straight-line | 80% | 123.75 | 99 | 24.75 | 0 | 123.75 | 99 | 24.75
WP2_S03-202712 | WP2_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | 2027-12-31 | 2027/28 | Straight-line | 80% | 123.75 | 99 | 24.75 | 0 | 123.75 | 99 | 24.75
WP2_S03-202801 | WP2_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | 2028-01-31 | 2027/28 | Straight-line | 80% | 123.75 | 99 | 24.75 | 0 | 123.75 | 99 | 24.75
WP2_S03-202802 | WP2_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | 2028-02-29 | 2027/28 | Straight-line | 80% | 123.75 | 99 | 24.75 | 0 | 123.75 | 99 | 24.75
WP2_S03-202803 | WP2_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | 2028-03-31 | 2027/28 | Straight-line | 80% | 123.75 | 99 | 24.75 | 0 | 123.75 | 99 | 24.75
WP2_S03-202804 | WP2_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | 2028-04-30 | 2028/29 | Straight-line | 80% | 123.75 | 99 | 24.75 | 0 | 123.75 | 99 | 24.75
WP2_S03-202805 | WP2_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | 2028-05-31 | 2028/29 | Straight-line | 80% | 123.75 | 99 | 24.75 | 0 | 123.75 | 99 | 24.75
WP2_S03-202806 | WP2_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | 2028-06-30 | 2028/29 | Straight-line | 80% | 123.75 | 99 | 24.75 | 0 | 123.75 | 99 | 24.75
WP2_S03-202807 | WP2_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | 2028-07-31 | 2028/29 | Straight-line | 80% | 123.75 | 99 | 24.75 | 0 | 123.75 | 99 | 24.75
WP2_S03-202808 | WP2_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | 2028-08-31 | 2028/29 | Straight-line | 80% | 123.75 | 99 | 24.75 | 0 | 123.75 | 99 | 24.75
WP2_S03-202809 | WP2_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | 2028-09-30 | 2028/29 | Straight-line | 80% | 123.75 | 99 | 24.75 | 0 | 123.75 | 99 | 24.75
WP2_S03-202810 | WP2_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | 2028-10-31 | 2028/29 | Straight-line | 80% | 123.75 | 99 | 24.75 | 0 | 123.75 | 99 | 24.75
WP2_S03-202811 | WP2_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | 2028-11-30 | 2028/29 | Straight-line | 80% | 123.75 | 99 | 24.75 | 0 | 123.75 | 99 | 24.75
WP2_S03-202812 | WP2_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | 2028-12-31 | 2028/29 | Straight-line | 80% | 123.75 | 99 | 24.75 | 0 | 123.75 | 99 | 24.75
WP2_S03-202901 | WP2_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | 2029-01-31 | 2028/29 | Straight-line | 80% | 123.75 | 99 | 24.75 | 0 | 123.75 | 99 | 24.75
WP2_S03-202902 | WP2_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | 2029-02-28 | 2028/29 | Straight-line | 80% | 123.75 | 99 | 24.75 | 0 | 123.75 | 99 | 24.75
WP2_S03-202903 | WP2_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | 2029-03-31 | 2028/29 | Straight-line | 80% | 123.75 | 99 | 24.75 | 0 | 123.75 | 99 | 24.75
WP2_TRAVEL-202604 | WP2_TRAVEL | RUSI - London-team and East Africa stakeholder travel/subsistence | WP2 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | 2026-04-30 | 2026/27 | Straight-line | 80% | 333.3333 | 266.6667 | 66.6667 | 0 | 333.3333 | 266.6667 | 66.6667
WP2_TRAVEL-202605 | WP2_TRAVEL | RUSI - London-team and East Africa stakeholder travel/subsistence | WP2 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | 2026-05-31 | 2026/27 | Straight-line | 80% | 333.3333 | 266.6667 | 66.6667 | 0 | 333.3333 | 266.6667 | 66.6667
WP2_TRAVEL-202606 | WP2_TRAVEL | RUSI - London-team and East Africa stakeholder travel/subsistence | WP2 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | 2026-06-30 | 2026/27 | Straight-line | 80% | 333.3333 | 266.6667 | 66.6667 | 0 | 333.3333 | 266.6667 | 66.6667
WP2_TRAVEL-202607 | WP2_TRAVEL | RUSI - London-team and East Africa stakeholder travel/subsistence | WP2 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | 2026-07-31 | 2026/27 | Straight-line | 80% | 333.3333 | 266.6667 | 66.6667 | 0 | 333.3333 | 266.6667 | 66.6667
WP2_TRAVEL-202608 | WP2_TRAVEL | RUSI - London-team and East Africa stakeholder travel/subsistence | WP2 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | 2026-08-31 | 2026/27 | Straight-line | 80% | 333.3333 | 266.6667 | 66.6667 | 0 | 333.3333 | 266.6667 | 66.6667
WP2_TRAVEL-202609 | WP2_TRAVEL | RUSI - London-team and East Africa stakeholder travel/subsistence | WP2 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | 2026-09-30 | 2026/27 | Straight-line | 80% | 333.3333 | 266.6667 | 66.6667 | 0 | 333.3333 | 266.6667 | 66.6667
WP2_TRAVEL-202610 | WP2_TRAVEL | RUSI - London-team and East Africa stakeholder travel/subsistence | WP2 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | 2026-10-31 | 2026/27 | Straight-line | 80% | 333.3333 | 266.6667 | 66.6667 | 0 | 333.3333 | 266.6667 | 66.6667
WP2_TRAVEL-202611 | WP2_TRAVEL | RUSI - London-team and East Africa stakeholder travel/subsistence | WP2 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | 2026-11-30 | 2026/27 | Straight-line | 80% | 333.3333 | 266.6667 | 66.6667 | 0 | 333.3333 | 266.6667 | 66.6667
WP2_TRAVEL-202612 | WP2_TRAVEL | RUSI - London-team and East Africa stakeholder travel/subsistence | WP2 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | 2026-12-31 | 2026/27 | Straight-line | 80% | 333.3333 | 266.6667 | 66.6667 | 0 | 333.3333 | 266.6667 | 66.6667
WP2_TRAVEL-202701 | WP2_TRAVEL | RUSI - London-team and East Africa stakeholder travel/subsistence | WP2 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | 2027-01-31 | 2026/27 | Straight-line | 80% | 333.3333 | 266.6667 | 66.6667 | 0 | 333.3333 | 266.6667 | 66.6667
WP2_TRAVEL-202702 | WP2_TRAVEL | RUSI - London-team and East Africa stakeholder travel/subsistence | WP2 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | 2027-02-28 | 2026/27 | Straight-line | 80% | 333.3333 | 266.6667 | 66.6667 | 0 | 333.3333 | 266.6667 | 66.6667
WP2_TRAVEL-202703 | WP2_TRAVEL | RUSI - London-team and East Africa stakeholder travel/subsistence | WP2 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | 2027-03-31 | 2026/27 | Straight-line | 80% | 333.3333 | 266.6667 | 66.6667 | 0 | 333.3333 | 266.6667 | 66.6667
WP2_TRAVEL-202704 | WP2_TRAVEL | RUSI - London-team and East Africa stakeholder travel/subsistence | WP2 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | 2027-04-30 | 2027/28 | Straight-line | 80% | 333.3333 | 266.6667 | 66.6667 | 0 | 333.3333 | 266.6667 | 66.6667
WP2_TRAVEL-202705 | WP2_TRAVEL | RUSI - London-team and East Africa stakeholder travel/subsistence | WP2 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | 2027-05-31 | 2027/28 | Straight-line | 80% | 333.3333 | 266.6667 | 66.6667 | 0 | 333.3333 | 266.6667 | 66.6667
WP2_TRAVEL-202706 | WP2_TRAVEL | RUSI - London-team and East Africa stakeholder travel/subsistence | WP2 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | 2027-06-30 | 2027/28 | Straight-line | 80% | 333.3333 | 266.6667 | 66.6667 | 0 | 333.3333 | 266.6667 | 66.6667
WP2_TRAVEL-202707 | WP2_TRAVEL | RUSI - London-team and East Africa stakeholder travel/subsistence | WP2 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | 2027-07-31 | 2027/28 | Straight-line | 80% | 333.3333 | 266.6667 | 66.6667 | 0 | 333.3333 | 266.6667 | 66.6667
WP2_TRAVEL-202708 | WP2_TRAVEL | RUSI - London-team and East Africa stakeholder travel/subsistence | WP2 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | 2027-08-31 | 2027/28 | Straight-line | 80% | 333.3333 | 266.6667 | 66.6667 | 0 | 333.3333 | 266.6667 | 66.6667
WP2_TRAVEL-202709 | WP2_TRAVEL | RUSI - London-team and East Africa stakeholder travel/subsistence | WP2 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | 2027-09-30 | 2027/28 | Straight-line | 80% | 333.3333 | 266.6667 | 66.6667 | 0 | 333.3333 | 266.6667 | 66.6667
WP2_TRAVEL-202710 | WP2_TRAVEL | RUSI - London-team and East Africa stakeholder travel/subsistence | WP2 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | 2027-10-31 | 2027/28 | Straight-line | 80% | 333.3333 | 266.6667 | 66.6667 | 0 | 333.3333 | 266.6667 | 66.6667
WP2_TRAVEL-202711 | WP2_TRAVEL | RUSI - London-team and East Africa stakeholder travel/subsistence | WP2 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | 2027-11-30 | 2027/28 | Straight-line | 80% | 333.3333 | 266.6667 | 66.6667 | 0 | 333.3333 | 266.6667 | 66.6667
WP2_TRAVEL-202712 | WP2_TRAVEL | RUSI - London-team and East Africa stakeholder travel/subsistence | WP2 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | 2027-12-31 | 2027/28 | Straight-line | 80% | 333.3333 | 266.6667 | 66.6667 | 0 | 333.3333 | 266.6667 | 66.6667
WP2_TRAVEL-202801 | WP2_TRAVEL | RUSI - London-team and East Africa stakeholder travel/subsistence | WP2 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | 2028-01-31 | 2027/28 | Straight-line | 80% | 333.3333 | 266.6667 | 66.6667 | 0 | 333.3333 | 266.6667 | 66.6667
WP2_TRAVEL-202802 | WP2_TRAVEL | RUSI - London-team and East Africa stakeholder travel/subsistence | WP2 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | 2028-02-29 | 2027/28 | Straight-line | 80% | 333.3333 | 266.6667 | 66.6667 | 0 | 333.3333 | 266.6667 | 66.6667
WP2_TRAVEL-202803 | WP2_TRAVEL | RUSI - London-team and East Africa stakeholder travel/subsistence | WP2 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | 2028-03-31 | 2027/28 | Straight-line | 80% | 333.3333 | 266.6667 | 66.6667 | 0 | 333.3333 | 266.6667 | 66.6667
WP2_TRAVEL-202804 | WP2_TRAVEL | RUSI - London-team and East Africa stakeholder travel/subsistence | WP2 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | 2028-04-30 | 2028/29 | Straight-line | 80% | 333.3333 | 266.6667 | 66.6667 | 0 | 333.3333 | 266.6667 | 66.6667
WP2_TRAVEL-202805 | WP2_TRAVEL | RUSI - London-team and East Africa stakeholder travel/subsistence | WP2 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | 2028-05-31 | 2028/29 | Straight-line | 80% | 333.3333 | 266.6667 | 66.6667 | 0 | 333.3333 | 266.6667 | 66.6667
WP2_TRAVEL-202806 | WP2_TRAVEL | RUSI - London-team and East Africa stakeholder travel/subsistence | WP2 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | 2028-06-30 | 2028/29 | Straight-line | 80% | 333.3333 | 266.6667 | 66.6667 | 0 | 333.3333 | 266.6667 | 66.6667
WP2_TRAVEL-202807 | WP2_TRAVEL | RUSI - London-team and East Africa stakeholder travel/subsistence | WP2 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | 2028-07-31 | 2028/29 | Straight-line | 80% | 333.3333 | 266.6667 | 66.6667 | 0 | 333.3333 | 266.6667 | 66.6667
WP2_TRAVEL-202808 | WP2_TRAVEL | RUSI - London-team and East Africa stakeholder travel/subsistence | WP2 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | 2028-08-31 | 2028/29 | Straight-line | 80% | 333.3333 | 266.6667 | 66.6667 | 0 | 333.3333 | 266.6667 | 66.6667
WP2_TRAVEL-202809 | WP2_TRAVEL | RUSI - London-team and East Africa stakeholder travel/subsistence | WP2 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | 2028-09-30 | 2028/29 | Straight-line | 80% | 333.3333 | 266.6667 | 66.6667 | 0 | 333.3333 | 266.6667 | 66.6667
WP2_TRAVEL-202810 | WP2_TRAVEL | RUSI - London-team and East Africa stakeholder travel/subsistence | WP2 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | 2028-10-31 | 2028/29 | Straight-line | 80% | 333.3333 | 266.6667 | 66.6667 | 0 | 333.3333 | 266.6667 | 66.6667
WP2_TRAVEL-202811 | WP2_TRAVEL | RUSI - London-team and East Africa stakeholder travel/subsistence | WP2 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | 2028-11-30 | 2028/29 | Straight-line | 80% | 333.3333 | 266.6667 | 66.6667 | 0 | 333.3333 | 266.6667 | 66.6667
WP2_TRAVEL-202812 | WP2_TRAVEL | RUSI - London-team and East Africa stakeholder travel/subsistence | WP2 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | 2028-12-31 | 2028/29 | Straight-line | 80% | 333.3333 | 266.6667 | 66.6667 | 0 | 333.3333 | 266.6667 | 66.6667
WP2_TRAVEL-202901 | WP2_TRAVEL | RUSI - London-team and East Africa stakeholder travel/subsistence | WP2 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | 2029-01-31 | 2028/29 | Straight-line | 80% | 333.3333 | 266.6667 | 66.6667 | 0 | 333.3333 | 266.6667 | 66.6667
WP2_TRAVEL-202902 | WP2_TRAVEL | RUSI - London-team and East Africa stakeholder travel/subsistence | WP2 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | 2029-02-28 | 2028/29 | Straight-line | 80% | 333.3333 | 266.6667 | 66.6667 | 0 | 333.3333 | 266.6667 | 66.6667
WP2_TRAVEL-202903 | WP2_TRAVEL | RUSI - London-team and East Africa stakeholder travel/subsistence | WP2 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | 2029-03-31 | 2028/29 | Straight-line | 80% | 333.3333 | 266.6667 | 66.6667 | 0 | 333.3333 | 266.6667 | 66.6667
WP2_CONSULT-202604 | WP2_CONSULT | RUSI - Nairobi-based regional network broker consultant | WP2 | Directly Incurred | Other Directly Incurred | Regional Consultancy | 2026-04-30 | 2026/27 | Straight-line | 80% | 350 | 280 | 70 | 0 | 350 | 280 | 70
WP2_CONSULT-202605 | WP2_CONSULT | RUSI - Nairobi-based regional network broker consultant | WP2 | Directly Incurred | Other Directly Incurred | Regional Consultancy | 2026-05-31 | 2026/27 | Straight-line | 80% | 350 | 280 | 70 | 0 | 350 | 280 | 70
WP2_CONSULT-202606 | WP2_CONSULT | RUSI - Nairobi-based regional network broker consultant | WP2 | Directly Incurred | Other Directly Incurred | Regional Consultancy | 2026-06-30 | 2026/27 | Straight-line | 80% | 350 | 280 | 70 | 0 | 350 | 280 | 70
WP2_CONSULT-202607 | WP2_CONSULT | RUSI - Nairobi-based regional network broker consultant | WP2 | Directly Incurred | Other Directly Incurred | Regional Consultancy | 2026-07-31 | 2026/27 | Straight-line | 80% | 350 | 280 | 70 | 0 | 350 | 280 | 70
WP2_CONSULT-202608 | WP2_CONSULT | RUSI - Nairobi-based regional network broker consultant | WP2 | Directly Incurred | Other Directly Incurred | Regional Consultancy | 2026-08-31 | 2026/27 | Straight-line | 80% | 350 | 280 | 70 | 0 | 350 | 280 | 70
WP2_CONSULT-202609 | WP2_CONSULT | RUSI - Nairobi-based regional network broker consultant | WP2 | Directly Incurred | Other Directly Incurred | Regional Consultancy | 2026-09-30 | 2026/27 | Straight-line | 80% | 350 | 280 | 70 | 0 | 350 | 280 | 70
WP2_CONSULT-202610 | WP2_CONSULT | RUSI - Nairobi-based regional network broker consultant | WP2 | Directly Incurred | Other Directly Incurred | Regional Consultancy | 2026-10-31 | 2026/27 | Straight-line | 80% | 350 | 280 | 70 | 0 | 350 | 280 | 70
WP2_CONSULT-202611 | WP2_CONSULT | RUSI - Nairobi-based regional network broker consultant | WP2 | Directly Incurred | Other Directly Incurred | Regional Consultancy | 2026-11-30 | 2026/27 | Straight-line | 80% | 350 | 280 | 70 | 0 | 350 | 280 | 70
WP2_CONSULT-202612 | WP2_CONSULT | RUSI - Nairobi-based regional network broker consultant | WP2 | Directly Incurred | Other Directly Incurred | Regional Consultancy | 2026-12-31 | 2026/27 | Straight-line | 80% | 350 | 280 | 70 | 0 | 350 | 280 | 70
WP2_CONSULT-202701 | WP2_CONSULT | RUSI - Nairobi-based regional network broker consultant | WP2 | Directly Incurred | Other Directly Incurred | Regional Consultancy | 2027-01-31 | 2026/27 | Straight-line | 80% | 350 | 280 | 70 | 0 | 350 | 280 | 70
WP2_CONSULT-202702 | WP2_CONSULT | RUSI - Nairobi-based regional network broker consultant | WP2 | Directly Incurred | Other Directly Incurred | Regional Consultancy | 2027-02-28 | 2026/27 | Straight-line | 80% | 350 | 280 | 70 | 0 | 350 | 280 | 70
WP2_CONSULT-202703 | WP2_CONSULT | RUSI - Nairobi-based regional network broker consultant | WP2 | Directly Incurred | Other Directly Incurred | Regional Consultancy | 2027-03-31 | 2026/27 | Straight-line | 80% | 350 | 280 | 70 | 0 | 350 | 280 | 70
WP2_CONSULT-202704 | WP2_CONSULT | RUSI - Nairobi-based regional network broker consultant | WP2 | Directly Incurred | Other Directly Incurred | Regional Consultancy | 2027-04-30 | 2027/28 | Straight-line | 80% | 350 | 280 | 70 | 0 | 350 | 280 | 70
WP2_CONSULT-202705 | WP2_CONSULT | RUSI - Nairobi-based regional network broker consultant | WP2 | Directly Incurred | Other Directly Incurred | Regional Consultancy | 2027-05-31 | 2027/28 | Straight-line | 80% | 350 | 280 | 70 | 0 | 350 | 280 | 70
WP2_CONSULT-202706 | WP2_CONSULT | RUSI - Nairobi-based regional network broker consultant | WP2 | Directly Incurred | Other Directly Incurred | Regional Consultancy | 2027-06-30 | 2027/28 | Straight-line | 80% | 350 | 280 | 70 | 0 | 350 | 280 | 70
WP2_CONSULT-202707 | WP2_CONSULT | RUSI - Nairobi-based regional network broker consultant | WP2 | Directly Incurred | Other Directly Incurred | Regional Consultancy | 2027-07-31 | 2027/28 | Straight-line | 80% | 350 | 280 | 70 | 0 | 350 | 280 | 70
WP2_CONSULT-202708 | WP2_CONSULT | RUSI - Nairobi-based regional network broker consultant | WP2 | Directly Incurred | Other Directly Incurred | Regional Consultancy | 2027-08-31 | 2027/28 | Straight-line | 80% | 350 | 280 | 70 | 0 | 350 | 280 | 70
WP2_CONSULT-202709 | WP2_CONSULT | RUSI - Nairobi-based regional network broker consultant | WP2 | Directly Incurred | Other Directly Incurred | Regional Consultancy | 2027-09-30 | 2027/28 | Straight-line | 80% | 350 | 280 | 70 | 0 | 350 | 280 | 70
WP2_CONSULT-202710 | WP2_CONSULT | RUSI - Nairobi-based regional network broker consultant | WP2 | Directly Incurred | Other Directly Incurred | Regional Consultancy | 2027-10-31 | 2027/28 | Straight-line | 80% | 350 | 280 | 70 | 0 | 350 | 280 | 70
WP2_CONSULT-202711 | WP2_CONSULT | RUSI - Nairobi-based regional network broker consultant | WP2 | Directly Incurred | Other Directly Incurred | Regional Consultancy | 2027-11-30 | 2027/28 | Straight-line | 80% | 350 | 280 | 70 | 0 | 350 | 280 | 70
WP2_CONSULT-202712 | WP2_CONSULT | RUSI - Nairobi-based regional network broker consultant | WP2 | Directly Incurred | Other Directly Incurred | Regional Consultancy | 2027-12-31 | 2027/28 | Straight-line | 80% | 350 | 280 | 70 | 0 | 350 | 280 | 70
WP2_CONSULT-202801 | WP2_CONSULT | RUSI - Nairobi-based regional network broker consultant | WP2 | Directly Incurred | Other Directly Incurred | Regional Consultancy | 2028-01-31 | 2027/28 | Straight-line | 80% | 350 | 280 | 70 | 0 | 350 | 280 | 70
WP2_CONSULT-202802 | WP2_CONSULT | RUSI - Nairobi-based regional network broker consultant | WP2 | Directly Incurred | Other Directly Incurred | Regional Consultancy | 2028-02-29 | 2027/28 | Straight-line | 80% | 350 | 280 | 70 | 0 | 350 | 280 | 70
WP2_CONSULT-202803 | WP2_CONSULT | RUSI - Nairobi-based regional network broker consultant | WP2 | Directly Incurred | Other Directly Incurred | Regional Consultancy | 2028-03-31 | 2027/28 | Straight-line | 80% | 350 | 280 | 70 | 0 | 350 | 280 | 70
WP2_CONSULT-202804 | WP2_CONSULT | RUSI - Nairobi-based regional network broker consultant | WP2 | Directly Incurred | Other Directly Incurred | Regional Consultancy | 2028-04-30 | 2028/29 | Straight-line | 80% | 350 | 280 | 70 | 0 | 350 | 280 | 70
WP2_CONSULT-202805 | WP2_CONSULT | RUSI - Nairobi-based regional network broker consultant | WP2 | Directly Incurred | Other Directly Incurred | Regional Consultancy | 2028-05-31 | 2028/29 | Straight-line | 80% | 350 | 280 | 70 | 0 | 350 | 280 | 70
WP2_CONSULT-202806 | WP2_CONSULT | RUSI - Nairobi-based regional network broker consultant | WP2 | Directly Incurred | Other Directly Incurred | Regional Consultancy | 2028-06-30 | 2028/29 | Straight-line | 80% | 350 | 280 | 70 | 0 | 350 | 280 | 70
WP2_CONSULT-202807 | WP2_CONSULT | RUSI - Nairobi-based regional network broker consultant | WP2 | Directly Incurred | Other Directly Incurred | Regional Consultancy | 2028-07-31 | 2028/29 | Straight-line | 80% | 350 | 280 | 70 | 0 | 350 | 280 | 70
WP2_CONSULT-202808 | WP2_CONSULT | RUSI - Nairobi-based regional network broker consultant | WP2 | Directly Incurred | Other Directly Incurred | Regional Consultancy | 2028-08-31 | 2028/29 | Straight-line | 80% | 350 | 280 | 70 | 0 | 350 | 280 | 70
WP2_CONSULT-202809 | WP2_CONSULT | RUSI - Nairobi-based regional network broker consultant | WP2 | Directly Incurred | Other Directly Incurred | Regional Consultancy | 2028-09-30 | 2028/29 | Straight-line | 80% | 350 | 280 | 70 | 0 | 350 | 280 | 70
WP2_CONSULT-202810 | WP2_CONSULT | RUSI - Nairobi-based regional network broker consultant | WP2 | Directly Incurred | Other Directly Incurred | Regional Consultancy | 2028-10-31 | 2028/29 | Straight-line | 80% | 350 | 280 | 70 | 0 | 350 | 280 | 70
WP2_CONSULT-202811 | WP2_CONSULT | RUSI - Nairobi-based regional network broker consultant | WP2 | Directly Incurred | Other Directly Incurred | Regional Consultancy | 2028-11-30 | 2028/29 | Straight-line | 80% | 350 | 280 | 70 | 0 | 350 | 280 | 70
WP2_CONSULT-202812 | WP2_CONSULT | RUSI - Nairobi-based regional network broker consultant | WP2 | Directly Incurred | Other Directly Incurred | Regional Consultancy | 2028-12-31 | 2028/29 | Straight-line | 80% | 350 | 280 | 70 | 0 | 350 | 280 | 70
WP2_CONSULT-202901 | WP2_CONSULT | RUSI - Nairobi-based regional network broker consultant | WP2 | Directly Incurred | Other Directly Incurred | Regional Consultancy | 2029-01-31 | 2028/29 | Straight-line | 80% | 350 | 280 | 70 | 0 | 350 | 280 | 70
WP2_CONSULT-202902 | WP2_CONSULT | RUSI - Nairobi-based regional network broker consultant | WP2 | Directly Incurred | Other Directly Incurred | Regional Consultancy | 2029-02-28 | 2028/29 | Straight-line | 80% | 350 | 280 | 70 | 0 | 350 | 280 | 70
WP2_CONSULT-202903 | WP2_CONSULT | RUSI - Nairobi-based regional network broker consultant | WP2 | Directly Incurred | Other Directly Incurred | Regional Consultancy | 2029-03-31 | 2028/29 | Straight-line | 80% | 350 | 280 | 70 | 0 | 350 | 280 | 70
WP2_CONF-202604 | WP2_CONF | RUSI - five-day Nairobi regional conference | WP2 | Directly Incurred | Other Directly Incurred | Conferences | 2026-04-30 | 2026/27 | Event month | 80% | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2_CONF-202605 | WP2_CONF | RUSI - five-day Nairobi regional conference | WP2 | Directly Incurred | Other Directly Incurred | Conferences | 2026-05-31 | 2026/27 | Event month | 80% | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2_CONF-202606 | WP2_CONF | RUSI - five-day Nairobi regional conference | WP2 | Directly Incurred | Other Directly Incurred | Conferences | 2026-06-30 | 2026/27 | Event month | 80% | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2_CONF-202607 | WP2_CONF | RUSI - five-day Nairobi regional conference | WP2 | Directly Incurred | Other Directly Incurred | Conferences | 2026-07-31 | 2026/27 | Event month | 80% | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2_CONF-202608 | WP2_CONF | RUSI - five-day Nairobi regional conference | WP2 | Directly Incurred | Other Directly Incurred | Conferences | 2026-08-31 | 2026/27 | Event month | 80% | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2_CONF-202609 | WP2_CONF | RUSI - five-day Nairobi regional conference | WP2 | Directly Incurred | Other Directly Incurred | Conferences | 2026-09-30 | 2026/27 | Event month | 80% | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2_CONF-202610 | WP2_CONF | RUSI - five-day Nairobi regional conference | WP2 | Directly Incurred | Other Directly Incurred | Conferences | 2026-10-31 | 2026/27 | Event month | 80% | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2_CONF-202611 | WP2_CONF | RUSI - five-day Nairobi regional conference | WP2 | Directly Incurred | Other Directly Incurred | Conferences | 2026-11-30 | 2026/27 | Event month | 80% | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2_CONF-202612 | WP2_CONF | RUSI - five-day Nairobi regional conference | WP2 | Directly Incurred | Other Directly Incurred | Conferences | 2026-12-31 | 2026/27 | Event month | 80% | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2_CONF-202701 | WP2_CONF | RUSI - five-day Nairobi regional conference | WP2 | Directly Incurred | Other Directly Incurred | Conferences | 2027-01-31 | 2026/27 | Event month | 80% | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2_CONF-202702 | WP2_CONF | RUSI - five-day Nairobi regional conference | WP2 | Directly Incurred | Other Directly Incurred | Conferences | 2027-02-28 | 2026/27 | Event month | 80% | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2_CONF-202703 | WP2_CONF | RUSI - five-day Nairobi regional conference | WP2 | Directly Incurred | Other Directly Incurred | Conferences | 2027-03-31 | 2026/27 | Event month | 80% | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2_CONF-202704 | WP2_CONF | RUSI - five-day Nairobi regional conference | WP2 | Directly Incurred | Other Directly Incurred | Conferences | 2027-04-30 | 2027/28 | Event month | 80% | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2_CONF-202705 | WP2_CONF | RUSI - five-day Nairobi regional conference | WP2 | Directly Incurred | Other Directly Incurred | Conferences | 2027-05-31 | 2027/28 | Event month | 80% | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2_CONF-202706 | WP2_CONF | RUSI - five-day Nairobi regional conference | WP2 | Directly Incurred | Other Directly Incurred | Conferences | 2027-06-30 | 2027/28 | Event month | 80% | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2_CONF-202707 | WP2_CONF | RUSI - five-day Nairobi regional conference | WP2 | Directly Incurred | Other Directly Incurred | Conferences | 2027-07-31 | 2027/28 | Event month | 80% | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2_CONF-202708 | WP2_CONF | RUSI - five-day Nairobi regional conference | WP2 | Directly Incurred | Other Directly Incurred | Conferences | 2027-08-31 | 2027/28 | Event month | 80% | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2_CONF-202709 | WP2_CONF | RUSI - five-day Nairobi regional conference | WP2 | Directly Incurred | Other Directly Incurred | Conferences | 2027-09-30 | 2027/28 | Event month | 80% | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2_CONF-202710 | WP2_CONF | RUSI - five-day Nairobi regional conference | WP2 | Directly Incurred | Other Directly Incurred | Conferences | 2027-10-31 | 2027/28 | Event month | 80% | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2_CONF-202711 | WP2_CONF | RUSI - five-day Nairobi regional conference | WP2 | Directly Incurred | Other Directly Incurred | Conferences | 2027-11-30 | 2027/28 | Event month | 80% | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2_CONF-202712 | WP2_CONF | RUSI - five-day Nairobi regional conference | WP2 | Directly Incurred | Other Directly Incurred | Conferences | 2027-12-31 | 2027/28 | Event month | 80% | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2_CONF-202801 | WP2_CONF | RUSI - five-day Nairobi regional conference | WP2 | Directly Incurred | Other Directly Incurred | Conferences | 2028-01-31 | 2027/28 | Event month | 80% | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2_CONF-202802 | WP2_CONF | RUSI - five-day Nairobi regional conference | WP2 | Directly Incurred | Other Directly Incurred | Conferences | 2028-02-29 | 2027/28 | Event month | 80% | 16000 | 12800 | 3200 | 0 | 16000 | 12800 | 3200
WP2_CONF-202803 | WP2_CONF | RUSI - five-day Nairobi regional conference | WP2 | Directly Incurred | Other Directly Incurred | Conferences | 2028-03-31 | 2027/28 | Event month | 80% | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2_CONF-202804 | WP2_CONF | RUSI - five-day Nairobi regional conference | WP2 | Directly Incurred | Other Directly Incurred | Conferences | 2028-04-30 | 2028/29 | Event month | 80% | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2_CONF-202805 | WP2_CONF | RUSI - five-day Nairobi regional conference | WP2 | Directly Incurred | Other Directly Incurred | Conferences | 2028-05-31 | 2028/29 | Event month | 80% | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2_CONF-202806 | WP2_CONF | RUSI - five-day Nairobi regional conference | WP2 | Directly Incurred | Other Directly Incurred | Conferences | 2028-06-30 | 2028/29 | Event month | 80% | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2_CONF-202807 | WP2_CONF | RUSI - five-day Nairobi regional conference | WP2 | Directly Incurred | Other Directly Incurred | Conferences | 2028-07-31 | 2028/29 | Event month | 80% | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2_CONF-202808 | WP2_CONF | RUSI - five-day Nairobi regional conference | WP2 | Directly Incurred | Other Directly Incurred | Conferences | 2028-08-31 | 2028/29 | Event month | 80% | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2_CONF-202809 | WP2_CONF | RUSI - five-day Nairobi regional conference | WP2 | Directly Incurred | Other Directly Incurred | Conferences | 2028-09-30 | 2028/29 | Event month | 80% | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2_CONF-202810 | WP2_CONF | RUSI - five-day Nairobi regional conference | WP2 | Directly Incurred | Other Directly Incurred | Conferences | 2028-10-31 | 2028/29 | Event month | 80% | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2_CONF-202811 | WP2_CONF | RUSI - five-day Nairobi regional conference | WP2 | Directly Incurred | Other Directly Incurred | Conferences | 2028-11-30 | 2028/29 | Event month | 80% | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2_CONF-202812 | WP2_CONF | RUSI - five-day Nairobi regional conference | WP2 | Directly Incurred | Other Directly Incurred | Conferences | 2028-12-31 | 2028/29 | Event month | 80% | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2_CONF-202901 | WP2_CONF | RUSI - five-day Nairobi regional conference | WP2 | Directly Incurred | Other Directly Incurred | Conferences | 2029-01-31 | 2028/29 | Event month | 80% | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2_CONF-202902 | WP2_CONF | RUSI - five-day Nairobi regional conference | WP2 | Directly Incurred | Other Directly Incurred | Conferences | 2029-02-28 | 2028/29 | Event month | 80% | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2_CONF-202903 | WP2_CONF | RUSI - five-day Nairobi regional conference | WP2 | Directly Incurred | Other Directly Incurred | Conferences | 2029-03-31 | 2028/29 | Event month | 80% | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2_WORKSHOP-202604 | WP2_WORKSHOP | RUSI - East Africa practitioner-policy-academic workshops | WP2 | Directly Incurred | Other Directly Incurred | Workshops | 2026-04-30 | 2026/27 | Straight-line | 80% | 166.6667 | 133.3333 | 33.3333 | 0 | 166.6667 | 133.3333 | 33.3333
WP2_WORKSHOP-202605 | WP2_WORKSHOP | RUSI - East Africa practitioner-policy-academic workshops | WP2 | Directly Incurred | Other Directly Incurred | Workshops | 2026-05-31 | 2026/27 | Straight-line | 80% | 166.6667 | 133.3333 | 33.3333 | 0 | 166.6667 | 133.3333 | 33.3333
WP2_WORKSHOP-202606 | WP2_WORKSHOP | RUSI - East Africa practitioner-policy-academic workshops | WP2 | Directly Incurred | Other Directly Incurred | Workshops | 2026-06-30 | 2026/27 | Straight-line | 80% | 166.6667 | 133.3333 | 33.3333 | 0 | 166.6667 | 133.3333 | 33.3333
WP2_WORKSHOP-202607 | WP2_WORKSHOP | RUSI - East Africa practitioner-policy-academic workshops | WP2 | Directly Incurred | Other Directly Incurred | Workshops | 2026-07-31 | 2026/27 | Straight-line | 80% | 166.6667 | 133.3333 | 33.3333 | 0 | 166.6667 | 133.3333 | 33.3333
WP2_WORKSHOP-202608 | WP2_WORKSHOP | RUSI - East Africa practitioner-policy-academic workshops | WP2 | Directly Incurred | Other Directly Incurred | Workshops | 2026-08-31 | 2026/27 | Straight-line | 80% | 166.6667 | 133.3333 | 33.3333 | 0 | 166.6667 | 133.3333 | 33.3333
WP2_WORKSHOP-202609 | WP2_WORKSHOP | RUSI - East Africa practitioner-policy-academic workshops | WP2 | Directly Incurred | Other Directly Incurred | Workshops | 2026-09-30 | 2026/27 | Straight-line | 80% | 166.6667 | 133.3333 | 33.3333 | 0 | 166.6667 | 133.3333 | 33.3333
WP2_WORKSHOP-202610 | WP2_WORKSHOP | RUSI - East Africa practitioner-policy-academic workshops | WP2 | Directly Incurred | Other Directly Incurred | Workshops | 2026-10-31 | 2026/27 | Straight-line | 80% | 166.6667 | 133.3333 | 33.3333 | 0 | 166.6667 | 133.3333 | 33.3333
WP2_WORKSHOP-202611 | WP2_WORKSHOP | RUSI - East Africa practitioner-policy-academic workshops | WP2 | Directly Incurred | Other Directly Incurred | Workshops | 2026-11-30 | 2026/27 | Straight-line | 80% | 166.6667 | 133.3333 | 33.3333 | 0 | 166.6667 | 133.3333 | 33.3333
WP2_WORKSHOP-202612 | WP2_WORKSHOP | RUSI - East Africa practitioner-policy-academic workshops | WP2 | Directly Incurred | Other Directly Incurred | Workshops | 2026-12-31 | 2026/27 | Straight-line | 80% | 166.6667 | 133.3333 | 33.3333 | 0 | 166.6667 | 133.3333 | 33.3333
WP2_WORKSHOP-202701 | WP2_WORKSHOP | RUSI - East Africa practitioner-policy-academic workshops | WP2 | Directly Incurred | Other Directly Incurred | Workshops | 2027-01-31 | 2026/27 | Straight-line | 80% | 166.6667 | 133.3333 | 33.3333 | 0 | 166.6667 | 133.3333 | 33.3333
WP2_WORKSHOP-202702 | WP2_WORKSHOP | RUSI - East Africa practitioner-policy-academic workshops | WP2 | Directly Incurred | Other Directly Incurred | Workshops | 2027-02-28 | 2026/27 | Straight-line | 80% | 166.6667 | 133.3333 | 33.3333 | 0 | 166.6667 | 133.3333 | 33.3333
WP2_WORKSHOP-202703 | WP2_WORKSHOP | RUSI - East Africa practitioner-policy-academic workshops | WP2 | Directly Incurred | Other Directly Incurred | Workshops | 2027-03-31 | 2026/27 | Straight-line | 80% | 166.6667 | 133.3333 | 33.3333 | 0 | 166.6667 | 133.3333 | 33.3333
WP2_WORKSHOP-202704 | WP2_WORKSHOP | RUSI - East Africa practitioner-policy-academic workshops | WP2 | Directly Incurred | Other Directly Incurred | Workshops | 2027-04-30 | 2027/28 | Straight-line | 80% | 166.6667 | 133.3333 | 33.3333 | 0 | 166.6667 | 133.3333 | 33.3333
WP2_WORKSHOP-202705 | WP2_WORKSHOP | RUSI - East Africa practitioner-policy-academic workshops | WP2 | Directly Incurred | Other Directly Incurred | Workshops | 2027-05-31 | 2027/28 | Straight-line | 80% | 166.6667 | 133.3333 | 33.3333 | 0 | 166.6667 | 133.3333 | 33.3333
WP2_WORKSHOP-202706 | WP2_WORKSHOP | RUSI - East Africa practitioner-policy-academic workshops | WP2 | Directly Incurred | Other Directly Incurred | Workshops | 2027-06-30 | 2027/28 | Straight-line | 80% | 166.6667 | 133.3333 | 33.3333 | 0 | 166.6667 | 133.3333 | 33.3333
WP2_WORKSHOP-202707 | WP2_WORKSHOP | RUSI - East Africa practitioner-policy-academic workshops | WP2 | Directly Incurred | Other Directly Incurred | Workshops | 2027-07-31 | 2027/28 | Straight-line | 80% | 166.6667 | 133.3333 | 33.3333 | 0 | 166.6667 | 133.3333 | 33.3333
WP2_WORKSHOP-202708 | WP2_WORKSHOP | RUSI - East Africa practitioner-policy-academic workshops | WP2 | Directly Incurred | Other Directly Incurred | Workshops | 2027-08-31 | 2027/28 | Straight-line | 80% | 166.6667 | 133.3333 | 33.3333 | 0 | 166.6667 | 133.3333 | 33.3333
WP2_WORKSHOP-202709 | WP2_WORKSHOP | RUSI - East Africa practitioner-policy-academic workshops | WP2 | Directly Incurred | Other Directly Incurred | Workshops | 2027-09-30 | 2027/28 | Straight-line | 80% | 166.6667 | 133.3333 | 33.3333 | 0 | 166.6667 | 133.3333 | 33.3333
WP2_WORKSHOP-202710 | WP2_WORKSHOP | RUSI - East Africa practitioner-policy-academic workshops | WP2 | Directly Incurred | Other Directly Incurred | Workshops | 2027-10-31 | 2027/28 | Straight-line | 80% | 166.6667 | 133.3333 | 33.3333 | 0 | 166.6667 | 133.3333 | 33.3333
WP2_WORKSHOP-202711 | WP2_WORKSHOP | RUSI - East Africa practitioner-policy-academic workshops | WP2 | Directly Incurred | Other Directly Incurred | Workshops | 2027-11-30 | 2027/28 | Straight-line | 80% | 166.6667 | 133.3333 | 33.3333 | 0 | 166.6667 | 133.3333 | 33.3333
WP2_WORKSHOP-202712 | WP2_WORKSHOP | RUSI - East Africa practitioner-policy-academic workshops | WP2 | Directly Incurred | Other Directly Incurred | Workshops | 2027-12-31 | 2027/28 | Straight-line | 80% | 166.6667 | 133.3333 | 33.3333 | 0 | 166.6667 | 133.3333 | 33.3333
WP2_WORKSHOP-202801 | WP2_WORKSHOP | RUSI - East Africa practitioner-policy-academic workshops | WP2 | Directly Incurred | Other Directly Incurred | Workshops | 2028-01-31 | 2027/28 | Straight-line | 80% | 166.6667 | 133.3333 | 33.3333 | 0 | 166.6667 | 133.3333 | 33.3333
WP2_WORKSHOP-202802 | WP2_WORKSHOP | RUSI - East Africa practitioner-policy-academic workshops | WP2 | Directly Incurred | Other Directly Incurred | Workshops | 2028-02-29 | 2027/28 | Straight-line | 80% | 166.6667 | 133.3333 | 33.3333 | 0 | 166.6667 | 133.3333 | 33.3333
WP2_WORKSHOP-202803 | WP2_WORKSHOP | RUSI - East Africa practitioner-policy-academic workshops | WP2 | Directly Incurred | Other Directly Incurred | Workshops | 2028-03-31 | 2027/28 | Straight-line | 80% | 166.6667 | 133.3333 | 33.3333 | 0 | 166.6667 | 133.3333 | 33.3333
WP2_WORKSHOP-202804 | WP2_WORKSHOP | RUSI - East Africa practitioner-policy-academic workshops | WP2 | Directly Incurred | Other Directly Incurred | Workshops | 2028-04-30 | 2028/29 | Straight-line | 80% | 166.6667 | 133.3333 | 33.3333 | 0 | 166.6667 | 133.3333 | 33.3333
WP2_WORKSHOP-202805 | WP2_WORKSHOP | RUSI - East Africa practitioner-policy-academic workshops | WP2 | Directly Incurred | Other Directly Incurred | Workshops | 2028-05-31 | 2028/29 | Straight-line | 80% | 166.6667 | 133.3333 | 33.3333 | 0 | 166.6667 | 133.3333 | 33.3333
WP2_WORKSHOP-202806 | WP2_WORKSHOP | RUSI - East Africa practitioner-policy-academic workshops | WP2 | Directly Incurred | Other Directly Incurred | Workshops | 2028-06-30 | 2028/29 | Straight-line | 80% | 166.6667 | 133.3333 | 33.3333 | 0 | 166.6667 | 133.3333 | 33.3333
WP2_WORKSHOP-202807 | WP2_WORKSHOP | RUSI - East Africa practitioner-policy-academic workshops | WP2 | Directly Incurred | Other Directly Incurred | Workshops | 2028-07-31 | 2028/29 | Straight-line | 80% | 166.6667 | 133.3333 | 33.3333 | 0 | 166.6667 | 133.3333 | 33.3333
WP2_WORKSHOP-202808 | WP2_WORKSHOP | RUSI - East Africa practitioner-policy-academic workshops | WP2 | Directly Incurred | Other Directly Incurred | Workshops | 2028-08-31 | 2028/29 | Straight-line | 80% | 166.6667 | 133.3333 | 33.3333 | 0 | 166.6667 | 133.3333 | 33.3333
WP2_WORKSHOP-202809 | WP2_WORKSHOP | RUSI - East Africa practitioner-policy-academic workshops | WP2 | Directly Incurred | Other Directly Incurred | Workshops | 2028-09-30 | 2028/29 | Straight-line | 80% | 166.6667 | 133.3333 | 33.3333 | 0 | 166.6667 | 133.3333 | 33.3333
WP2_WORKSHOP-202810 | WP2_WORKSHOP | RUSI - East Africa practitioner-policy-academic workshops | WP2 | Directly Incurred | Other Directly Incurred | Workshops | 2028-10-31 | 2028/29 | Straight-line | 80% | 166.6667 | 133.3333 | 33.3333 | 0 | 166.6667 | 133.3333 | 33.3333
WP2_WORKSHOP-202811 | WP2_WORKSHOP | RUSI - East Africa practitioner-policy-academic workshops | WP2 | Directly Incurred | Other Directly Incurred | Workshops | 2028-11-30 | 2028/29 | Straight-line | 80% | 166.6667 | 133.3333 | 33.3333 | 0 | 166.6667 | 133.3333 | 33.3333
WP2_WORKSHOP-202812 | WP2_WORKSHOP | RUSI - East Africa practitioner-policy-academic workshops | WP2 | Directly Incurred | Other Directly Incurred | Workshops | 2028-12-31 | 2028/29 | Straight-line | 80% | 166.6667 | 133.3333 | 33.3333 | 0 | 166.6667 | 133.3333 | 33.3333
WP2_WORKSHOP-202901 | WP2_WORKSHOP | RUSI - East Africa practitioner-policy-academic workshops | WP2 | Directly Incurred | Other Directly Incurred | Workshops | 2029-01-31 | 2028/29 | Straight-line | 80% | 166.6667 | 133.3333 | 33.3333 | 0 | 166.6667 | 133.3333 | 33.3333
WP2_WORKSHOP-202902 | WP2_WORKSHOP | RUSI - East Africa practitioner-policy-academic workshops | WP2 | Directly Incurred | Other Directly Incurred | Workshops | 2029-02-28 | 2028/29 | Straight-line | 80% | 166.6667 | 133.3333 | 33.3333 | 0 | 166.6667 | 133.3333 | 33.3333
WP2_WORKSHOP-202903 | WP2_WORKSHOP | RUSI - East Africa practitioner-policy-academic workshops | WP2 | Directly Incurred | Other Directly Incurred | Workshops | 2029-03-31 | 2028/29 | Straight-line | 80% | 166.6667 | 133.3333 | 33.3333 | 0 | 166.6667 | 133.3333 | 33.3333
WP2_COMMS-202604 | WP2_COMMS | RUSI - participant materials and regional communications | WP2 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | 2026-04-30 | 2026/27 | Straight-line | 80% | 55.5558 | 44.4447 | 11.1112 | 0 | 55.5558 | 44.4447 | 11.1112
WP2_COMMS-202605 | WP2_COMMS | RUSI - participant materials and regional communications | WP2 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | 2026-05-31 | 2026/27 | Straight-line | 80% | 55.5558 | 44.4447 | 11.1112 | 0 | 55.5558 | 44.4447 | 11.1112
WP2_COMMS-202606 | WP2_COMMS | RUSI - participant materials and regional communications | WP2 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | 2026-06-30 | 2026/27 | Straight-line | 80% | 55.5558 | 44.4447 | 11.1112 | 0 | 55.5558 | 44.4447 | 11.1112
WP2_COMMS-202607 | WP2_COMMS | RUSI - participant materials and regional communications | WP2 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | 2026-07-31 | 2026/27 | Straight-line | 80% | 55.5558 | 44.4447 | 11.1112 | 0 | 55.5558 | 44.4447 | 11.1112
WP2_COMMS-202608 | WP2_COMMS | RUSI - participant materials and regional communications | WP2 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | 2026-08-31 | 2026/27 | Straight-line | 80% | 55.5558 | 44.4447 | 11.1112 | 0 | 55.5558 | 44.4447 | 11.1112
WP2_COMMS-202609 | WP2_COMMS | RUSI - participant materials and regional communications | WP2 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | 2026-09-30 | 2026/27 | Straight-line | 80% | 55.5558 | 44.4447 | 11.1112 | 0 | 55.5558 | 44.4447 | 11.1112
WP2_COMMS-202610 | WP2_COMMS | RUSI - participant materials and regional communications | WP2 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | 2026-10-31 | 2026/27 | Straight-line | 80% | 55.5558 | 44.4447 | 11.1112 | 0 | 55.5558 | 44.4447 | 11.1112
WP2_COMMS-202611 | WP2_COMMS | RUSI - participant materials and regional communications | WP2 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | 2026-11-30 | 2026/27 | Straight-line | 80% | 55.5558 | 44.4447 | 11.1112 | 0 | 55.5558 | 44.4447 | 11.1112
WP2_COMMS-202612 | WP2_COMMS | RUSI - participant materials and regional communications | WP2 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | 2026-12-31 | 2026/27 | Straight-line | 80% | 55.5558 | 44.4447 | 11.1112 | 0 | 55.5558 | 44.4447 | 11.1112
WP2_COMMS-202701 | WP2_COMMS | RUSI - participant materials and regional communications | WP2 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | 2027-01-31 | 2026/27 | Straight-line | 80% | 55.5558 | 44.4447 | 11.1112 | 0 | 55.5558 | 44.4447 | 11.1112
WP2_COMMS-202702 | WP2_COMMS | RUSI - participant materials and regional communications | WP2 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | 2027-02-28 | 2026/27 | Straight-line | 80% | 55.5558 | 44.4447 | 11.1112 | 0 | 55.5558 | 44.4447 | 11.1112
WP2_COMMS-202703 | WP2_COMMS | RUSI - participant materials and regional communications | WP2 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | 2027-03-31 | 2026/27 | Straight-line | 80% | 55.5558 | 44.4447 | 11.1112 | 0 | 55.5558 | 44.4447 | 11.1112
WP2_COMMS-202704 | WP2_COMMS | RUSI - participant materials and regional communications | WP2 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | 2027-04-30 | 2027/28 | Straight-line | 80% | 55.5558 | 44.4447 | 11.1112 | 0 | 55.5558 | 44.4447 | 11.1112
WP2_COMMS-202705 | WP2_COMMS | RUSI - participant materials and regional communications | WP2 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | 2027-05-31 | 2027/28 | Straight-line | 80% | 55.5558 | 44.4447 | 11.1112 | 0 | 55.5558 | 44.4447 | 11.1112
WP2_COMMS-202706 | WP2_COMMS | RUSI - participant materials and regional communications | WP2 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | 2027-06-30 | 2027/28 | Straight-line | 80% | 55.5558 | 44.4447 | 11.1112 | 0 | 55.5558 | 44.4447 | 11.1112
WP2_COMMS-202707 | WP2_COMMS | RUSI - participant materials and regional communications | WP2 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | 2027-07-31 | 2027/28 | Straight-line | 80% | 55.5558 | 44.4447 | 11.1112 | 0 | 55.5558 | 44.4447 | 11.1112
WP2_COMMS-202708 | WP2_COMMS | RUSI - participant materials and regional communications | WP2 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | 2027-08-31 | 2027/28 | Straight-line | 80% | 55.5558 | 44.4447 | 11.1112 | 0 | 55.5558 | 44.4447 | 11.1112
WP2_COMMS-202709 | WP2_COMMS | RUSI - participant materials and regional communications | WP2 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | 2027-09-30 | 2027/28 | Straight-line | 80% | 55.5558 | 44.4447 | 11.1112 | 0 | 55.5558 | 44.4447 | 11.1112
WP2_COMMS-202710 | WP2_COMMS | RUSI - participant materials and regional communications | WP2 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | 2027-10-31 | 2027/28 | Straight-line | 80% | 55.5558 | 44.4447 | 11.1112 | 0 | 55.5558 | 44.4447 | 11.1112
WP2_COMMS-202711 | WP2_COMMS | RUSI - participant materials and regional communications | WP2 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | 2027-11-30 | 2027/28 | Straight-line | 80% | 55.5558 | 44.4447 | 11.1112 | 0 | 55.5558 | 44.4447 | 11.1112
WP2_COMMS-202712 | WP2_COMMS | RUSI - participant materials and regional communications | WP2 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | 2027-12-31 | 2027/28 | Straight-line | 80% | 55.5558 | 44.4447 | 11.1112 | 0 | 55.5558 | 44.4447 | 11.1112
WP2_COMMS-202801 | WP2_COMMS | RUSI - participant materials and regional communications | WP2 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | 2028-01-31 | 2027/28 | Straight-line | 80% | 55.5558 | 44.4447 | 11.1112 | 0 | 55.5558 | 44.4447 | 11.1112
WP2_COMMS-202802 | WP2_COMMS | RUSI - participant materials and regional communications | WP2 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | 2028-02-29 | 2027/28 | Straight-line | 80% | 55.5558 | 44.4447 | 11.1112 | 0 | 55.5558 | 44.4447 | 11.1112
WP2_COMMS-202803 | WP2_COMMS | RUSI - participant materials and regional communications | WP2 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | 2028-03-31 | 2027/28 | Straight-line | 80% | 55.5558 | 44.4447 | 11.1112 | 0 | 55.5558 | 44.4447 | 11.1112
WP2_COMMS-202804 | WP2_COMMS | RUSI - participant materials and regional communications | WP2 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | 2028-04-30 | 2028/29 | Straight-line | 80% | 55.5558 | 44.4447 | 11.1112 | 0 | 55.5558 | 44.4447 | 11.1112
WP2_COMMS-202805 | WP2_COMMS | RUSI - participant materials and regional communications | WP2 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | 2028-05-31 | 2028/29 | Straight-line | 80% | 55.5558 | 44.4447 | 11.1112 | 0 | 55.5558 | 44.4447 | 11.1112
WP2_COMMS-202806 | WP2_COMMS | RUSI - participant materials and regional communications | WP2 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | 2028-06-30 | 2028/29 | Straight-line | 80% | 55.5558 | 44.4447 | 11.1112 | 0 | 55.5558 | 44.4447 | 11.1112
WP2_COMMS-202807 | WP2_COMMS | RUSI - participant materials and regional communications | WP2 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | 2028-07-31 | 2028/29 | Straight-line | 80% | 55.5558 | 44.4447 | 11.1112 | 0 | 55.5558 | 44.4447 | 11.1112
WP2_COMMS-202808 | WP2_COMMS | RUSI - participant materials and regional communications | WP2 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | 2028-08-31 | 2028/29 | Straight-line | 80% | 55.5558 | 44.4447 | 11.1112 | 0 | 55.5558 | 44.4447 | 11.1112
WP2_COMMS-202809 | WP2_COMMS | RUSI - participant materials and regional communications | WP2 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | 2028-09-30 | 2028/29 | Straight-line | 80% | 55.5558 | 44.4447 | 11.1112 | 0 | 55.5558 | 44.4447 | 11.1112
WP2_COMMS-202810 | WP2_COMMS | RUSI - participant materials and regional communications | WP2 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | 2028-10-31 | 2028/29 | Straight-line | 80% | 55.5558 | 44.4447 | 11.1112 | 0 | 55.5558 | 44.4447 | 11.1112
WP2_COMMS-202811 | WP2_COMMS | RUSI - participant materials and regional communications | WP2 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | 2028-11-30 | 2028/29 | Straight-line | 80% | 55.5558 | 44.4447 | 11.1112 | 0 | 55.5558 | 44.4447 | 11.1112
WP2_COMMS-202812 | WP2_COMMS | RUSI - participant materials and regional communications | WP2 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | 2028-12-31 | 2028/29 | Straight-line | 80% | 55.5558 | 44.4447 | 11.1112 | 0 | 55.5558 | 44.4447 | 11.1112
WP2_COMMS-202901 | WP2_COMMS | RUSI - participant materials and regional communications | WP2 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | 2029-01-31 | 2028/29 | Straight-line | 80% | 55.5558 | 44.4447 | 11.1112 | 0 | 55.5558 | 44.4447 | 11.1112
WP2_COMMS-202902 | WP2_COMMS | RUSI - participant materials and regional communications | WP2 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | 2029-02-28 | 2028/29 | Straight-line | 80% | 55.5558 | 44.4447 | 11.1112 | 0 | 55.5558 | 44.4447 | 11.1112
WP2_COMMS-202903 | WP2_COMMS | RUSI - participant materials and regional communications | WP2 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | 2029-03-31 | 2028/29 | Straight-line | 80% | 55.5558 | 44.4447 | 11.1112 | 0 | 55.5558 | 44.4447 | 11.1112
WP2_IND-202604 | WP2_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP2 | Indirect | Indirect | Indirect Costs | 2026-04-30 | 2026/27 | Straight-line | 80% | 383.3533 | 306.6827 | 76.6707 | 0 | 383.3533 | 306.6827 | 76.6707
WP2_IND-202605 | WP2_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP2 | Indirect | Indirect | Indirect Costs | 2026-05-31 | 2026/27 | Straight-line | 80% | 383.3533 | 306.6827 | 76.6707 | 0 | 383.3533 | 306.6827 | 76.6707
WP2_IND-202606 | WP2_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP2 | Indirect | Indirect | Indirect Costs | 2026-06-30 | 2026/27 | Straight-line | 80% | 383.3533 | 306.6827 | 76.6707 | 0 | 383.3533 | 306.6827 | 76.6707
WP2_IND-202607 | WP2_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP2 | Indirect | Indirect | Indirect Costs | 2026-07-31 | 2026/27 | Straight-line | 80% | 383.3533 | 306.6827 | 76.6707 | 0 | 383.3533 | 306.6827 | 76.6707
WP2_IND-202608 | WP2_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP2 | Indirect | Indirect | Indirect Costs | 2026-08-31 | 2026/27 | Straight-line | 80% | 383.3533 | 306.6827 | 76.6707 | 0 | 383.3533 | 306.6827 | 76.6707
WP2_IND-202609 | WP2_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP2 | Indirect | Indirect | Indirect Costs | 2026-09-30 | 2026/27 | Straight-line | 80% | 383.3533 | 306.6827 | 76.6707 | 0 | 383.3533 | 306.6827 | 76.6707
WP2_IND-202610 | WP2_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP2 | Indirect | Indirect | Indirect Costs | 2026-10-31 | 2026/27 | Straight-line | 80% | 383.3533 | 306.6827 | 76.6707 | 0 | 383.3533 | 306.6827 | 76.6707
WP2_IND-202611 | WP2_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP2 | Indirect | Indirect | Indirect Costs | 2026-11-30 | 2026/27 | Straight-line | 80% | 383.3533 | 306.6827 | 76.6707 | 0 | 383.3533 | 306.6827 | 76.6707
WP2_IND-202612 | WP2_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP2 | Indirect | Indirect | Indirect Costs | 2026-12-31 | 2026/27 | Straight-line | 80% | 383.3533 | 306.6827 | 76.6707 | 0 | 383.3533 | 306.6827 | 76.6707
WP2_IND-202701 | WP2_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP2 | Indirect | Indirect | Indirect Costs | 2027-01-31 | 2026/27 | Straight-line | 80% | 383.3533 | 306.6827 | 76.6707 | 0 | 383.3533 | 306.6827 | 76.6707
WP2_IND-202702 | WP2_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP2 | Indirect | Indirect | Indirect Costs | 2027-02-28 | 2026/27 | Straight-line | 80% | 383.3533 | 306.6827 | 76.6707 | 0 | 383.3533 | 306.6827 | 76.6707
WP2_IND-202703 | WP2_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP2 | Indirect | Indirect | Indirect Costs | 2027-03-31 | 2026/27 | Straight-line | 80% | 383.3533 | 306.6827 | 76.6707 | 0 | 383.3533 | 306.6827 | 76.6707
WP2_IND-202704 | WP2_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP2 | Indirect | Indirect | Indirect Costs | 2027-04-30 | 2027/28 | Straight-line | 80% | 383.3533 | 306.6827 | 76.6707 | 0 | 383.3533 | 306.6827 | 76.6707
WP2_IND-202705 | WP2_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP2 | Indirect | Indirect | Indirect Costs | 2027-05-31 | 2027/28 | Straight-line | 80% | 383.3533 | 306.6827 | 76.6707 | 0 | 383.3533 | 306.6827 | 76.6707
WP2_IND-202706 | WP2_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP2 | Indirect | Indirect | Indirect Costs | 2027-06-30 | 2027/28 | Straight-line | 80% | 383.3533 | 306.6827 | 76.6707 | 0 | 383.3533 | 306.6827 | 76.6707
WP2_IND-202707 | WP2_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP2 | Indirect | Indirect | Indirect Costs | 2027-07-31 | 2027/28 | Straight-line | 80% | 383.3533 | 306.6827 | 76.6707 | 0 | 383.3533 | 306.6827 | 76.6707
WP2_IND-202708 | WP2_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP2 | Indirect | Indirect | Indirect Costs | 2027-08-31 | 2027/28 | Straight-line | 80% | 383.3533 | 306.6827 | 76.6707 | 0 | 383.3533 | 306.6827 | 76.6707
WP2_IND-202709 | WP2_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP2 | Indirect | Indirect | Indirect Costs | 2027-09-30 | 2027/28 | Straight-line | 80% | 383.3533 | 306.6827 | 76.6707 | 0 | 383.3533 | 306.6827 | 76.6707
WP2_IND-202710 | WP2_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP2 | Indirect | Indirect | Indirect Costs | 2027-10-31 | 2027/28 | Straight-line | 80% | 383.3533 | 306.6827 | 76.6707 | 0 | 383.3533 | 306.6827 | 76.6707
WP2_IND-202711 | WP2_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP2 | Indirect | Indirect | Indirect Costs | 2027-11-30 | 2027/28 | Straight-line | 80% | 383.3533 | 306.6827 | 76.6707 | 0 | 383.3533 | 306.6827 | 76.6707
WP2_IND-202712 | WP2_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP2 | Indirect | Indirect | Indirect Costs | 2027-12-31 | 2027/28 | Straight-line | 80% | 383.3533 | 306.6827 | 76.6707 | 0 | 383.3533 | 306.6827 | 76.6707
WP2_IND-202801 | WP2_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP2 | Indirect | Indirect | Indirect Costs | 2028-01-31 | 2027/28 | Straight-line | 80% | 383.3533 | 306.6827 | 76.6707 | 0 | 383.3533 | 306.6827 | 76.6707
WP2_IND-202802 | WP2_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP2 | Indirect | Indirect | Indirect Costs | 2028-02-29 | 2027/28 | Straight-line | 80% | 383.3533 | 306.6827 | 76.6707 | 0 | 383.3533 | 306.6827 | 76.6707
WP2_IND-202803 | WP2_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP2 | Indirect | Indirect | Indirect Costs | 2028-03-31 | 2027/28 | Straight-line | 80% | 383.3533 | 306.6827 | 76.6707 | 0 | 383.3533 | 306.6827 | 76.6707
WP2_IND-202804 | WP2_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP2 | Indirect | Indirect | Indirect Costs | 2028-04-30 | 2028/29 | Straight-line | 80% | 383.3533 | 306.6827 | 76.6707 | 0 | 383.3533 | 306.6827 | 76.6707
WP2_IND-202805 | WP2_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP2 | Indirect | Indirect | Indirect Costs | 2028-05-31 | 2028/29 | Straight-line | 80% | 383.3533 | 306.6827 | 76.6707 | 0 | 383.3533 | 306.6827 | 76.6707
WP2_IND-202806 | WP2_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP2 | Indirect | Indirect | Indirect Costs | 2028-06-30 | 2028/29 | Straight-line | 80% | 383.3533 | 306.6827 | 76.6707 | 0 | 383.3533 | 306.6827 | 76.6707
WP2_IND-202807 | WP2_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP2 | Indirect | Indirect | Indirect Costs | 2028-07-31 | 2028/29 | Straight-line | 80% | 383.3533 | 306.6827 | 76.6707 | 0 | 383.3533 | 306.6827 | 76.6707
WP2_IND-202808 | WP2_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP2 | Indirect | Indirect | Indirect Costs | 2028-08-31 | 2028/29 | Straight-line | 80% | 383.3533 | 306.6827 | 76.6707 | 0 | 383.3533 | 306.6827 | 76.6707
WP2_IND-202809 | WP2_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP2 | Indirect | Indirect | Indirect Costs | 2028-09-30 | 2028/29 | Straight-line | 80% | 383.3533 | 306.6827 | 76.6707 | 0 | 383.3533 | 306.6827 | 76.6707
WP2_IND-202810 | WP2_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP2 | Indirect | Indirect | Indirect Costs | 2028-10-31 | 2028/29 | Straight-line | 80% | 383.3533 | 306.6827 | 76.6707 | 0 | 383.3533 | 306.6827 | 76.6707
WP2_IND-202811 | WP2_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP2 | Indirect | Indirect | Indirect Costs | 2028-11-30 | 2028/29 | Straight-line | 80% | 383.3533 | 306.6827 | 76.6707 | 0 | 383.3533 | 306.6827 | 76.6707
WP2_IND-202812 | WP2_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP2 | Indirect | Indirect | Indirect Costs | 2028-12-31 | 2028/29 | Straight-line | 80% | 383.3533 | 306.6827 | 76.6707 | 0 | 383.3533 | 306.6827 | 76.6707
WP2_IND-202901 | WP2_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP2 | Indirect | Indirect | Indirect Costs | 2029-01-31 | 2028/29 | Straight-line | 80% | 383.3533 | 306.6827 | 76.6707 | 0 | 383.3533 | 306.6827 | 76.6707
WP2_IND-202902 | WP2_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP2 | Indirect | Indirect | Indirect Costs | 2029-02-28 | 2028/29 | Straight-line | 80% | 383.3533 | 306.6827 | 76.6707 | 0 | 383.3533 | 306.6827 | 76.6707
WP2_IND-202903 | WP2_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP2 | Indirect | Indirect | Indirect Costs | 2029-03-31 | 2028/29 | Straight-line | 80% | 383.3533 | 306.6827 | 76.6707 | 0 | 383.3533 | 306.6827 | 76.6707
WP2_EST-202604 | WP2_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP2 | Directly Allocated | Estates | Estate Costs | 2026-04-30 | 2026/27 | Straight-line | 80% | 48.8533 | 39.0827 | 9.7707 | 0 | 48.8533 | 39.0827 | 9.7707
WP2_EST-202605 | WP2_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP2 | Directly Allocated | Estates | Estate Costs | 2026-05-31 | 2026/27 | Straight-line | 80% | 48.8533 | 39.0827 | 9.7707 | 0 | 48.8533 | 39.0827 | 9.7707
WP2_EST-202606 | WP2_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP2 | Directly Allocated | Estates | Estate Costs | 2026-06-30 | 2026/27 | Straight-line | 80% | 48.8533 | 39.0827 | 9.7707 | 0 | 48.8533 | 39.0827 | 9.7707
WP2_EST-202607 | WP2_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP2 | Directly Allocated | Estates | Estate Costs | 2026-07-31 | 2026/27 | Straight-line | 80% | 48.8533 | 39.0827 | 9.7707 | 0 | 48.8533 | 39.0827 | 9.7707
WP2_EST-202608 | WP2_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP2 | Directly Allocated | Estates | Estate Costs | 2026-08-31 | 2026/27 | Straight-line | 80% | 48.8533 | 39.0827 | 9.7707 | 0 | 48.8533 | 39.0827 | 9.7707
WP2_EST-202609 | WP2_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP2 | Directly Allocated | Estates | Estate Costs | 2026-09-30 | 2026/27 | Straight-line | 80% | 48.8533 | 39.0827 | 9.7707 | 0 | 48.8533 | 39.0827 | 9.7707
WP2_EST-202610 | WP2_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP2 | Directly Allocated | Estates | Estate Costs | 2026-10-31 | 2026/27 | Straight-line | 80% | 48.8533 | 39.0827 | 9.7707 | 0 | 48.8533 | 39.0827 | 9.7707
WP2_EST-202611 | WP2_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP2 | Directly Allocated | Estates | Estate Costs | 2026-11-30 | 2026/27 | Straight-line | 80% | 48.8533 | 39.0827 | 9.7707 | 0 | 48.8533 | 39.0827 | 9.7707
WP2_EST-202612 | WP2_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP2 | Directly Allocated | Estates | Estate Costs | 2026-12-31 | 2026/27 | Straight-line | 80% | 48.8533 | 39.0827 | 9.7707 | 0 | 48.8533 | 39.0827 | 9.7707
WP2_EST-202701 | WP2_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP2 | Directly Allocated | Estates | Estate Costs | 2027-01-31 | 2026/27 | Straight-line | 80% | 48.8533 | 39.0827 | 9.7707 | 0 | 48.8533 | 39.0827 | 9.7707
WP2_EST-202702 | WP2_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP2 | Directly Allocated | Estates | Estate Costs | 2027-02-28 | 2026/27 | Straight-line | 80% | 48.8533 | 39.0827 | 9.7707 | 0 | 48.8533 | 39.0827 | 9.7707
WP2_EST-202703 | WP2_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP2 | Directly Allocated | Estates | Estate Costs | 2027-03-31 | 2026/27 | Straight-line | 80% | 48.8533 | 39.0827 | 9.7707 | 0 | 48.8533 | 39.0827 | 9.7707
WP2_EST-202704 | WP2_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP2 | Directly Allocated | Estates | Estate Costs | 2027-04-30 | 2027/28 | Straight-line | 80% | 48.8533 | 39.0827 | 9.7707 | 0 | 48.8533 | 39.0827 | 9.7707
WP2_EST-202705 | WP2_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP2 | Directly Allocated | Estates | Estate Costs | 2027-05-31 | 2027/28 | Straight-line | 80% | 48.8533 | 39.0827 | 9.7707 | 0 | 48.8533 | 39.0827 | 9.7707
WP2_EST-202706 | WP2_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP2 | Directly Allocated | Estates | Estate Costs | 2027-06-30 | 2027/28 | Straight-line | 80% | 48.8533 | 39.0827 | 9.7707 | 0 | 48.8533 | 39.0827 | 9.7707
WP2_EST-202707 | WP2_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP2 | Directly Allocated | Estates | Estate Costs | 2027-07-31 | 2027/28 | Straight-line | 80% | 48.8533 | 39.0827 | 9.7707 | 0 | 48.8533 | 39.0827 | 9.7707
WP2_EST-202708 | WP2_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP2 | Directly Allocated | Estates | Estate Costs | 2027-08-31 | 2027/28 | Straight-line | 80% | 48.8533 | 39.0827 | 9.7707 | 0 | 48.8533 | 39.0827 | 9.7707
WP2_EST-202709 | WP2_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP2 | Directly Allocated | Estates | Estate Costs | 2027-09-30 | 2027/28 | Straight-line | 80% | 48.8533 | 39.0827 | 9.7707 | 0 | 48.8533 | 39.0827 | 9.7707
WP2_EST-202710 | WP2_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP2 | Directly Allocated | Estates | Estate Costs | 2027-10-31 | 2027/28 | Straight-line | 80% | 48.8533 | 39.0827 | 9.7707 | 0 | 48.8533 | 39.0827 | 9.7707
WP2_EST-202711 | WP2_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP2 | Directly Allocated | Estates | Estate Costs | 2027-11-30 | 2027/28 | Straight-line | 80% | 48.8533 | 39.0827 | 9.7707 | 0 | 48.8533 | 39.0827 | 9.7707
WP2_EST-202712 | WP2_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP2 | Directly Allocated | Estates | Estate Costs | 2027-12-31 | 2027/28 | Straight-line | 80% | 48.8533 | 39.0827 | 9.7707 | 0 | 48.8533 | 39.0827 | 9.7707
WP2_EST-202801 | WP2_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP2 | Directly Allocated | Estates | Estate Costs | 2028-01-31 | 2027/28 | Straight-line | 80% | 48.8533 | 39.0827 | 9.7707 | 0 | 48.8533 | 39.0827 | 9.7707
WP2_EST-202802 | WP2_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP2 | Directly Allocated | Estates | Estate Costs | 2028-02-29 | 2027/28 | Straight-line | 80% | 48.8533 | 39.0827 | 9.7707 | 0 | 48.8533 | 39.0827 | 9.7707
WP2_EST-202803 | WP2_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP2 | Directly Allocated | Estates | Estate Costs | 2028-03-31 | 2027/28 | Straight-line | 80% | 48.8533 | 39.0827 | 9.7707 | 0 | 48.8533 | 39.0827 | 9.7707
WP2_EST-202804 | WP2_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP2 | Directly Allocated | Estates | Estate Costs | 2028-04-30 | 2028/29 | Straight-line | 80% | 48.8533 | 39.0827 | 9.7707 | 0 | 48.8533 | 39.0827 | 9.7707
WP2_EST-202805 | WP2_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP2 | Directly Allocated | Estates | Estate Costs | 2028-05-31 | 2028/29 | Straight-line | 80% | 48.8533 | 39.0827 | 9.7707 | 0 | 48.8533 | 39.0827 | 9.7707
WP2_EST-202806 | WP2_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP2 | Directly Allocated | Estates | Estate Costs | 2028-06-30 | 2028/29 | Straight-line | 80% | 48.8533 | 39.0827 | 9.7707 | 0 | 48.8533 | 39.0827 | 9.7707
WP2_EST-202807 | WP2_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP2 | Directly Allocated | Estates | Estate Costs | 2028-07-31 | 2028/29 | Straight-line | 80% | 48.8533 | 39.0827 | 9.7707 | 0 | 48.8533 | 39.0827 | 9.7707
WP2_EST-202808 | WP2_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP2 | Directly Allocated | Estates | Estate Costs | 2028-08-31 | 2028/29 | Straight-line | 80% | 48.8533 | 39.0827 | 9.7707 | 0 | 48.8533 | 39.0827 | 9.7707
WP2_EST-202809 | WP2_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP2 | Directly Allocated | Estates | Estate Costs | 2028-09-30 | 2028/29 | Straight-line | 80% | 48.8533 | 39.0827 | 9.7707 | 0 | 48.8533 | 39.0827 | 9.7707
WP2_EST-202810 | WP2_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP2 | Directly Allocated | Estates | Estate Costs | 2028-10-31 | 2028/29 | Straight-line | 80% | 48.8533 | 39.0827 | 9.7707 | 0 | 48.8533 | 39.0827 | 9.7707
WP2_EST-202811 | WP2_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP2 | Directly Allocated | Estates | Estate Costs | 2028-11-30 | 2028/29 | Straight-line | 80% | 48.8533 | 39.0827 | 9.7707 | 0 | 48.8533 | 39.0827 | 9.7707
WP2_EST-202812 | WP2_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP2 | Directly Allocated | Estates | Estate Costs | 2028-12-31 | 2028/29 | Straight-line | 80% | 48.8533 | 39.0827 | 9.7707 | 0 | 48.8533 | 39.0827 | 9.7707
WP2_EST-202901 | WP2_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP2 | Directly Allocated | Estates | Estate Costs | 2029-01-31 | 2028/29 | Straight-line | 80% | 48.8533 | 39.0827 | 9.7707 | 0 | 48.8533 | 39.0827 | 9.7707
WP2_EST-202902 | WP2_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP2 | Directly Allocated | Estates | Estate Costs | 2029-02-28 | 2028/29 | Straight-line | 80% | 48.8533 | 39.0827 | 9.7707 | 0 | 48.8533 | 39.0827 | 9.7707
WP2_EST-202903 | WP2_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP2 | Directly Allocated | Estates | Estate Costs | 2029-03-31 | 2028/29 | Straight-line | 80% | 48.8533 | 39.0827 | 9.7707 | 0 | 48.8533 | 39.0827 | 9.7707
WP3_S01-202604 | WP3_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | 2026-04-30 | 2026/27 | Straight-line | 80% | 261.6667 | 209.3333 | 52.3333 | 0 | 261.6667 | 209.3333 | 52.3333
WP3_S01-202605 | WP3_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | 2026-05-31 | 2026/27 | Straight-line | 80% | 261.6667 | 209.3333 | 52.3333 | 0 | 261.6667 | 209.3333 | 52.3333
WP3_S01-202606 | WP3_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | 2026-06-30 | 2026/27 | Straight-line | 80% | 261.6667 | 209.3333 | 52.3333 | 0 | 261.6667 | 209.3333 | 52.3333
WP3_S01-202607 | WP3_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | 2026-07-31 | 2026/27 | Straight-line | 80% | 261.6667 | 209.3333 | 52.3333 | 0 | 261.6667 | 209.3333 | 52.3333
WP3_S01-202608 | WP3_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | 2026-08-31 | 2026/27 | Straight-line | 80% | 261.6667 | 209.3333 | 52.3333 | 0 | 261.6667 | 209.3333 | 52.3333
WP3_S01-202609 | WP3_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | 2026-09-30 | 2026/27 | Straight-line | 80% | 261.6667 | 209.3333 | 52.3333 | 0 | 261.6667 | 209.3333 | 52.3333
WP3_S01-202610 | WP3_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | 2026-10-31 | 2026/27 | Straight-line | 80% | 261.6667 | 209.3333 | 52.3333 | 0 | 261.6667 | 209.3333 | 52.3333
WP3_S01-202611 | WP3_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | 2026-11-30 | 2026/27 | Straight-line | 80% | 261.6667 | 209.3333 | 52.3333 | 0 | 261.6667 | 209.3333 | 52.3333
WP3_S01-202612 | WP3_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | 2026-12-31 | 2026/27 | Straight-line | 80% | 261.6667 | 209.3333 | 52.3333 | 0 | 261.6667 | 209.3333 | 52.3333
WP3_S01-202701 | WP3_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | 2027-01-31 | 2026/27 | Straight-line | 80% | 261.6667 | 209.3333 | 52.3333 | 0 | 261.6667 | 209.3333 | 52.3333
WP3_S01-202702 | WP3_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | 2027-02-28 | 2026/27 | Straight-line | 80% | 261.6667 | 209.3333 | 52.3333 | 0 | 261.6667 | 209.3333 | 52.3333
WP3_S01-202703 | WP3_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | 2027-03-31 | 2026/27 | Straight-line | 80% | 261.6667 | 209.3333 | 52.3333 | 0 | 261.6667 | 209.3333 | 52.3333
WP3_S01-202704 | WP3_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | 2027-04-30 | 2027/28 | Straight-line | 80% | 261.6667 | 209.3333 | 52.3333 | 0 | 261.6667 | 209.3333 | 52.3333
WP3_S01-202705 | WP3_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | 2027-05-31 | 2027/28 | Straight-line | 80% | 261.6667 | 209.3333 | 52.3333 | 0 | 261.6667 | 209.3333 | 52.3333
WP3_S01-202706 | WP3_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | 2027-06-30 | 2027/28 | Straight-line | 80% | 261.6667 | 209.3333 | 52.3333 | 0 | 261.6667 | 209.3333 | 52.3333
WP3_S01-202707 | WP3_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | 2027-07-31 | 2027/28 | Straight-line | 80% | 261.6667 | 209.3333 | 52.3333 | 0 | 261.6667 | 209.3333 | 52.3333
WP3_S01-202708 | WP3_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | 2027-08-31 | 2027/28 | Straight-line | 80% | 261.6667 | 209.3333 | 52.3333 | 0 | 261.6667 | 209.3333 | 52.3333
WP3_S01-202709 | WP3_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | 2027-09-30 | 2027/28 | Straight-line | 80% | 261.6667 | 209.3333 | 52.3333 | 0 | 261.6667 | 209.3333 | 52.3333
WP3_S01-202710 | WP3_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | 2027-10-31 | 2027/28 | Straight-line | 80% | 261.6667 | 209.3333 | 52.3333 | 0 | 261.6667 | 209.3333 | 52.3333
WP3_S01-202711 | WP3_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | 2027-11-30 | 2027/28 | Straight-line | 80% | 261.6667 | 209.3333 | 52.3333 | 0 | 261.6667 | 209.3333 | 52.3333
WP3_S01-202712 | WP3_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | 2027-12-31 | 2027/28 | Straight-line | 80% | 261.6667 | 209.3333 | 52.3333 | 0 | 261.6667 | 209.3333 | 52.3333
WP3_S01-202801 | WP3_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | 2028-01-31 | 2027/28 | Straight-line | 80% | 261.6667 | 209.3333 | 52.3333 | 0 | 261.6667 | 209.3333 | 52.3333
WP3_S01-202802 | WP3_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | 2028-02-29 | 2027/28 | Straight-line | 80% | 261.6667 | 209.3333 | 52.3333 | 0 | 261.6667 | 209.3333 | 52.3333
WP3_S01-202803 | WP3_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | 2028-03-31 | 2027/28 | Straight-line | 80% | 261.6667 | 209.3333 | 52.3333 | 0 | 261.6667 | 209.3333 | 52.3333
WP3_S01-202804 | WP3_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | 2028-04-30 | 2028/29 | Straight-line | 80% | 261.6667 | 209.3333 | 52.3333 | 0 | 261.6667 | 209.3333 | 52.3333
WP3_S01-202805 | WP3_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | 2028-05-31 | 2028/29 | Straight-line | 80% | 261.6667 | 209.3333 | 52.3333 | 0 | 261.6667 | 209.3333 | 52.3333
WP3_S01-202806 | WP3_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | 2028-06-30 | 2028/29 | Straight-line | 80% | 261.6667 | 209.3333 | 52.3333 | 0 | 261.6667 | 209.3333 | 52.3333
WP3_S01-202807 | WP3_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | 2028-07-31 | 2028/29 | Straight-line | 80% | 261.6667 | 209.3333 | 52.3333 | 0 | 261.6667 | 209.3333 | 52.3333
WP3_S01-202808 | WP3_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | 2028-08-31 | 2028/29 | Straight-line | 80% | 261.6667 | 209.3333 | 52.3333 | 0 | 261.6667 | 209.3333 | 52.3333
WP3_S01-202809 | WP3_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | 2028-09-30 | 2028/29 | Straight-line | 80% | 261.6667 | 209.3333 | 52.3333 | 0 | 261.6667 | 209.3333 | 52.3333
WP3_S01-202810 | WP3_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | 2028-10-31 | 2028/29 | Straight-line | 80% | 261.6667 | 209.3333 | 52.3333 | 0 | 261.6667 | 209.3333 | 52.3333
WP3_S01-202811 | WP3_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | 2028-11-30 | 2028/29 | Straight-line | 80% | 261.6667 | 209.3333 | 52.3333 | 0 | 261.6667 | 209.3333 | 52.3333
WP3_S01-202812 | WP3_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | 2028-12-31 | 2028/29 | Straight-line | 80% | 261.6667 | 209.3333 | 52.3333 | 0 | 261.6667 | 209.3333 | 52.3333
WP3_S01-202901 | WP3_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | 2029-01-31 | 2028/29 | Straight-line | 80% | 261.6667 | 209.3333 | 52.3333 | 0 | 261.6667 | 209.3333 | 52.3333
WP3_S01-202902 | WP3_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | 2029-02-28 | 2028/29 | Straight-line | 80% | 261.6667 | 209.3333 | 52.3333 | 0 | 261.6667 | 209.3333 | 52.3333
WP3_S01-202903 | WP3_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | 2029-03-31 | 2028/29 | Straight-line | 80% | 261.6667 | 209.3333 | 52.3333 | 0 | 261.6667 | 209.3333 | 52.3333
WP3_S02-202604 | WP3_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | 2026-04-30 | 2026/27 | Straight-line | 80% | 120.625 | 96.5 | 24.125 | 0 | 120.625 | 96.5 | 24.125
WP3_S02-202605 | WP3_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | 2026-05-31 | 2026/27 | Straight-line | 80% | 120.625 | 96.5 | 24.125 | 0 | 120.625 | 96.5 | 24.125
WP3_S02-202606 | WP3_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | 2026-06-30 | 2026/27 | Straight-line | 80% | 120.625 | 96.5 | 24.125 | 0 | 120.625 | 96.5 | 24.125
WP3_S02-202607 | WP3_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | 2026-07-31 | 2026/27 | Straight-line | 80% | 120.625 | 96.5 | 24.125 | 0 | 120.625 | 96.5 | 24.125
WP3_S02-202608 | WP3_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | 2026-08-31 | 2026/27 | Straight-line | 80% | 120.625 | 96.5 | 24.125 | 0 | 120.625 | 96.5 | 24.125
WP3_S02-202609 | WP3_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | 2026-09-30 | 2026/27 | Straight-line | 80% | 120.625 | 96.5 | 24.125 | 0 | 120.625 | 96.5 | 24.125
WP3_S02-202610 | WP3_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | 2026-10-31 | 2026/27 | Straight-line | 80% | 120.625 | 96.5 | 24.125 | 0 | 120.625 | 96.5 | 24.125
WP3_S02-202611 | WP3_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | 2026-11-30 | 2026/27 | Straight-line | 80% | 120.625 | 96.5 | 24.125 | 0 | 120.625 | 96.5 | 24.125
WP3_S02-202612 | WP3_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | 2026-12-31 | 2026/27 | Straight-line | 80% | 120.625 | 96.5 | 24.125 | 0 | 120.625 | 96.5 | 24.125
WP3_S02-202701 | WP3_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | 2027-01-31 | 2026/27 | Straight-line | 80% | 120.625 | 96.5 | 24.125 | 0 | 120.625 | 96.5 | 24.125
WP3_S02-202702 | WP3_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | 2027-02-28 | 2026/27 | Straight-line | 80% | 120.625 | 96.5 | 24.125 | 0 | 120.625 | 96.5 | 24.125
WP3_S02-202703 | WP3_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | 2027-03-31 | 2026/27 | Straight-line | 80% | 120.625 | 96.5 | 24.125 | 0 | 120.625 | 96.5 | 24.125
WP3_S02-202704 | WP3_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | 2027-04-30 | 2027/28 | Straight-line | 80% | 120.625 | 96.5 | 24.125 | 0 | 120.625 | 96.5 | 24.125
WP3_S02-202705 | WP3_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | 2027-05-31 | 2027/28 | Straight-line | 80% | 120.625 | 96.5 | 24.125 | 0 | 120.625 | 96.5 | 24.125
WP3_S02-202706 | WP3_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | 2027-06-30 | 2027/28 | Straight-line | 80% | 120.625 | 96.5 | 24.125 | 0 | 120.625 | 96.5 | 24.125
WP3_S02-202707 | WP3_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | 2027-07-31 | 2027/28 | Straight-line | 80% | 120.625 | 96.5 | 24.125 | 0 | 120.625 | 96.5 | 24.125
WP3_S02-202708 | WP3_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | 2027-08-31 | 2027/28 | Straight-line | 80% | 120.625 | 96.5 | 24.125 | 0 | 120.625 | 96.5 | 24.125
WP3_S02-202709 | WP3_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | 2027-09-30 | 2027/28 | Straight-line | 80% | 120.625 | 96.5 | 24.125 | 0 | 120.625 | 96.5 | 24.125
WP3_S02-202710 | WP3_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | 2027-10-31 | 2027/28 | Straight-line | 80% | 120.625 | 96.5 | 24.125 | 0 | 120.625 | 96.5 | 24.125
WP3_S02-202711 | WP3_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | 2027-11-30 | 2027/28 | Straight-line | 80% | 120.625 | 96.5 | 24.125 | 0 | 120.625 | 96.5 | 24.125
WP3_S02-202712 | WP3_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | 2027-12-31 | 2027/28 | Straight-line | 80% | 120.625 | 96.5 | 24.125 | 0 | 120.625 | 96.5 | 24.125
WP3_S02-202801 | WP3_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | 2028-01-31 | 2027/28 | Straight-line | 80% | 120.625 | 96.5 | 24.125 | 0 | 120.625 | 96.5 | 24.125
WP3_S02-202802 | WP3_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | 2028-02-29 | 2027/28 | Straight-line | 80% | 120.625 | 96.5 | 24.125 | 0 | 120.625 | 96.5 | 24.125
WP3_S02-202803 | WP3_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | 2028-03-31 | 2027/28 | Straight-line | 80% | 120.625 | 96.5 | 24.125 | 0 | 120.625 | 96.5 | 24.125
WP3_S02-202804 | WP3_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | 2028-04-30 | 2028/29 | Straight-line | 80% | 120.625 | 96.5 | 24.125 | 0 | 120.625 | 96.5 | 24.125
WP3_S02-202805 | WP3_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | 2028-05-31 | 2028/29 | Straight-line | 80% | 120.625 | 96.5 | 24.125 | 0 | 120.625 | 96.5 | 24.125
WP3_S02-202806 | WP3_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | 2028-06-30 | 2028/29 | Straight-line | 80% | 120.625 | 96.5 | 24.125 | 0 | 120.625 | 96.5 | 24.125
WP3_S02-202807 | WP3_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | 2028-07-31 | 2028/29 | Straight-line | 80% | 120.625 | 96.5 | 24.125 | 0 | 120.625 | 96.5 | 24.125
WP3_S02-202808 | WP3_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | 2028-08-31 | 2028/29 | Straight-line | 80% | 120.625 | 96.5 | 24.125 | 0 | 120.625 | 96.5 | 24.125
WP3_S02-202809 | WP3_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | 2028-09-30 | 2028/29 | Straight-line | 80% | 120.625 | 96.5 | 24.125 | 0 | 120.625 | 96.5 | 24.125
WP3_S02-202810 | WP3_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | 2028-10-31 | 2028/29 | Straight-line | 80% | 120.625 | 96.5 | 24.125 | 0 | 120.625 | 96.5 | 24.125
WP3_S02-202811 | WP3_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | 2028-11-30 | 2028/29 | Straight-line | 80% | 120.625 | 96.5 | 24.125 | 0 | 120.625 | 96.5 | 24.125
WP3_S02-202812 | WP3_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | 2028-12-31 | 2028/29 | Straight-line | 80% | 120.625 | 96.5 | 24.125 | 0 | 120.625 | 96.5 | 24.125
WP3_S02-202901 | WP3_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | 2029-01-31 | 2028/29 | Straight-line | 80% | 120.625 | 96.5 | 24.125 | 0 | 120.625 | 96.5 | 24.125
WP3_S02-202902 | WP3_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | 2029-02-28 | 2028/29 | Straight-line | 80% | 120.625 | 96.5 | 24.125 | 0 | 120.625 | 96.5 | 24.125
WP3_S02-202903 | WP3_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | 2029-03-31 | 2028/29 | Straight-line | 80% | 120.625 | 96.5 | 24.125 | 0 | 120.625 | 96.5 | 24.125
WP3_S03-202604 | WP3_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | 2026-04-30 | 2026/27 | Straight-line | 80% | 123.75 | 99 | 24.75 | 0 | 123.75 | 99 | 24.75
WP3_S03-202605 | WP3_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | 2026-05-31 | 2026/27 | Straight-line | 80% | 123.75 | 99 | 24.75 | 0 | 123.75 | 99 | 24.75
WP3_S03-202606 | WP3_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | 2026-06-30 | 2026/27 | Straight-line | 80% | 123.75 | 99 | 24.75 | 0 | 123.75 | 99 | 24.75
WP3_S03-202607 | WP3_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | 2026-07-31 | 2026/27 | Straight-line | 80% | 123.75 | 99 | 24.75 | 0 | 123.75 | 99 | 24.75
WP3_S03-202608 | WP3_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | 2026-08-31 | 2026/27 | Straight-line | 80% | 123.75 | 99 | 24.75 | 0 | 123.75 | 99 | 24.75
WP3_S03-202609 | WP3_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | 2026-09-30 | 2026/27 | Straight-line | 80% | 123.75 | 99 | 24.75 | 0 | 123.75 | 99 | 24.75
WP3_S03-202610 | WP3_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | 2026-10-31 | 2026/27 | Straight-line | 80% | 123.75 | 99 | 24.75 | 0 | 123.75 | 99 | 24.75
WP3_S03-202611 | WP3_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | 2026-11-30 | 2026/27 | Straight-line | 80% | 123.75 | 99 | 24.75 | 0 | 123.75 | 99 | 24.75
WP3_S03-202612 | WP3_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | 2026-12-31 | 2026/27 | Straight-line | 80% | 123.75 | 99 | 24.75 | 0 | 123.75 | 99 | 24.75
WP3_S03-202701 | WP3_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | 2027-01-31 | 2026/27 | Straight-line | 80% | 123.75 | 99 | 24.75 | 0 | 123.75 | 99 | 24.75
WP3_S03-202702 | WP3_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | 2027-02-28 | 2026/27 | Straight-line | 80% | 123.75 | 99 | 24.75 | 0 | 123.75 | 99 | 24.75
WP3_S03-202703 | WP3_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | 2027-03-31 | 2026/27 | Straight-line | 80% | 123.75 | 99 | 24.75 | 0 | 123.75 | 99 | 24.75
WP3_S03-202704 | WP3_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | 2027-04-30 | 2027/28 | Straight-line | 80% | 123.75 | 99 | 24.75 | 0 | 123.75 | 99 | 24.75
WP3_S03-202705 | WP3_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | 2027-05-31 | 2027/28 | Straight-line | 80% | 123.75 | 99 | 24.75 | 0 | 123.75 | 99 | 24.75
WP3_S03-202706 | WP3_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | 2027-06-30 | 2027/28 | Straight-line | 80% | 123.75 | 99 | 24.75 | 0 | 123.75 | 99 | 24.75
WP3_S03-202707 | WP3_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | 2027-07-31 | 2027/28 | Straight-line | 80% | 123.75 | 99 | 24.75 | 0 | 123.75 | 99 | 24.75
WP3_S03-202708 | WP3_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | 2027-08-31 | 2027/28 | Straight-line | 80% | 123.75 | 99 | 24.75 | 0 | 123.75 | 99 | 24.75
WP3_S03-202709 | WP3_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | 2027-09-30 | 2027/28 | Straight-line | 80% | 123.75 | 99 | 24.75 | 0 | 123.75 | 99 | 24.75
WP3_S03-202710 | WP3_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | 2027-10-31 | 2027/28 | Straight-line | 80% | 123.75 | 99 | 24.75 | 0 | 123.75 | 99 | 24.75
WP3_S03-202711 | WP3_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | 2027-11-30 | 2027/28 | Straight-line | 80% | 123.75 | 99 | 24.75 | 0 | 123.75 | 99 | 24.75
WP3_S03-202712 | WP3_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | 2027-12-31 | 2027/28 | Straight-line | 80% | 123.75 | 99 | 24.75 | 0 | 123.75 | 99 | 24.75
WP3_S03-202801 | WP3_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | 2028-01-31 | 2027/28 | Straight-line | 80% | 123.75 | 99 | 24.75 | 0 | 123.75 | 99 | 24.75
WP3_S03-202802 | WP3_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | 2028-02-29 | 2027/28 | Straight-line | 80% | 123.75 | 99 | 24.75 | 0 | 123.75 | 99 | 24.75
WP3_S03-202803 | WP3_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | 2028-03-31 | 2027/28 | Straight-line | 80% | 123.75 | 99 | 24.75 | 0 | 123.75 | 99 | 24.75
WP3_S03-202804 | WP3_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | 2028-04-30 | 2028/29 | Straight-line | 80% | 123.75 | 99 | 24.75 | 0 | 123.75 | 99 | 24.75
WP3_S03-202805 | WP3_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | 2028-05-31 | 2028/29 | Straight-line | 80% | 123.75 | 99 | 24.75 | 0 | 123.75 | 99 | 24.75
WP3_S03-202806 | WP3_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | 2028-06-30 | 2028/29 | Straight-line | 80% | 123.75 | 99 | 24.75 | 0 | 123.75 | 99 | 24.75
WP3_S03-202807 | WP3_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | 2028-07-31 | 2028/29 | Straight-line | 80% | 123.75 | 99 | 24.75 | 0 | 123.75 | 99 | 24.75
WP3_S03-202808 | WP3_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | 2028-08-31 | 2028/29 | Straight-line | 80% | 123.75 | 99 | 24.75 | 0 | 123.75 | 99 | 24.75
WP3_S03-202809 | WP3_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | 2028-09-30 | 2028/29 | Straight-line | 80% | 123.75 | 99 | 24.75 | 0 | 123.75 | 99 | 24.75
WP3_S03-202810 | WP3_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | 2028-10-31 | 2028/29 | Straight-line | 80% | 123.75 | 99 | 24.75 | 0 | 123.75 | 99 | 24.75
WP3_S03-202811 | WP3_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | 2028-11-30 | 2028/29 | Straight-line | 80% | 123.75 | 99 | 24.75 | 0 | 123.75 | 99 | 24.75
WP3_S03-202812 | WP3_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | 2028-12-31 | 2028/29 | Straight-line | 80% | 123.75 | 99 | 24.75 | 0 | 123.75 | 99 | 24.75
WP3_S03-202901 | WP3_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | 2029-01-31 | 2028/29 | Straight-line | 80% | 123.75 | 99 | 24.75 | 0 | 123.75 | 99 | 24.75
WP3_S03-202902 | WP3_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | 2029-02-28 | 2028/29 | Straight-line | 80% | 123.75 | 99 | 24.75 | 0 | 123.75 | 99 | 24.75
WP3_S03-202903 | WP3_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | 2029-03-31 | 2028/29 | Straight-line | 80% | 123.75 | 99 | 24.75 | 0 | 123.75 | 99 | 24.75
WP3_TRAVEL-202604 | WP3_TRAVEL | RUSI - London-team and Latin America stakeholder travel/subsistence | WP3 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | 2026-04-30 | 2026/27 | Straight-line | 80% | 333.3333 | 266.6667 | 66.6667 | 0 | 333.3333 | 266.6667 | 66.6667
WP3_TRAVEL-202605 | WP3_TRAVEL | RUSI - London-team and Latin America stakeholder travel/subsistence | WP3 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | 2026-05-31 | 2026/27 | Straight-line | 80% | 333.3333 | 266.6667 | 66.6667 | 0 | 333.3333 | 266.6667 | 66.6667
WP3_TRAVEL-202606 | WP3_TRAVEL | RUSI - London-team and Latin America stakeholder travel/subsistence | WP3 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | 2026-06-30 | 2026/27 | Straight-line | 80% | 333.3333 | 266.6667 | 66.6667 | 0 | 333.3333 | 266.6667 | 66.6667
WP3_TRAVEL-202607 | WP3_TRAVEL | RUSI - London-team and Latin America stakeholder travel/subsistence | WP3 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | 2026-07-31 | 2026/27 | Straight-line | 80% | 333.3333 | 266.6667 | 66.6667 | 0 | 333.3333 | 266.6667 | 66.6667
WP3_TRAVEL-202608 | WP3_TRAVEL | RUSI - London-team and Latin America stakeholder travel/subsistence | WP3 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | 2026-08-31 | 2026/27 | Straight-line | 80% | 333.3333 | 266.6667 | 66.6667 | 0 | 333.3333 | 266.6667 | 66.6667
WP3_TRAVEL-202609 | WP3_TRAVEL | RUSI - London-team and Latin America stakeholder travel/subsistence | WP3 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | 2026-09-30 | 2026/27 | Straight-line | 80% | 333.3333 | 266.6667 | 66.6667 | 0 | 333.3333 | 266.6667 | 66.6667
WP3_TRAVEL-202610 | WP3_TRAVEL | RUSI - London-team and Latin America stakeholder travel/subsistence | WP3 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | 2026-10-31 | 2026/27 | Straight-line | 80% | 333.3333 | 266.6667 | 66.6667 | 0 | 333.3333 | 266.6667 | 66.6667
WP3_TRAVEL-202611 | WP3_TRAVEL | RUSI - London-team and Latin America stakeholder travel/subsistence | WP3 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | 2026-11-30 | 2026/27 | Straight-line | 80% | 333.3333 | 266.6667 | 66.6667 | 0 | 333.3333 | 266.6667 | 66.6667
WP3_TRAVEL-202612 | WP3_TRAVEL | RUSI - London-team and Latin America stakeholder travel/subsistence | WP3 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | 2026-12-31 | 2026/27 | Straight-line | 80% | 333.3333 | 266.6667 | 66.6667 | 0 | 333.3333 | 266.6667 | 66.6667
WP3_TRAVEL-202701 | WP3_TRAVEL | RUSI - London-team and Latin America stakeholder travel/subsistence | WP3 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | 2027-01-31 | 2026/27 | Straight-line | 80% | 333.3333 | 266.6667 | 66.6667 | 0 | 333.3333 | 266.6667 | 66.6667
WP3_TRAVEL-202702 | WP3_TRAVEL | RUSI - London-team and Latin America stakeholder travel/subsistence | WP3 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | 2027-02-28 | 2026/27 | Straight-line | 80% | 333.3333 | 266.6667 | 66.6667 | 0 | 333.3333 | 266.6667 | 66.6667
WP3_TRAVEL-202703 | WP3_TRAVEL | RUSI - London-team and Latin America stakeholder travel/subsistence | WP3 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | 2027-03-31 | 2026/27 | Straight-line | 80% | 333.3333 | 266.6667 | 66.6667 | 0 | 333.3333 | 266.6667 | 66.6667
WP3_TRAVEL-202704 | WP3_TRAVEL | RUSI - London-team and Latin America stakeholder travel/subsistence | WP3 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | 2027-04-30 | 2027/28 | Straight-line | 80% | 333.3333 | 266.6667 | 66.6667 | 0 | 333.3333 | 266.6667 | 66.6667
WP3_TRAVEL-202705 | WP3_TRAVEL | RUSI - London-team and Latin America stakeholder travel/subsistence | WP3 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | 2027-05-31 | 2027/28 | Straight-line | 80% | 333.3333 | 266.6667 | 66.6667 | 0 | 333.3333 | 266.6667 | 66.6667
WP3_TRAVEL-202706 | WP3_TRAVEL | RUSI - London-team and Latin America stakeholder travel/subsistence | WP3 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | 2027-06-30 | 2027/28 | Straight-line | 80% | 333.3333 | 266.6667 | 66.6667 | 0 | 333.3333 | 266.6667 | 66.6667
WP3_TRAVEL-202707 | WP3_TRAVEL | RUSI - London-team and Latin America stakeholder travel/subsistence | WP3 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | 2027-07-31 | 2027/28 | Straight-line | 80% | 333.3333 | 266.6667 | 66.6667 | 0 | 333.3333 | 266.6667 | 66.6667
WP3_TRAVEL-202708 | WP3_TRAVEL | RUSI - London-team and Latin America stakeholder travel/subsistence | WP3 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | 2027-08-31 | 2027/28 | Straight-line | 80% | 333.3333 | 266.6667 | 66.6667 | 0 | 333.3333 | 266.6667 | 66.6667
WP3_TRAVEL-202709 | WP3_TRAVEL | RUSI - London-team and Latin America stakeholder travel/subsistence | WP3 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | 2027-09-30 | 2027/28 | Straight-line | 80% | 333.3333 | 266.6667 | 66.6667 | 0 | 333.3333 | 266.6667 | 66.6667
WP3_TRAVEL-202710 | WP3_TRAVEL | RUSI - London-team and Latin America stakeholder travel/subsistence | WP3 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | 2027-10-31 | 2027/28 | Straight-line | 80% | 333.3333 | 266.6667 | 66.6667 | 0 | 333.3333 | 266.6667 | 66.6667
WP3_TRAVEL-202711 | WP3_TRAVEL | RUSI - London-team and Latin America stakeholder travel/subsistence | WP3 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | 2027-11-30 | 2027/28 | Straight-line | 80% | 333.3333 | 266.6667 | 66.6667 | 0 | 333.3333 | 266.6667 | 66.6667
WP3_TRAVEL-202712 | WP3_TRAVEL | RUSI - London-team and Latin America stakeholder travel/subsistence | WP3 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | 2027-12-31 | 2027/28 | Straight-line | 80% | 333.3333 | 266.6667 | 66.6667 | 0 | 333.3333 | 266.6667 | 66.6667
WP3_TRAVEL-202801 | WP3_TRAVEL | RUSI - London-team and Latin America stakeholder travel/subsistence | WP3 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | 2028-01-31 | 2027/28 | Straight-line | 80% | 333.3333 | 266.6667 | 66.6667 | 0 | 333.3333 | 266.6667 | 66.6667
WP3_TRAVEL-202802 | WP3_TRAVEL | RUSI - London-team and Latin America stakeholder travel/subsistence | WP3 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | 2028-02-29 | 2027/28 | Straight-line | 80% | 333.3333 | 266.6667 | 66.6667 | 0 | 333.3333 | 266.6667 | 66.6667
WP3_TRAVEL-202803 | WP3_TRAVEL | RUSI - London-team and Latin America stakeholder travel/subsistence | WP3 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | 2028-03-31 | 2027/28 | Straight-line | 80% | 333.3333 | 266.6667 | 66.6667 | 0 | 333.3333 | 266.6667 | 66.6667
WP3_TRAVEL-202804 | WP3_TRAVEL | RUSI - London-team and Latin America stakeholder travel/subsistence | WP3 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | 2028-04-30 | 2028/29 | Straight-line | 80% | 333.3333 | 266.6667 | 66.6667 | 0 | 333.3333 | 266.6667 | 66.6667
WP3_TRAVEL-202805 | WP3_TRAVEL | RUSI - London-team and Latin America stakeholder travel/subsistence | WP3 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | 2028-05-31 | 2028/29 | Straight-line | 80% | 333.3333 | 266.6667 | 66.6667 | 0 | 333.3333 | 266.6667 | 66.6667
WP3_TRAVEL-202806 | WP3_TRAVEL | RUSI - London-team and Latin America stakeholder travel/subsistence | WP3 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | 2028-06-30 | 2028/29 | Straight-line | 80% | 333.3333 | 266.6667 | 66.6667 | 0 | 333.3333 | 266.6667 | 66.6667
WP3_TRAVEL-202807 | WP3_TRAVEL | RUSI - London-team and Latin America stakeholder travel/subsistence | WP3 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | 2028-07-31 | 2028/29 | Straight-line | 80% | 333.3333 | 266.6667 | 66.6667 | 0 | 333.3333 | 266.6667 | 66.6667
WP3_TRAVEL-202808 | WP3_TRAVEL | RUSI - London-team and Latin America stakeholder travel/subsistence | WP3 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | 2028-08-31 | 2028/29 | Straight-line | 80% | 333.3333 | 266.6667 | 66.6667 | 0 | 333.3333 | 266.6667 | 66.6667
WP3_TRAVEL-202809 | WP3_TRAVEL | RUSI - London-team and Latin America stakeholder travel/subsistence | WP3 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | 2028-09-30 | 2028/29 | Straight-line | 80% | 333.3333 | 266.6667 | 66.6667 | 0 | 333.3333 | 266.6667 | 66.6667
WP3_TRAVEL-202810 | WP3_TRAVEL | RUSI - London-team and Latin America stakeholder travel/subsistence | WP3 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | 2028-10-31 | 2028/29 | Straight-line | 80% | 333.3333 | 266.6667 | 66.6667 | 0 | 333.3333 | 266.6667 | 66.6667
WP3_TRAVEL-202811 | WP3_TRAVEL | RUSI - London-team and Latin America stakeholder travel/subsistence | WP3 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | 2028-11-30 | 2028/29 | Straight-line | 80% | 333.3333 | 266.6667 | 66.6667 | 0 | 333.3333 | 266.6667 | 66.6667
WP3_TRAVEL-202812 | WP3_TRAVEL | RUSI - London-team and Latin America stakeholder travel/subsistence | WP3 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | 2028-12-31 | 2028/29 | Straight-line | 80% | 333.3333 | 266.6667 | 66.6667 | 0 | 333.3333 | 266.6667 | 66.6667
WP3_TRAVEL-202901 | WP3_TRAVEL | RUSI - London-team and Latin America stakeholder travel/subsistence | WP3 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | 2029-01-31 | 2028/29 | Straight-line | 80% | 333.3333 | 266.6667 | 66.6667 | 0 | 333.3333 | 266.6667 | 66.6667
WP3_TRAVEL-202902 | WP3_TRAVEL | RUSI - London-team and Latin America stakeholder travel/subsistence | WP3 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | 2029-02-28 | 2028/29 | Straight-line | 80% | 333.3333 | 266.6667 | 66.6667 | 0 | 333.3333 | 266.6667 | 66.6667
WP3_TRAVEL-202903 | WP3_TRAVEL | RUSI - London-team and Latin America stakeholder travel/subsistence | WP3 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | 2029-03-31 | 2028/29 | Straight-line | 80% | 333.3333 | 266.6667 | 66.6667 | 0 | 333.3333 | 266.6667 | 66.6667
WP3_CONSULT-202604 | WP3_CONSULT | RUSI - Latin America-based regional network broker consultant | WP3 | Directly Incurred | Other Directly Incurred | Regional Consultancy | 2026-04-30 | 2026/27 | Straight-line | 80% | 350 | 280 | 70 | 0 | 350 | 280 | 70
WP3_CONSULT-202605 | WP3_CONSULT | RUSI - Latin America-based regional network broker consultant | WP3 | Directly Incurred | Other Directly Incurred | Regional Consultancy | 2026-05-31 | 2026/27 | Straight-line | 80% | 350 | 280 | 70 | 0 | 350 | 280 | 70
WP3_CONSULT-202606 | WP3_CONSULT | RUSI - Latin America-based regional network broker consultant | WP3 | Directly Incurred | Other Directly Incurred | Regional Consultancy | 2026-06-30 | 2026/27 | Straight-line | 80% | 350 | 280 | 70 | 0 | 350 | 280 | 70
WP3_CONSULT-202607 | WP3_CONSULT | RUSI - Latin America-based regional network broker consultant | WP3 | Directly Incurred | Other Directly Incurred | Regional Consultancy | 2026-07-31 | 2026/27 | Straight-line | 80% | 350 | 280 | 70 | 0 | 350 | 280 | 70
WP3_CONSULT-202608 | WP3_CONSULT | RUSI - Latin America-based regional network broker consultant | WP3 | Directly Incurred | Other Directly Incurred | Regional Consultancy | 2026-08-31 | 2026/27 | Straight-line | 80% | 350 | 280 | 70 | 0 | 350 | 280 | 70
WP3_CONSULT-202609 | WP3_CONSULT | RUSI - Latin America-based regional network broker consultant | WP3 | Directly Incurred | Other Directly Incurred | Regional Consultancy | 2026-09-30 | 2026/27 | Straight-line | 80% | 350 | 280 | 70 | 0 | 350 | 280 | 70
WP3_CONSULT-202610 | WP3_CONSULT | RUSI - Latin America-based regional network broker consultant | WP3 | Directly Incurred | Other Directly Incurred | Regional Consultancy | 2026-10-31 | 2026/27 | Straight-line | 80% | 350 | 280 | 70 | 0 | 350 | 280 | 70
WP3_CONSULT-202611 | WP3_CONSULT | RUSI - Latin America-based regional network broker consultant | WP3 | Directly Incurred | Other Directly Incurred | Regional Consultancy | 2026-11-30 | 2026/27 | Straight-line | 80% | 350 | 280 | 70 | 0 | 350 | 280 | 70
WP3_CONSULT-202612 | WP3_CONSULT | RUSI - Latin America-based regional network broker consultant | WP3 | Directly Incurred | Other Directly Incurred | Regional Consultancy | 2026-12-31 | 2026/27 | Straight-line | 80% | 350 | 280 | 70 | 0 | 350 | 280 | 70
WP3_CONSULT-202701 | WP3_CONSULT | RUSI - Latin America-based regional network broker consultant | WP3 | Directly Incurred | Other Directly Incurred | Regional Consultancy | 2027-01-31 | 2026/27 | Straight-line | 80% | 350 | 280 | 70 | 0 | 350 | 280 | 70
WP3_CONSULT-202702 | WP3_CONSULT | RUSI - Latin America-based regional network broker consultant | WP3 | Directly Incurred | Other Directly Incurred | Regional Consultancy | 2027-02-28 | 2026/27 | Straight-line | 80% | 350 | 280 | 70 | 0 | 350 | 280 | 70
WP3_CONSULT-202703 | WP3_CONSULT | RUSI - Latin America-based regional network broker consultant | WP3 | Directly Incurred | Other Directly Incurred | Regional Consultancy | 2027-03-31 | 2026/27 | Straight-line | 80% | 350 | 280 | 70 | 0 | 350 | 280 | 70
WP3_CONSULT-202704 | WP3_CONSULT | RUSI - Latin America-based regional network broker consultant | WP3 | Directly Incurred | Other Directly Incurred | Regional Consultancy | 2027-04-30 | 2027/28 | Straight-line | 80% | 350 | 280 | 70 | 0 | 350 | 280 | 70
WP3_CONSULT-202705 | WP3_CONSULT | RUSI - Latin America-based regional network broker consultant | WP3 | Directly Incurred | Other Directly Incurred | Regional Consultancy | 2027-05-31 | 2027/28 | Straight-line | 80% | 350 | 280 | 70 | 0 | 350 | 280 | 70
WP3_CONSULT-202706 | WP3_CONSULT | RUSI - Latin America-based regional network broker consultant | WP3 | Directly Incurred | Other Directly Incurred | Regional Consultancy | 2027-06-30 | 2027/28 | Straight-line | 80% | 350 | 280 | 70 | 0 | 350 | 280 | 70
WP3_CONSULT-202707 | WP3_CONSULT | RUSI - Latin America-based regional network broker consultant | WP3 | Directly Incurred | Other Directly Incurred | Regional Consultancy | 2027-07-31 | 2027/28 | Straight-line | 80% | 350 | 280 | 70 | 0 | 350 | 280 | 70
WP3_CONSULT-202708 | WP3_CONSULT | RUSI - Latin America-based regional network broker consultant | WP3 | Directly Incurred | Other Directly Incurred | Regional Consultancy | 2027-08-31 | 2027/28 | Straight-line | 80% | 350 | 280 | 70 | 0 | 350 | 280 | 70
WP3_CONSULT-202709 | WP3_CONSULT | RUSI - Latin America-based regional network broker consultant | WP3 | Directly Incurred | Other Directly Incurred | Regional Consultancy | 2027-09-30 | 2027/28 | Straight-line | 80% | 350 | 280 | 70 | 0 | 350 | 280 | 70
WP3_CONSULT-202710 | WP3_CONSULT | RUSI - Latin America-based regional network broker consultant | WP3 | Directly Incurred | Other Directly Incurred | Regional Consultancy | 2027-10-31 | 2027/28 | Straight-line | 80% | 350 | 280 | 70 | 0 | 350 | 280 | 70
WP3_CONSULT-202711 | WP3_CONSULT | RUSI - Latin America-based regional network broker consultant | WP3 | Directly Incurred | Other Directly Incurred | Regional Consultancy | 2027-11-30 | 2027/28 | Straight-line | 80% | 350 | 280 | 70 | 0 | 350 | 280 | 70
WP3_CONSULT-202712 | WP3_CONSULT | RUSI - Latin America-based regional network broker consultant | WP3 | Directly Incurred | Other Directly Incurred | Regional Consultancy | 2027-12-31 | 2027/28 | Straight-line | 80% | 350 | 280 | 70 | 0 | 350 | 280 | 70
WP3_CONSULT-202801 | WP3_CONSULT | RUSI - Latin America-based regional network broker consultant | WP3 | Directly Incurred | Other Directly Incurred | Regional Consultancy | 2028-01-31 | 2027/28 | Straight-line | 80% | 350 | 280 | 70 | 0 | 350 | 280 | 70
WP3_CONSULT-202802 | WP3_CONSULT | RUSI - Latin America-based regional network broker consultant | WP3 | Directly Incurred | Other Directly Incurred | Regional Consultancy | 2028-02-29 | 2027/28 | Straight-line | 80% | 350 | 280 | 70 | 0 | 350 | 280 | 70
WP3_CONSULT-202803 | WP3_CONSULT | RUSI - Latin America-based regional network broker consultant | WP3 | Directly Incurred | Other Directly Incurred | Regional Consultancy | 2028-03-31 | 2027/28 | Straight-line | 80% | 350 | 280 | 70 | 0 | 350 | 280 | 70
WP3_CONSULT-202804 | WP3_CONSULT | RUSI - Latin America-based regional network broker consultant | WP3 | Directly Incurred | Other Directly Incurred | Regional Consultancy | 2028-04-30 | 2028/29 | Straight-line | 80% | 350 | 280 | 70 | 0 | 350 | 280 | 70
WP3_CONSULT-202805 | WP3_CONSULT | RUSI - Latin America-based regional network broker consultant | WP3 | Directly Incurred | Other Directly Incurred | Regional Consultancy | 2028-05-31 | 2028/29 | Straight-line | 80% | 350 | 280 | 70 | 0 | 350 | 280 | 70
WP3_CONSULT-202806 | WP3_CONSULT | RUSI - Latin America-based regional network broker consultant | WP3 | Directly Incurred | Other Directly Incurred | Regional Consultancy | 2028-06-30 | 2028/29 | Straight-line | 80% | 350 | 280 | 70 | 0 | 350 | 280 | 70
WP3_CONSULT-202807 | WP3_CONSULT | RUSI - Latin America-based regional network broker consultant | WP3 | Directly Incurred | Other Directly Incurred | Regional Consultancy | 2028-07-31 | 2028/29 | Straight-line | 80% | 350 | 280 | 70 | 0 | 350 | 280 | 70
WP3_CONSULT-202808 | WP3_CONSULT | RUSI - Latin America-based regional network broker consultant | WP3 | Directly Incurred | Other Directly Incurred | Regional Consultancy | 2028-08-31 | 2028/29 | Straight-line | 80% | 350 | 280 | 70 | 0 | 350 | 280 | 70
WP3_CONSULT-202809 | WP3_CONSULT | RUSI - Latin America-based regional network broker consultant | WP3 | Directly Incurred | Other Directly Incurred | Regional Consultancy | 2028-09-30 | 2028/29 | Straight-line | 80% | 350 | 280 | 70 | 0 | 350 | 280 | 70
WP3_CONSULT-202810 | WP3_CONSULT | RUSI - Latin America-based regional network broker consultant | WP3 | Directly Incurred | Other Directly Incurred | Regional Consultancy | 2028-10-31 | 2028/29 | Straight-line | 80% | 350 | 280 | 70 | 0 | 350 | 280 | 70
WP3_CONSULT-202811 | WP3_CONSULT | RUSI - Latin America-based regional network broker consultant | WP3 | Directly Incurred | Other Directly Incurred | Regional Consultancy | 2028-11-30 | 2028/29 | Straight-line | 80% | 350 | 280 | 70 | 0 | 350 | 280 | 70
WP3_CONSULT-202812 | WP3_CONSULT | RUSI - Latin America-based regional network broker consultant | WP3 | Directly Incurred | Other Directly Incurred | Regional Consultancy | 2028-12-31 | 2028/29 | Straight-line | 80% | 350 | 280 | 70 | 0 | 350 | 280 | 70
WP3_CONSULT-202901 | WP3_CONSULT | RUSI - Latin America-based regional network broker consultant | WP3 | Directly Incurred | Other Directly Incurred | Regional Consultancy | 2029-01-31 | 2028/29 | Straight-line | 80% | 350 | 280 | 70 | 0 | 350 | 280 | 70
WP3_CONSULT-202902 | WP3_CONSULT | RUSI - Latin America-based regional network broker consultant | WP3 | Directly Incurred | Other Directly Incurred | Regional Consultancy | 2029-02-28 | 2028/29 | Straight-line | 80% | 350 | 280 | 70 | 0 | 350 | 280 | 70
WP3_CONSULT-202903 | WP3_CONSULT | RUSI - Latin America-based regional network broker consultant | WP3 | Directly Incurred | Other Directly Incurred | Regional Consultancy | 2029-03-31 | 2028/29 | Straight-line | 80% | 350 | 280 | 70 | 0 | 350 | 280 | 70
WP3_CONF-202604 | WP3_CONF | RUSI - five-day Latin America hub conference (hub to be confirmed) | WP3 | Directly Incurred | Other Directly Incurred | Conferences | 2026-04-30 | 2026/27 | Event month | 80% | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3_CONF-202605 | WP3_CONF | RUSI - five-day Latin America hub conference (hub to be confirmed) | WP3 | Directly Incurred | Other Directly Incurred | Conferences | 2026-05-31 | 2026/27 | Event month | 80% | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3_CONF-202606 | WP3_CONF | RUSI - five-day Latin America hub conference (hub to be confirmed) | WP3 | Directly Incurred | Other Directly Incurred | Conferences | 2026-06-30 | 2026/27 | Event month | 80% | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3_CONF-202607 | WP3_CONF | RUSI - five-day Latin America hub conference (hub to be confirmed) | WP3 | Directly Incurred | Other Directly Incurred | Conferences | 2026-07-31 | 2026/27 | Event month | 80% | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3_CONF-202608 | WP3_CONF | RUSI - five-day Latin America hub conference (hub to be confirmed) | WP3 | Directly Incurred | Other Directly Incurred | Conferences | 2026-08-31 | 2026/27 | Event month | 80% | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3_CONF-202609 | WP3_CONF | RUSI - five-day Latin America hub conference (hub to be confirmed) | WP3 | Directly Incurred | Other Directly Incurred | Conferences | 2026-09-30 | 2026/27 | Event month | 80% | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3_CONF-202610 | WP3_CONF | RUSI - five-day Latin America hub conference (hub to be confirmed) | WP3 | Directly Incurred | Other Directly Incurred | Conferences | 2026-10-31 | 2026/27 | Event month | 80% | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3_CONF-202611 | WP3_CONF | RUSI - five-day Latin America hub conference (hub to be confirmed) | WP3 | Directly Incurred | Other Directly Incurred | Conferences | 2026-11-30 | 2026/27 | Event month | 80% | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3_CONF-202612 | WP3_CONF | RUSI - five-day Latin America hub conference (hub to be confirmed) | WP3 | Directly Incurred | Other Directly Incurred | Conferences | 2026-12-31 | 2026/27 | Event month | 80% | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3_CONF-202701 | WP3_CONF | RUSI - five-day Latin America hub conference (hub to be confirmed) | WP3 | Directly Incurred | Other Directly Incurred | Conferences | 2027-01-31 | 2026/27 | Event month | 80% | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3_CONF-202702 | WP3_CONF | RUSI - five-day Latin America hub conference (hub to be confirmed) | WP3 | Directly Incurred | Other Directly Incurred | Conferences | 2027-02-28 | 2026/27 | Event month | 80% | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3_CONF-202703 | WP3_CONF | RUSI - five-day Latin America hub conference (hub to be confirmed) | WP3 | Directly Incurred | Other Directly Incurred | Conferences | 2027-03-31 | 2026/27 | Event month | 80% | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3_CONF-202704 | WP3_CONF | RUSI - five-day Latin America hub conference (hub to be confirmed) | WP3 | Directly Incurred | Other Directly Incurred | Conferences | 2027-04-30 | 2027/28 | Event month | 80% | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3_CONF-202705 | WP3_CONF | RUSI - five-day Latin America hub conference (hub to be confirmed) | WP3 | Directly Incurred | Other Directly Incurred | Conferences | 2027-05-31 | 2027/28 | Event month | 80% | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3_CONF-202706 | WP3_CONF | RUSI - five-day Latin America hub conference (hub to be confirmed) | WP3 | Directly Incurred | Other Directly Incurred | Conferences | 2027-06-30 | 2027/28 | Event month | 80% | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3_CONF-202707 | WP3_CONF | RUSI - five-day Latin America hub conference (hub to be confirmed) | WP3 | Directly Incurred | Other Directly Incurred | Conferences | 2027-07-31 | 2027/28 | Event month | 80% | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3_CONF-202708 | WP3_CONF | RUSI - five-day Latin America hub conference (hub to be confirmed) | WP3 | Directly Incurred | Other Directly Incurred | Conferences | 2027-08-31 | 2027/28 | Event month | 80% | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3_CONF-202709 | WP3_CONF | RUSI - five-day Latin America hub conference (hub to be confirmed) | WP3 | Directly Incurred | Other Directly Incurred | Conferences | 2027-09-30 | 2027/28 | Event month | 80% | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3_CONF-202710 | WP3_CONF | RUSI - five-day Latin America hub conference (hub to be confirmed) | WP3 | Directly Incurred | Other Directly Incurred | Conferences | 2027-10-31 | 2027/28 | Event month | 80% | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3_CONF-202711 | WP3_CONF | RUSI - five-day Latin America hub conference (hub to be confirmed) | WP3 | Directly Incurred | Other Directly Incurred | Conferences | 2027-11-30 | 2027/28 | Event month | 80% | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3_CONF-202712 | WP3_CONF | RUSI - five-day Latin America hub conference (hub to be confirmed) | WP3 | Directly Incurred | Other Directly Incurred | Conferences | 2027-12-31 | 2027/28 | Event month | 80% | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3_CONF-202801 | WP3_CONF | RUSI - five-day Latin America hub conference (hub to be confirmed) | WP3 | Directly Incurred | Other Directly Incurred | Conferences | 2028-01-31 | 2027/28 | Event month | 80% | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3_CONF-202802 | WP3_CONF | RUSI - five-day Latin America hub conference (hub to be confirmed) | WP3 | Directly Incurred | Other Directly Incurred | Conferences | 2028-02-29 | 2027/28 | Event month | 80% | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3_CONF-202803 | WP3_CONF | RUSI - five-day Latin America hub conference (hub to be confirmed) | WP3 | Directly Incurred | Other Directly Incurred | Conferences | 2028-03-31 | 2027/28 | Event month | 80% | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3_CONF-202804 | WP3_CONF | RUSI - five-day Latin America hub conference (hub to be confirmed) | WP3 | Directly Incurred | Other Directly Incurred | Conferences | 2028-04-30 | 2028/29 | Event month | 80% | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3_CONF-202805 | WP3_CONF | RUSI - five-day Latin America hub conference (hub to be confirmed) | WP3 | Directly Incurred | Other Directly Incurred | Conferences | 2028-05-31 | 2028/29 | Event month | 80% | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3_CONF-202806 | WP3_CONF | RUSI - five-day Latin America hub conference (hub to be confirmed) | WP3 | Directly Incurred | Other Directly Incurred | Conferences | 2028-06-30 | 2028/29 | Event month | 80% | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3_CONF-202807 | WP3_CONF | RUSI - five-day Latin America hub conference (hub to be confirmed) | WP3 | Directly Incurred | Other Directly Incurred | Conferences | 2028-07-31 | 2028/29 | Event month | 80% | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3_CONF-202808 | WP3_CONF | RUSI - five-day Latin America hub conference (hub to be confirmed) | WP3 | Directly Incurred | Other Directly Incurred | Conferences | 2028-08-31 | 2028/29 | Event month | 80% | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3_CONF-202809 | WP3_CONF | RUSI - five-day Latin America hub conference (hub to be confirmed) | WP3 | Directly Incurred | Other Directly Incurred | Conferences | 2028-09-30 | 2028/29 | Event month | 80% | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3_CONF-202810 | WP3_CONF | RUSI - five-day Latin America hub conference (hub to be confirmed) | WP3 | Directly Incurred | Other Directly Incurred | Conferences | 2028-10-31 | 2028/29 | Event month | 80% | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3_CONF-202811 | WP3_CONF | RUSI - five-day Latin America hub conference (hub to be confirmed) | WP3 | Directly Incurred | Other Directly Incurred | Conferences | 2028-11-30 | 2028/29 | Event month | 80% | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3_CONF-202812 | WP3_CONF | RUSI - five-day Latin America hub conference (hub to be confirmed) | WP3 | Directly Incurred | Other Directly Incurred | Conferences | 2028-12-31 | 2028/29 | Event month | 80% | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3_CONF-202901 | WP3_CONF | RUSI - five-day Latin America hub conference (hub to be confirmed) | WP3 | Directly Incurred | Other Directly Incurred | Conferences | 2029-01-31 | 2028/29 | Event month | 80% | 16000 | 12800 | 3200 | 0 | 16000 | 12800 | 3200
WP3_CONF-202902 | WP3_CONF | RUSI - five-day Latin America hub conference (hub to be confirmed) | WP3 | Directly Incurred | Other Directly Incurred | Conferences | 2029-02-28 | 2028/29 | Event month | 80% | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3_CONF-202903 | WP3_CONF | RUSI - five-day Latin America hub conference (hub to be confirmed) | WP3 | Directly Incurred | Other Directly Incurred | Conferences | 2029-03-31 | 2028/29 | Event month | 80% | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3_WORKSHOP-202604 | WP3_WORKSHOP | RUSI - Latin America practitioner-policy-academic workshops | WP3 | Directly Incurred | Other Directly Incurred | Workshops | 2026-04-30 | 2026/27 | Straight-line | 80% | 166.6667 | 133.3333 | 33.3333 | 0 | 166.6667 | 133.3333 | 33.3333
WP3_WORKSHOP-202605 | WP3_WORKSHOP | RUSI - Latin America practitioner-policy-academic workshops | WP3 | Directly Incurred | Other Directly Incurred | Workshops | 2026-05-31 | 2026/27 | Straight-line | 80% | 166.6667 | 133.3333 | 33.3333 | 0 | 166.6667 | 133.3333 | 33.3333
WP3_WORKSHOP-202606 | WP3_WORKSHOP | RUSI - Latin America practitioner-policy-academic workshops | WP3 | Directly Incurred | Other Directly Incurred | Workshops | 2026-06-30 | 2026/27 | Straight-line | 80% | 166.6667 | 133.3333 | 33.3333 | 0 | 166.6667 | 133.3333 | 33.3333
WP3_WORKSHOP-202607 | WP3_WORKSHOP | RUSI - Latin America practitioner-policy-academic workshops | WP3 | Directly Incurred | Other Directly Incurred | Workshops | 2026-07-31 | 2026/27 | Straight-line | 80% | 166.6667 | 133.3333 | 33.3333 | 0 | 166.6667 | 133.3333 | 33.3333
WP3_WORKSHOP-202608 | WP3_WORKSHOP | RUSI - Latin America practitioner-policy-academic workshops | WP3 | Directly Incurred | Other Directly Incurred | Workshops | 2026-08-31 | 2026/27 | Straight-line | 80% | 166.6667 | 133.3333 | 33.3333 | 0 | 166.6667 | 133.3333 | 33.3333
WP3_WORKSHOP-202609 | WP3_WORKSHOP | RUSI - Latin America practitioner-policy-academic workshops | WP3 | Directly Incurred | Other Directly Incurred | Workshops | 2026-09-30 | 2026/27 | Straight-line | 80% | 166.6667 | 133.3333 | 33.3333 | 0 | 166.6667 | 133.3333 | 33.3333
WP3_WORKSHOP-202610 | WP3_WORKSHOP | RUSI - Latin America practitioner-policy-academic workshops | WP3 | Directly Incurred | Other Directly Incurred | Workshops | 2026-10-31 | 2026/27 | Straight-line | 80% | 166.6667 | 133.3333 | 33.3333 | 0 | 166.6667 | 133.3333 | 33.3333
WP3_WORKSHOP-202611 | WP3_WORKSHOP | RUSI - Latin America practitioner-policy-academic workshops | WP3 | Directly Incurred | Other Directly Incurred | Workshops | 2026-11-30 | 2026/27 | Straight-line | 80% | 166.6667 | 133.3333 | 33.3333 | 0 | 166.6667 | 133.3333 | 33.3333
WP3_WORKSHOP-202612 | WP3_WORKSHOP | RUSI - Latin America practitioner-policy-academic workshops | WP3 | Directly Incurred | Other Directly Incurred | Workshops | 2026-12-31 | 2026/27 | Straight-line | 80% | 166.6667 | 133.3333 | 33.3333 | 0 | 166.6667 | 133.3333 | 33.3333
WP3_WORKSHOP-202701 | WP3_WORKSHOP | RUSI - Latin America practitioner-policy-academic workshops | WP3 | Directly Incurred | Other Directly Incurred | Workshops | 2027-01-31 | 2026/27 | Straight-line | 80% | 166.6667 | 133.3333 | 33.3333 | 0 | 166.6667 | 133.3333 | 33.3333
WP3_WORKSHOP-202702 | WP3_WORKSHOP | RUSI - Latin America practitioner-policy-academic workshops | WP3 | Directly Incurred | Other Directly Incurred | Workshops | 2027-02-28 | 2026/27 | Straight-line | 80% | 166.6667 | 133.3333 | 33.3333 | 0 | 166.6667 | 133.3333 | 33.3333
WP3_WORKSHOP-202703 | WP3_WORKSHOP | RUSI - Latin America practitioner-policy-academic workshops | WP3 | Directly Incurred | Other Directly Incurred | Workshops | 2027-03-31 | 2026/27 | Straight-line | 80% | 166.6667 | 133.3333 | 33.3333 | 0 | 166.6667 | 133.3333 | 33.3333
WP3_WORKSHOP-202704 | WP3_WORKSHOP | RUSI - Latin America practitioner-policy-academic workshops | WP3 | Directly Incurred | Other Directly Incurred | Workshops | 2027-04-30 | 2027/28 | Straight-line | 80% | 166.6667 | 133.3333 | 33.3333 | 0 | 166.6667 | 133.3333 | 33.3333
WP3_WORKSHOP-202705 | WP3_WORKSHOP | RUSI - Latin America practitioner-policy-academic workshops | WP3 | Directly Incurred | Other Directly Incurred | Workshops | 2027-05-31 | 2027/28 | Straight-line | 80% | 166.6667 | 133.3333 | 33.3333 | 0 | 166.6667 | 133.3333 | 33.3333
WP3_WORKSHOP-202706 | WP3_WORKSHOP | RUSI - Latin America practitioner-policy-academic workshops | WP3 | Directly Incurred | Other Directly Incurred | Workshops | 2027-06-30 | 2027/28 | Straight-line | 80% | 166.6667 | 133.3333 | 33.3333 | 0 | 166.6667 | 133.3333 | 33.3333
WP3_WORKSHOP-202707 | WP3_WORKSHOP | RUSI - Latin America practitioner-policy-academic workshops | WP3 | Directly Incurred | Other Directly Incurred | Workshops | 2027-07-31 | 2027/28 | Straight-line | 80% | 166.6667 | 133.3333 | 33.3333 | 0 | 166.6667 | 133.3333 | 33.3333
WP3_WORKSHOP-202708 | WP3_WORKSHOP | RUSI - Latin America practitioner-policy-academic workshops | WP3 | Directly Incurred | Other Directly Incurred | Workshops | 2027-08-31 | 2027/28 | Straight-line | 80% | 166.6667 | 133.3333 | 33.3333 | 0 | 166.6667 | 133.3333 | 33.3333
WP3_WORKSHOP-202709 | WP3_WORKSHOP | RUSI - Latin America practitioner-policy-academic workshops | WP3 | Directly Incurred | Other Directly Incurred | Workshops | 2027-09-30 | 2027/28 | Straight-line | 80% | 166.6667 | 133.3333 | 33.3333 | 0 | 166.6667 | 133.3333 | 33.3333
WP3_WORKSHOP-202710 | WP3_WORKSHOP | RUSI - Latin America practitioner-policy-academic workshops | WP3 | Directly Incurred | Other Directly Incurred | Workshops | 2027-10-31 | 2027/28 | Straight-line | 80% | 166.6667 | 133.3333 | 33.3333 | 0 | 166.6667 | 133.3333 | 33.3333
WP3_WORKSHOP-202711 | WP3_WORKSHOP | RUSI - Latin America practitioner-policy-academic workshops | WP3 | Directly Incurred | Other Directly Incurred | Workshops | 2027-11-30 | 2027/28 | Straight-line | 80% | 166.6667 | 133.3333 | 33.3333 | 0 | 166.6667 | 133.3333 | 33.3333
WP3_WORKSHOP-202712 | WP3_WORKSHOP | RUSI - Latin America practitioner-policy-academic workshops | WP3 | Directly Incurred | Other Directly Incurred | Workshops | 2027-12-31 | 2027/28 | Straight-line | 80% | 166.6667 | 133.3333 | 33.3333 | 0 | 166.6667 | 133.3333 | 33.3333
WP3_WORKSHOP-202801 | WP3_WORKSHOP | RUSI - Latin America practitioner-policy-academic workshops | WP3 | Directly Incurred | Other Directly Incurred | Workshops | 2028-01-31 | 2027/28 | Straight-line | 80% | 166.6667 | 133.3333 | 33.3333 | 0 | 166.6667 | 133.3333 | 33.3333
WP3_WORKSHOP-202802 | WP3_WORKSHOP | RUSI - Latin America practitioner-policy-academic workshops | WP3 | Directly Incurred | Other Directly Incurred | Workshops | 2028-02-29 | 2027/28 | Straight-line | 80% | 166.6667 | 133.3333 | 33.3333 | 0 | 166.6667 | 133.3333 | 33.3333
WP3_WORKSHOP-202803 | WP3_WORKSHOP | RUSI - Latin America practitioner-policy-academic workshops | WP3 | Directly Incurred | Other Directly Incurred | Workshops | 2028-03-31 | 2027/28 | Straight-line | 80% | 166.6667 | 133.3333 | 33.3333 | 0 | 166.6667 | 133.3333 | 33.3333
WP3_WORKSHOP-202804 | WP3_WORKSHOP | RUSI - Latin America practitioner-policy-academic workshops | WP3 | Directly Incurred | Other Directly Incurred | Workshops | 2028-04-30 | 2028/29 | Straight-line | 80% | 166.6667 | 133.3333 | 33.3333 | 0 | 166.6667 | 133.3333 | 33.3333
WP3_WORKSHOP-202805 | WP3_WORKSHOP | RUSI - Latin America practitioner-policy-academic workshops | WP3 | Directly Incurred | Other Directly Incurred | Workshops | 2028-05-31 | 2028/29 | Straight-line | 80% | 166.6667 | 133.3333 | 33.3333 | 0 | 166.6667 | 133.3333 | 33.3333
WP3_WORKSHOP-202806 | WP3_WORKSHOP | RUSI - Latin America practitioner-policy-academic workshops | WP3 | Directly Incurred | Other Directly Incurred | Workshops | 2028-06-30 | 2028/29 | Straight-line | 80% | 166.6667 | 133.3333 | 33.3333 | 0 | 166.6667 | 133.3333 | 33.3333
WP3_WORKSHOP-202807 | WP3_WORKSHOP | RUSI - Latin America practitioner-policy-academic workshops | WP3 | Directly Incurred | Other Directly Incurred | Workshops | 2028-07-31 | 2028/29 | Straight-line | 80% | 166.6667 | 133.3333 | 33.3333 | 0 | 166.6667 | 133.3333 | 33.3333
WP3_WORKSHOP-202808 | WP3_WORKSHOP | RUSI - Latin America practitioner-policy-academic workshops | WP3 | Directly Incurred | Other Directly Incurred | Workshops | 2028-08-31 | 2028/29 | Straight-line | 80% | 166.6667 | 133.3333 | 33.3333 | 0 | 166.6667 | 133.3333 | 33.3333
WP3_WORKSHOP-202809 | WP3_WORKSHOP | RUSI - Latin America practitioner-policy-academic workshops | WP3 | Directly Incurred | Other Directly Incurred | Workshops | 2028-09-30 | 2028/29 | Straight-line | 80% | 166.6667 | 133.3333 | 33.3333 | 0 | 166.6667 | 133.3333 | 33.3333
WP3_WORKSHOP-202810 | WP3_WORKSHOP | RUSI - Latin America practitioner-policy-academic workshops | WP3 | Directly Incurred | Other Directly Incurred | Workshops | 2028-10-31 | 2028/29 | Straight-line | 80% | 166.6667 | 133.3333 | 33.3333 | 0 | 166.6667 | 133.3333 | 33.3333
WP3_WORKSHOP-202811 | WP3_WORKSHOP | RUSI - Latin America practitioner-policy-academic workshops | WP3 | Directly Incurred | Other Directly Incurred | Workshops | 2028-11-30 | 2028/29 | Straight-line | 80% | 166.6667 | 133.3333 | 33.3333 | 0 | 166.6667 | 133.3333 | 33.3333
WP3_WORKSHOP-202812 | WP3_WORKSHOP | RUSI - Latin America practitioner-policy-academic workshops | WP3 | Directly Incurred | Other Directly Incurred | Workshops | 2028-12-31 | 2028/29 | Straight-line | 80% | 166.6667 | 133.3333 | 33.3333 | 0 | 166.6667 | 133.3333 | 33.3333
WP3_WORKSHOP-202901 | WP3_WORKSHOP | RUSI - Latin America practitioner-policy-academic workshops | WP3 | Directly Incurred | Other Directly Incurred | Workshops | 2029-01-31 | 2028/29 | Straight-line | 80% | 166.6667 | 133.3333 | 33.3333 | 0 | 166.6667 | 133.3333 | 33.3333
WP3_WORKSHOP-202902 | WP3_WORKSHOP | RUSI - Latin America practitioner-policy-academic workshops | WP3 | Directly Incurred | Other Directly Incurred | Workshops | 2029-02-28 | 2028/29 | Straight-line | 80% | 166.6667 | 133.3333 | 33.3333 | 0 | 166.6667 | 133.3333 | 33.3333
WP3_WORKSHOP-202903 | WP3_WORKSHOP | RUSI - Latin America practitioner-policy-academic workshops | WP3 | Directly Incurred | Other Directly Incurred | Workshops | 2029-03-31 | 2028/29 | Straight-line | 80% | 166.6667 | 133.3333 | 33.3333 | 0 | 166.6667 | 133.3333 | 33.3333
WP3_COMMS-202604 | WP3_COMMS | RUSI - Spanish/Portuguese materials and regional communications | WP3 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | 2026-04-30 | 2026/27 | Straight-line | 80% | 55.5558 | 44.4447 | 11.1112 | 0 | 55.5558 | 44.4447 | 11.1112
WP3_COMMS-202605 | WP3_COMMS | RUSI - Spanish/Portuguese materials and regional communications | WP3 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | 2026-05-31 | 2026/27 | Straight-line | 80% | 55.5558 | 44.4447 | 11.1112 | 0 | 55.5558 | 44.4447 | 11.1112
WP3_COMMS-202606 | WP3_COMMS | RUSI - Spanish/Portuguese materials and regional communications | WP3 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | 2026-06-30 | 2026/27 | Straight-line | 80% | 55.5558 | 44.4447 | 11.1112 | 0 | 55.5558 | 44.4447 | 11.1112
WP3_COMMS-202607 | WP3_COMMS | RUSI - Spanish/Portuguese materials and regional communications | WP3 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | 2026-07-31 | 2026/27 | Straight-line | 80% | 55.5558 | 44.4447 | 11.1112 | 0 | 55.5558 | 44.4447 | 11.1112
WP3_COMMS-202608 | WP3_COMMS | RUSI - Spanish/Portuguese materials and regional communications | WP3 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | 2026-08-31 | 2026/27 | Straight-line | 80% | 55.5558 | 44.4447 | 11.1112 | 0 | 55.5558 | 44.4447 | 11.1112
WP3_COMMS-202609 | WP3_COMMS | RUSI - Spanish/Portuguese materials and regional communications | WP3 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | 2026-09-30 | 2026/27 | Straight-line | 80% | 55.5558 | 44.4447 | 11.1112 | 0 | 55.5558 | 44.4447 | 11.1112
WP3_COMMS-202610 | WP3_COMMS | RUSI - Spanish/Portuguese materials and regional communications | WP3 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | 2026-10-31 | 2026/27 | Straight-line | 80% | 55.5558 | 44.4447 | 11.1112 | 0 | 55.5558 | 44.4447 | 11.1112
WP3_COMMS-202611 | WP3_COMMS | RUSI - Spanish/Portuguese materials and regional communications | WP3 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | 2026-11-30 | 2026/27 | Straight-line | 80% | 55.5558 | 44.4447 | 11.1112 | 0 | 55.5558 | 44.4447 | 11.1112
WP3_COMMS-202612 | WP3_COMMS | RUSI - Spanish/Portuguese materials and regional communications | WP3 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | 2026-12-31 | 2026/27 | Straight-line | 80% | 55.5558 | 44.4447 | 11.1112 | 0 | 55.5558 | 44.4447 | 11.1112
WP3_COMMS-202701 | WP3_COMMS | RUSI - Spanish/Portuguese materials and regional communications | WP3 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | 2027-01-31 | 2026/27 | Straight-line | 80% | 55.5558 | 44.4447 | 11.1112 | 0 | 55.5558 | 44.4447 | 11.1112
WP3_COMMS-202702 | WP3_COMMS | RUSI - Spanish/Portuguese materials and regional communications | WP3 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | 2027-02-28 | 2026/27 | Straight-line | 80% | 55.5558 | 44.4447 | 11.1112 | 0 | 55.5558 | 44.4447 | 11.1112
WP3_COMMS-202703 | WP3_COMMS | RUSI - Spanish/Portuguese materials and regional communications | WP3 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | 2027-03-31 | 2026/27 | Straight-line | 80% | 55.5558 | 44.4447 | 11.1112 | 0 | 55.5558 | 44.4447 | 11.1112
WP3_COMMS-202704 | WP3_COMMS | RUSI - Spanish/Portuguese materials and regional communications | WP3 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | 2027-04-30 | 2027/28 | Straight-line | 80% | 55.5558 | 44.4447 | 11.1112 | 0 | 55.5558 | 44.4447 | 11.1112
WP3_COMMS-202705 | WP3_COMMS | RUSI - Spanish/Portuguese materials and regional communications | WP3 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | 2027-05-31 | 2027/28 | Straight-line | 80% | 55.5558 | 44.4447 | 11.1112 | 0 | 55.5558 | 44.4447 | 11.1112
WP3_COMMS-202706 | WP3_COMMS | RUSI - Spanish/Portuguese materials and regional communications | WP3 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | 2027-06-30 | 2027/28 | Straight-line | 80% | 55.5558 | 44.4447 | 11.1112 | 0 | 55.5558 | 44.4447 | 11.1112
WP3_COMMS-202707 | WP3_COMMS | RUSI - Spanish/Portuguese materials and regional communications | WP3 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | 2027-07-31 | 2027/28 | Straight-line | 80% | 55.5558 | 44.4447 | 11.1112 | 0 | 55.5558 | 44.4447 | 11.1112
WP3_COMMS-202708 | WP3_COMMS | RUSI - Spanish/Portuguese materials and regional communications | WP3 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | 2027-08-31 | 2027/28 | Straight-line | 80% | 55.5558 | 44.4447 | 11.1112 | 0 | 55.5558 | 44.4447 | 11.1112
WP3_COMMS-202709 | WP3_COMMS | RUSI - Spanish/Portuguese materials and regional communications | WP3 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | 2027-09-30 | 2027/28 | Straight-line | 80% | 55.5558 | 44.4447 | 11.1112 | 0 | 55.5558 | 44.4447 | 11.1112
WP3_COMMS-202710 | WP3_COMMS | RUSI - Spanish/Portuguese materials and regional communications | WP3 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | 2027-10-31 | 2027/28 | Straight-line | 80% | 55.5558 | 44.4447 | 11.1112 | 0 | 55.5558 | 44.4447 | 11.1112
WP3_COMMS-202711 | WP3_COMMS | RUSI - Spanish/Portuguese materials and regional communications | WP3 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | 2027-11-30 | 2027/28 | Straight-line | 80% | 55.5558 | 44.4447 | 11.1112 | 0 | 55.5558 | 44.4447 | 11.1112
WP3_COMMS-202712 | WP3_COMMS | RUSI - Spanish/Portuguese materials and regional communications | WP3 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | 2027-12-31 | 2027/28 | Straight-line | 80% | 55.5558 | 44.4447 | 11.1112 | 0 | 55.5558 | 44.4447 | 11.1112
WP3_COMMS-202801 | WP3_COMMS | RUSI - Spanish/Portuguese materials and regional communications | WP3 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | 2028-01-31 | 2027/28 | Straight-line | 80% | 55.5558 | 44.4447 | 11.1112 | 0 | 55.5558 | 44.4447 | 11.1112
WP3_COMMS-202802 | WP3_COMMS | RUSI - Spanish/Portuguese materials and regional communications | WP3 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | 2028-02-29 | 2027/28 | Straight-line | 80% | 55.5558 | 44.4447 | 11.1112 | 0 | 55.5558 | 44.4447 | 11.1112
WP3_COMMS-202803 | WP3_COMMS | RUSI - Spanish/Portuguese materials and regional communications | WP3 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | 2028-03-31 | 2027/28 | Straight-line | 80% | 55.5558 | 44.4447 | 11.1112 | 0 | 55.5558 | 44.4447 | 11.1112
WP3_COMMS-202804 | WP3_COMMS | RUSI - Spanish/Portuguese materials and regional communications | WP3 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | 2028-04-30 | 2028/29 | Straight-line | 80% | 55.5558 | 44.4447 | 11.1112 | 0 | 55.5558 | 44.4447 | 11.1112
WP3_COMMS-202805 | WP3_COMMS | RUSI - Spanish/Portuguese materials and regional communications | WP3 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | 2028-05-31 | 2028/29 | Straight-line | 80% | 55.5558 | 44.4447 | 11.1112 | 0 | 55.5558 | 44.4447 | 11.1112
WP3_COMMS-202806 | WP3_COMMS | RUSI - Spanish/Portuguese materials and regional communications | WP3 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | 2028-06-30 | 2028/29 | Straight-line | 80% | 55.5558 | 44.4447 | 11.1112 | 0 | 55.5558 | 44.4447 | 11.1112
WP3_COMMS-202807 | WP3_COMMS | RUSI - Spanish/Portuguese materials and regional communications | WP3 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | 2028-07-31 | 2028/29 | Straight-line | 80% | 55.5558 | 44.4447 | 11.1112 | 0 | 55.5558 | 44.4447 | 11.1112
WP3_COMMS-202808 | WP3_COMMS | RUSI - Spanish/Portuguese materials and regional communications | WP3 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | 2028-08-31 | 2028/29 | Straight-line | 80% | 55.5558 | 44.4447 | 11.1112 | 0 | 55.5558 | 44.4447 | 11.1112
WP3_COMMS-202809 | WP3_COMMS | RUSI - Spanish/Portuguese materials and regional communications | WP3 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | 2028-09-30 | 2028/29 | Straight-line | 80% | 55.5558 | 44.4447 | 11.1112 | 0 | 55.5558 | 44.4447 | 11.1112
WP3_COMMS-202810 | WP3_COMMS | RUSI - Spanish/Portuguese materials and regional communications | WP3 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | 2028-10-31 | 2028/29 | Straight-line | 80% | 55.5558 | 44.4447 | 11.1112 | 0 | 55.5558 | 44.4447 | 11.1112
WP3_COMMS-202811 | WP3_COMMS | RUSI - Spanish/Portuguese materials and regional communications | WP3 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | 2028-11-30 | 2028/29 | Straight-line | 80% | 55.5558 | 44.4447 | 11.1112 | 0 | 55.5558 | 44.4447 | 11.1112
WP3_COMMS-202812 | WP3_COMMS | RUSI - Spanish/Portuguese materials and regional communications | WP3 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | 2028-12-31 | 2028/29 | Straight-line | 80% | 55.5558 | 44.4447 | 11.1112 | 0 | 55.5558 | 44.4447 | 11.1112
WP3_COMMS-202901 | WP3_COMMS | RUSI - Spanish/Portuguese materials and regional communications | WP3 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | 2029-01-31 | 2028/29 | Straight-line | 80% | 55.5558 | 44.4447 | 11.1112 | 0 | 55.5558 | 44.4447 | 11.1112
WP3_COMMS-202902 | WP3_COMMS | RUSI - Spanish/Portuguese materials and regional communications | WP3 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | 2029-02-28 | 2028/29 | Straight-line | 80% | 55.5558 | 44.4447 | 11.1112 | 0 | 55.5558 | 44.4447 | 11.1112
WP3_COMMS-202903 | WP3_COMMS | RUSI - Spanish/Portuguese materials and regional communications | WP3 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | 2029-03-31 | 2028/29 | Straight-line | 80% | 55.5558 | 44.4447 | 11.1112 | 0 | 55.5558 | 44.4447 | 11.1112
WP3_IND-202604 | WP3_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP3 | Indirect | Indirect | Indirect Costs | 2026-04-30 | 2026/27 | Straight-line | 80% | 622.9492 | 498.3593 | 124.5898 | 0 | 622.9492 | 498.3593 | 124.5898
WP3_IND-202605 | WP3_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP3 | Indirect | Indirect | Indirect Costs | 2026-05-31 | 2026/27 | Straight-line | 80% | 622.9492 | 498.3593 | 124.5898 | 0 | 622.9492 | 498.3593 | 124.5898
WP3_IND-202606 | WP3_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP3 | Indirect | Indirect | Indirect Costs | 2026-06-30 | 2026/27 | Straight-line | 80% | 622.9492 | 498.3593 | 124.5898 | 0 | 622.9492 | 498.3593 | 124.5898
WP3_IND-202607 | WP3_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP3 | Indirect | Indirect | Indirect Costs | 2026-07-31 | 2026/27 | Straight-line | 80% | 622.9492 | 498.3593 | 124.5898 | 0 | 622.9492 | 498.3593 | 124.5898
WP3_IND-202608 | WP3_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP3 | Indirect | Indirect | Indirect Costs | 2026-08-31 | 2026/27 | Straight-line | 80% | 622.9492 | 498.3593 | 124.5898 | 0 | 622.9492 | 498.3593 | 124.5898
WP3_IND-202609 | WP3_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP3 | Indirect | Indirect | Indirect Costs | 2026-09-30 | 2026/27 | Straight-line | 80% | 622.9492 | 498.3593 | 124.5898 | 0 | 622.9492 | 498.3593 | 124.5898
WP3_IND-202610 | WP3_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP3 | Indirect | Indirect | Indirect Costs | 2026-10-31 | 2026/27 | Straight-line | 80% | 622.9492 | 498.3593 | 124.5898 | 0 | 622.9492 | 498.3593 | 124.5898
WP3_IND-202611 | WP3_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP3 | Indirect | Indirect | Indirect Costs | 2026-11-30 | 2026/27 | Straight-line | 80% | 622.9492 | 498.3593 | 124.5898 | 0 | 622.9492 | 498.3593 | 124.5898
WP3_IND-202612 | WP3_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP3 | Indirect | Indirect | Indirect Costs | 2026-12-31 | 2026/27 | Straight-line | 80% | 622.9492 | 498.3593 | 124.5898 | 0 | 622.9492 | 498.3593 | 124.5898
WP3_IND-202701 | WP3_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP3 | Indirect | Indirect | Indirect Costs | 2027-01-31 | 2026/27 | Straight-line | 80% | 622.9492 | 498.3593 | 124.5898 | 0 | 622.9492 | 498.3593 | 124.5898
WP3_IND-202702 | WP3_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP3 | Indirect | Indirect | Indirect Costs | 2027-02-28 | 2026/27 | Straight-line | 80% | 622.9492 | 498.3593 | 124.5898 | 0 | 622.9492 | 498.3593 | 124.5898
WP3_IND-202703 | WP3_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP3 | Indirect | Indirect | Indirect Costs | 2027-03-31 | 2026/27 | Straight-line | 80% | 622.9492 | 498.3593 | 124.5898 | 0 | 622.9492 | 498.3593 | 124.5898
WP3_IND-202704 | WP3_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP3 | Indirect | Indirect | Indirect Costs | 2027-04-30 | 2027/28 | Straight-line | 80% | 622.9492 | 498.3593 | 124.5898 | 0 | 622.9492 | 498.3593 | 124.5898
WP3_IND-202705 | WP3_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP3 | Indirect | Indirect | Indirect Costs | 2027-05-31 | 2027/28 | Straight-line | 80% | 622.9492 | 498.3593 | 124.5898 | 0 | 622.9492 | 498.3593 | 124.5898
WP3_IND-202706 | WP3_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP3 | Indirect | Indirect | Indirect Costs | 2027-06-30 | 2027/28 | Straight-line | 80% | 622.9492 | 498.3593 | 124.5898 | 0 | 622.9492 | 498.3593 | 124.5898
WP3_IND-202707 | WP3_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP3 | Indirect | Indirect | Indirect Costs | 2027-07-31 | 2027/28 | Straight-line | 80% | 622.9492 | 498.3593 | 124.5898 | 0 | 622.9492 | 498.3593 | 124.5898
WP3_IND-202708 | WP3_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP3 | Indirect | Indirect | Indirect Costs | 2027-08-31 | 2027/28 | Straight-line | 80% | 622.9492 | 498.3593 | 124.5898 | 0 | 622.9492 | 498.3593 | 124.5898
WP3_IND-202709 | WP3_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP3 | Indirect | Indirect | Indirect Costs | 2027-09-30 | 2027/28 | Straight-line | 80% | 622.9492 | 498.3593 | 124.5898 | 0 | 622.9492 | 498.3593 | 124.5898
WP3_IND-202710 | WP3_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP3 | Indirect | Indirect | Indirect Costs | 2027-10-31 | 2027/28 | Straight-line | 80% | 622.9492 | 498.3593 | 124.5898 | 0 | 622.9492 | 498.3593 | 124.5898
WP3_IND-202711 | WP3_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP3 | Indirect | Indirect | Indirect Costs | 2027-11-30 | 2027/28 | Straight-line | 80% | 622.9492 | 498.3593 | 124.5898 | 0 | 622.9492 | 498.3593 | 124.5898
WP3_IND-202712 | WP3_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP3 | Indirect | Indirect | Indirect Costs | 2027-12-31 | 2027/28 | Straight-line | 80% | 622.9492 | 498.3593 | 124.5898 | 0 | 622.9492 | 498.3593 | 124.5898
WP3_IND-202801 | WP3_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP3 | Indirect | Indirect | Indirect Costs | 2028-01-31 | 2027/28 | Straight-line | 80% | 622.9492 | 498.3593 | 124.5898 | 0 | 622.9492 | 498.3593 | 124.5898
WP3_IND-202802 | WP3_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP3 | Indirect | Indirect | Indirect Costs | 2028-02-29 | 2027/28 | Straight-line | 80% | 622.9492 | 498.3593 | 124.5898 | 0 | 622.9492 | 498.3593 | 124.5898
WP3_IND-202803 | WP3_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP3 | Indirect | Indirect | Indirect Costs | 2028-03-31 | 2027/28 | Straight-line | 80% | 622.9492 | 498.3593 | 124.5898 | 0 | 622.9492 | 498.3593 | 124.5898
WP3_IND-202804 | WP3_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP3 | Indirect | Indirect | Indirect Costs | 2028-04-30 | 2028/29 | Straight-line | 80% | 622.9492 | 498.3593 | 124.5898 | 0 | 622.9492 | 498.3593 | 124.5898
WP3_IND-202805 | WP3_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP3 | Indirect | Indirect | Indirect Costs | 2028-05-31 | 2028/29 | Straight-line | 80% | 622.9492 | 498.3593 | 124.5898 | 0 | 622.9492 | 498.3593 | 124.5898
WP3_IND-202806 | WP3_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP3 | Indirect | Indirect | Indirect Costs | 2028-06-30 | 2028/29 | Straight-line | 80% | 622.9492 | 498.3593 | 124.5898 | 0 | 622.9492 | 498.3593 | 124.5898
WP3_IND-202807 | WP3_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP3 | Indirect | Indirect | Indirect Costs | 2028-07-31 | 2028/29 | Straight-line | 80% | 622.9492 | 498.3593 | 124.5898 | 0 | 622.9492 | 498.3593 | 124.5898
WP3_IND-202808 | WP3_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP3 | Indirect | Indirect | Indirect Costs | 2028-08-31 | 2028/29 | Straight-line | 80% | 622.9492 | 498.3593 | 124.5898 | 0 | 622.9492 | 498.3593 | 124.5898
WP3_IND-202809 | WP3_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP3 | Indirect | Indirect | Indirect Costs | 2028-09-30 | 2028/29 | Straight-line | 80% | 622.9492 | 498.3593 | 124.5898 | 0 | 622.9492 | 498.3593 | 124.5898
WP3_IND-202810 | WP3_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP3 | Indirect | Indirect | Indirect Costs | 2028-10-31 | 2028/29 | Straight-line | 80% | 622.9492 | 498.3593 | 124.5898 | 0 | 622.9492 | 498.3593 | 124.5898
WP3_IND-202811 | WP3_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP3 | Indirect | Indirect | Indirect Costs | 2028-11-30 | 2028/29 | Straight-line | 80% | 622.9492 | 498.3593 | 124.5898 | 0 | 622.9492 | 498.3593 | 124.5898
WP3_IND-202812 | WP3_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP3 | Indirect | Indirect | Indirect Costs | 2028-12-31 | 2028/29 | Straight-line | 80% | 622.9492 | 498.3593 | 124.5898 | 0 | 622.9492 | 498.3593 | 124.5898
WP3_IND-202901 | WP3_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP3 | Indirect | Indirect | Indirect Costs | 2029-01-31 | 2028/29 | Straight-line | 80% | 622.9492 | 498.3593 | 124.5898 | 0 | 622.9492 | 498.3593 | 124.5898
WP3_IND-202902 | WP3_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP3 | Indirect | Indirect | Indirect Costs | 2029-02-28 | 2028/29 | Straight-line | 80% | 622.9492 | 498.3593 | 124.5898 | 0 | 622.9492 | 498.3593 | 124.5898
WP3_IND-202903 | WP3_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP3 | Indirect | Indirect | Indirect Costs | 2029-03-31 | 2028/29 | Straight-line | 80% | 622.9492 | 498.3593 | 124.5898 | 0 | 622.9492 | 498.3593 | 124.5898
WP3_EST-202604 | WP3_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP3 | Directly Allocated | Estates | Estate Costs | 2026-04-30 | 2026/27 | Straight-line | 80% | 79.3867 | 63.5093 | 15.8773 | 0 | 79.3867 | 63.5093 | 15.8773
WP3_EST-202605 | WP3_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP3 | Directly Allocated | Estates | Estate Costs | 2026-05-31 | 2026/27 | Straight-line | 80% | 79.3867 | 63.5093 | 15.8773 | 0 | 79.3867 | 63.5093 | 15.8773
WP3_EST-202606 | WP3_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP3 | Directly Allocated | Estates | Estate Costs | 2026-06-30 | 2026/27 | Straight-line | 80% | 79.3867 | 63.5093 | 15.8773 | 0 | 79.3867 | 63.5093 | 15.8773
WP3_EST-202607 | WP3_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP3 | Directly Allocated | Estates | Estate Costs | 2026-07-31 | 2026/27 | Straight-line | 80% | 79.3867 | 63.5093 | 15.8773 | 0 | 79.3867 | 63.5093 | 15.8773
WP3_EST-202608 | WP3_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP3 | Directly Allocated | Estates | Estate Costs | 2026-08-31 | 2026/27 | Straight-line | 80% | 79.3867 | 63.5093 | 15.8773 | 0 | 79.3867 | 63.5093 | 15.8773
WP3_EST-202609 | WP3_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP3 | Directly Allocated | Estates | Estate Costs | 2026-09-30 | 2026/27 | Straight-line | 80% | 79.3867 | 63.5093 | 15.8773 | 0 | 79.3867 | 63.5093 | 15.8773
WP3_EST-202610 | WP3_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP3 | Directly Allocated | Estates | Estate Costs | 2026-10-31 | 2026/27 | Straight-line | 80% | 79.3867 | 63.5093 | 15.8773 | 0 | 79.3867 | 63.5093 | 15.8773
WP3_EST-202611 | WP3_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP3 | Directly Allocated | Estates | Estate Costs | 2026-11-30 | 2026/27 | Straight-line | 80% | 79.3867 | 63.5093 | 15.8773 | 0 | 79.3867 | 63.5093 | 15.8773
WP3_EST-202612 | WP3_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP3 | Directly Allocated | Estates | Estate Costs | 2026-12-31 | 2026/27 | Straight-line | 80% | 79.3867 | 63.5093 | 15.8773 | 0 | 79.3867 | 63.5093 | 15.8773
WP3_EST-202701 | WP3_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP3 | Directly Allocated | Estates | Estate Costs | 2027-01-31 | 2026/27 | Straight-line | 80% | 79.3867 | 63.5093 | 15.8773 | 0 | 79.3867 | 63.5093 | 15.8773
WP3_EST-202702 | WP3_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP3 | Directly Allocated | Estates | Estate Costs | 2027-02-28 | 2026/27 | Straight-line | 80% | 79.3867 | 63.5093 | 15.8773 | 0 | 79.3867 | 63.5093 | 15.8773
WP3_EST-202703 | WP3_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP3 | Directly Allocated | Estates | Estate Costs | 2027-03-31 | 2026/27 | Straight-line | 80% | 79.3867 | 63.5093 | 15.8773 | 0 | 79.3867 | 63.5093 | 15.8773
WP3_EST-202704 | WP3_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP3 | Directly Allocated | Estates | Estate Costs | 2027-04-30 | 2027/28 | Straight-line | 80% | 79.3867 | 63.5093 | 15.8773 | 0 | 79.3867 | 63.5093 | 15.8773
WP3_EST-202705 | WP3_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP3 | Directly Allocated | Estates | Estate Costs | 2027-05-31 | 2027/28 | Straight-line | 80% | 79.3867 | 63.5093 | 15.8773 | 0 | 79.3867 | 63.5093 | 15.8773
WP3_EST-202706 | WP3_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP3 | Directly Allocated | Estates | Estate Costs | 2027-06-30 | 2027/28 | Straight-line | 80% | 79.3867 | 63.5093 | 15.8773 | 0 | 79.3867 | 63.5093 | 15.8773
WP3_EST-202707 | WP3_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP3 | Directly Allocated | Estates | Estate Costs | 2027-07-31 | 2027/28 | Straight-line | 80% | 79.3867 | 63.5093 | 15.8773 | 0 | 79.3867 | 63.5093 | 15.8773
WP3_EST-202708 | WP3_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP3 | Directly Allocated | Estates | Estate Costs | 2027-08-31 | 2027/28 | Straight-line | 80% | 79.3867 | 63.5093 | 15.8773 | 0 | 79.3867 | 63.5093 | 15.8773
WP3_EST-202709 | WP3_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP3 | Directly Allocated | Estates | Estate Costs | 2027-09-30 | 2027/28 | Straight-line | 80% | 79.3867 | 63.5093 | 15.8773 | 0 | 79.3867 | 63.5093 | 15.8773
WP3_EST-202710 | WP3_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP3 | Directly Allocated | Estates | Estate Costs | 2027-10-31 | 2027/28 | Straight-line | 80% | 79.3867 | 63.5093 | 15.8773 | 0 | 79.3867 | 63.5093 | 15.8773
WP3_EST-202711 | WP3_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP3 | Directly Allocated | Estates | Estate Costs | 2027-11-30 | 2027/28 | Straight-line | 80% | 79.3867 | 63.5093 | 15.8773 | 0 | 79.3867 | 63.5093 | 15.8773
WP3_EST-202712 | WP3_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP3 | Directly Allocated | Estates | Estate Costs | 2027-12-31 | 2027/28 | Straight-line | 80% | 79.3867 | 63.5093 | 15.8773 | 0 | 79.3867 | 63.5093 | 15.8773
WP3_EST-202801 | WP3_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP3 | Directly Allocated | Estates | Estate Costs | 2028-01-31 | 2027/28 | Straight-line | 80% | 79.3867 | 63.5093 | 15.8773 | 0 | 79.3867 | 63.5093 | 15.8773
WP3_EST-202802 | WP3_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP3 | Directly Allocated | Estates | Estate Costs | 2028-02-29 | 2027/28 | Straight-line | 80% | 79.3867 | 63.5093 | 15.8773 | 0 | 79.3867 | 63.5093 | 15.8773
WP3_EST-202803 | WP3_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP3 | Directly Allocated | Estates | Estate Costs | 2028-03-31 | 2027/28 | Straight-line | 80% | 79.3867 | 63.5093 | 15.8773 | 0 | 79.3867 | 63.5093 | 15.8773
WP3_EST-202804 | WP3_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP3 | Directly Allocated | Estates | Estate Costs | 2028-04-30 | 2028/29 | Straight-line | 80% | 79.3867 | 63.5093 | 15.8773 | 0 | 79.3867 | 63.5093 | 15.8773
WP3_EST-202805 | WP3_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP3 | Directly Allocated | Estates | Estate Costs | 2028-05-31 | 2028/29 | Straight-line | 80% | 79.3867 | 63.5093 | 15.8773 | 0 | 79.3867 | 63.5093 | 15.8773
WP3_EST-202806 | WP3_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP3 | Directly Allocated | Estates | Estate Costs | 2028-06-30 | 2028/29 | Straight-line | 80% | 79.3867 | 63.5093 | 15.8773 | 0 | 79.3867 | 63.5093 | 15.8773
WP3_EST-202807 | WP3_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP3 | Directly Allocated | Estates | Estate Costs | 2028-07-31 | 2028/29 | Straight-line | 80% | 79.3867 | 63.5093 | 15.8773 | 0 | 79.3867 | 63.5093 | 15.8773
WP3_EST-202808 | WP3_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP3 | Directly Allocated | Estates | Estate Costs | 2028-08-31 | 2028/29 | Straight-line | 80% | 79.3867 | 63.5093 | 15.8773 | 0 | 79.3867 | 63.5093 | 15.8773
WP3_EST-202809 | WP3_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP3 | Directly Allocated | Estates | Estate Costs | 2028-09-30 | 2028/29 | Straight-line | 80% | 79.3867 | 63.5093 | 15.8773 | 0 | 79.3867 | 63.5093 | 15.8773
WP3_EST-202810 | WP3_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP3 | Directly Allocated | Estates | Estate Costs | 2028-10-31 | 2028/29 | Straight-line | 80% | 79.3867 | 63.5093 | 15.8773 | 0 | 79.3867 | 63.5093 | 15.8773
WP3_EST-202811 | WP3_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP3 | Directly Allocated | Estates | Estate Costs | 2028-11-30 | 2028/29 | Straight-line | 80% | 79.3867 | 63.5093 | 15.8773 | 0 | 79.3867 | 63.5093 | 15.8773
WP3_EST-202812 | WP3_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP3 | Directly Allocated | Estates | Estate Costs | 2028-12-31 | 2028/29 | Straight-line | 80% | 79.3867 | 63.5093 | 15.8773 | 0 | 79.3867 | 63.5093 | 15.8773
WP3_EST-202901 | WP3_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP3 | Directly Allocated | Estates | Estate Costs | 2029-01-31 | 2028/29 | Straight-line | 80% | 79.3867 | 63.5093 | 15.8773 | 0 | 79.3867 | 63.5093 | 15.8773
WP3_EST-202902 | WP3_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP3 | Directly Allocated | Estates | Estate Costs | 2029-02-28 | 2028/29 | Straight-line | 80% | 79.3867 | 63.5093 | 15.8773 | 0 | 79.3867 | 63.5093 | 15.8773
WP3_EST-202903 | WP3_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP3 | Directly Allocated | Estates | Estate Costs | 2029-03-31 | 2028/29 | Straight-line | 80% | 79.3867 | 63.5093 | 15.8773 | 0 | 79.3867 | 63.5093 | 15.8773

## 10) Budget Changes
Approved Budget changes
Log any changes made to the originally proposed project Budget here (adjustments, virements etc.) Note: The original Budget is never overwritten
No changes are approved in this example. Add one row per item and effective month when adding changes. For virements, record the transfer-out and transfer-in lines.
Change ID | Approved Date | Effective Period | Budget Item ID | Amount 100% fEC | Authority | Rationale | Notes | Status

## 11) Model Audit Checks
Workbook controls and reconciliations
MODEL STATUS | PASS
Controls use the frozen source Budget, approved-batch totals and item-level forecast bridge. Power Query configuration is deliberately not a PASS condition because the workbook must remain complete offline.
Check | Actual | Expected | Difference | Tolerance | Status | Where to fix | Notes
Original 100% fEC equals frozen source total | 320708.28 | 320708.28 | 0 | 0.01 | PASS | Budget Baseline | Source workbook total
Original UKRI plus RUSI equals full fEC | 320708.28 | 320708.28 | 0 | 0.01 | PASS | Budget Baseline | Funding-basis reconciliation
Budget baseline contains 1,080 records | 1080 | 1080 | 0 | 0 | PASS | Budget Baseline | 30 items × 36 months
Every mapped Budget item has 36 monthly records | 0 | 0 | 0 | 0 | PASS | Budget Baseline/Mappings | Count of items failing the 36-month test
Project monthly span is 36 months | 36 | 36 | 0 | 0 | PASS | Budget Baseline | April 2026 to March 2029
Approved Budget equals original plus approved changes | 320708.28 | 320708.28 | 0 | 0.01 | PASS | Budget Changes | Original baseline is not overwritten
Approved UKRI plus RUSI equals approved full cost | 320708.28 | 320708.28 | 0 | 0.01 | PASS | Mappings/Budget Baseline | Supports future 100% exceptions
Actuals source row count reconciles | 56 | 56 | 0 | 0 | PASS | Refresh Log/Actuals Ledger | Approved demo batch
Actuals source amount reconciles | 13751.2 | 13751.2 | 0 | 0.01 | PASS | Refresh Log/Actuals Ledger | Approved demo batch
Allocation source row count reconciles | 75 | 75 | 0 | 0 | PASS | Refresh Log/Allocations | Approved demo batch
Allocation source amount reconciles | 21837.92 | 21837.92 | 0 | 0.01 | PASS | Refresh Log/Allocations | Approved demo batch
Commitment source row count reconciles | 10 | 10 | 0 | 0 | PASS | Refresh Log/Commitments Forecast | Approved demo batch
Commitment source amount reconciles | 27200 | 27200 | 0 | 0.01 | PASS | Refresh Log/Commitments Forecast | Approved demo batch
No invalid actual transaction rows | 0 | 0 | 0 | 0 | PASS | Actuals Ledger | Resolve every non-OK populated row
No invalid allocation rows | 0 | 0 | 0 | 0 | PASS | Allocations | Resolve every non-OK populated row
No invalid open commitment rows | 0 | 0 | 0 | 0 | PASS | Commitments Forecast | Closed/cancelled records are permitted
Recognised total agrees to item forecast bridge | 35589.12 | 35589.12 | 0 | 0.01 | PASS | Forecast Bridge | Full-cost recognised total at cut-off
Forecast bridge adds recognised, commitments and ETC | 323608.28 | 323608.28 | 0 | 0.01 | PASS | Forecast Bridge | No double counting
Forecast item Budgets agree to approved Budget | 320708.28 | 320708.28 | 0 | 0.01 | PASS | Forecast Bridge/Budget Baseline | 30 item bridge
Actuals funding shares reconcile to full value | 13751.2 | 13751.2 | 0 | 0.01 | PASS | Actuals Ledger | Current rows use mapped funding rates
Allocation funding shares reconcile to full value | 21837.92 | 21837.92 | 0 | 0.01 | PASS | Allocations | Current rows use mapped funding rates
Commitment funding shares reconcile to full value | 27200 | 27200 | 0 | 0.01 | PASS | Commitments Forecast | Current rows use mapped funding rates
Allocation ledger contains no DI rows | 0 | 0 | 0 | 0 | PASS | Allocations/Mappings | DI belongs in Actuals Ledger
Funding rates are between 0% and 100% | 0 | 0 | 0 | 0 | PASS | Mappings | Allows 80% and authorised 100% lines
Reporting cut-off is within the project | 1 | 1 | 0 | 0 | PASS | Dashboard | Use a valid reporting cut-off
Period-view selector is valid | 1 | 1 | 0 | 0 | PASS | Dashboard | Cumulative, Monthly or Quarterly
Funding-basis selector is valid | 1 | 1 | 0 | 0 | PASS | Dashboard | 100% fEC, UKRI or RUSI
UKRI and RUSI source control totals match the frozen award | 320708.28 | 320708.28 | 0 | 0.01 | PASS | Budget Baseline | Two-decimal presentation basis
No approved Budget changes are assumed in the demo | 0 | 0 | 0 | 0 | PASS | Budget Changes | Update only with documented authority

## 12) Budget Line Mapping
Budget-item mappings | [9 empty] | Period View | Funding Basis | Work Package | fEC Heading | fEC Subheading | Statuses
Validation table mapping various Budget headings and funding rates across different Budget levels, from specifdic Work Package lines to top-level fEC cost headings (e.g. 'Directly Incurred' or 'Indirects'). | [9 empty] | Cumulative | 100% fEC | All | All | All | APPROVED
[10 empty] | Monthly | Price to Funder (UKRI) | WP1 | Directly Allocated | Staff | STAGED
This hypothetical Budget assumes there are no Exceptional costs (fEC 100%). 80% UKRI is assumed for all lines. If an Exception is introduced, update the mapped funding rate and keep the original award baseline for reference. | [9 empty] | Quarterly | RUSI | WP2 | Directly Incurred | Estates | REJECTED
[12 empty] | WP3 | Indirect | Travel & Subsistence | Open
[14 empty] | Other Directly Incurred | Closed
Budget Item ID | Description | Work Package | fEC Heading | fEC Subheading | Reporting Category | Funding Rate | DI Eligible? | Evidence Expectation | Notes |  |  |  |  | Indirect | Cancelled
WP1_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | 80% | No | Approved staff-time/allocation basis | Illustrative mapping from source Budget
WP1_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | 80% | No | Approved staff-time/allocation basis | Illustrative mapping from source Budget
WP1_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP1 | Directly Allocated | Staff | Directly Allocated Staff | 80% | No | Approved staff-time/allocation basis | Illustrative mapping from source Budget
WP1_TRAVEL | RUSI - UK rail, local travel and subsistence Budget | WP1 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | 80% | Yes | Invoice, expense or contract evidence | Illustrative mapping from source Budget
WP1_CONF | RUSI - five-day flagship London conferences (launch and close) | WP1 | Directly Incurred | Other Directly Incurred | Conferences | 80% | Yes | Invoice, expense or contract evidence | Illustrative mapping from source Budget
WP1_WORKSHOP | RUSI - UK national and regional workshops | WP1 | Directly Incurred | Other Directly Incurred | Workshops | 80% | Yes | Invoice, expense or contract evidence | Illustrative mapping from source Budget
WP1_PANEL | RUSI - hybrid panels and practitioner roundtables | WP1 | Directly Incurred | Other Directly Incurred | Panels & Roundtables | 80% | Yes | Invoice, expense or contract evidence | Illustrative mapping from source Budget
WP1_COMMS | RUSI - knowledge products and digital communications | WP1 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | 80% | Yes | Invoice, expense or contract evidence | Illustrative mapping from source Budget
WP1_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP1 | Indirect | Indirect | Indirect Costs | 80% | No | Approved indirect allocation basis | Illustrative mapping from source Budget
WP1_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP1 | Directly Allocated | Estates | Estate Costs | 80% | No | Approved estate allocation basis | Illustrative mapping from source Budget
WP2_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | 80% | No | Approved staff-time/allocation basis | Illustrative mapping from source Budget
WP2_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | 80% | No | Approved staff-time/allocation basis | Illustrative mapping from source Budget
WP2_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP2 | Directly Allocated | Staff | Directly Allocated Staff | 80% | No | Approved staff-time/allocation basis | Illustrative mapping from source Budget
WP2_TRAVEL | RUSI - London-team and East Africa stakeholder travel/subsistence | WP2 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | 80% | Yes | Invoice, expense or contract evidence | Illustrative mapping from source Budget
WP2_CONSULT | RUSI - Nairobi-based regional network broker consultant | WP2 | Directly Incurred | Other Directly Incurred | Regional Consultancy | 80% | Yes | Invoice, expense or contract evidence | Illustrative mapping from source Budget
WP2_CONF | RUSI - five-day Nairobi regional conference | WP2 | Directly Incurred | Other Directly Incurred | Conferences | 80% | Yes | Invoice, expense or contract evidence | Illustrative mapping from source Budget
WP2_WORKSHOP | RUSI - East Africa practitioner-policy-academic workshops | WP2 | Directly Incurred | Other Directly Incurred | Workshops | 80% | Yes | Invoice, expense or contract evidence | Illustrative mapping from source Budget
WP2_COMMS | RUSI - participant materials and regional communications | WP2 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | 80% | Yes | Invoice, expense or contract evidence | Illustrative mapping from source Budget
WP2_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP2 | Indirect | Indirect | Indirect Costs | 80% | No | Approved indirect allocation basis | Illustrative mapping from source Budget
WP2_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP2 | Directly Allocated | Estates | Estate Costs | 80% | No | Approved estate allocation basis | Illustrative mapping from source Budget
WP3_S01 | RUSI - Project Officer (existing staff, DA) @GrB/4 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | 80% | No | Approved staff-time/allocation basis | Illustrative mapping from source Budget
WP3_S02 | RUSI - Research Analyst (existing staff, DA) @GrC/8 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | 80% | No | Approved staff-time/allocation basis | Illustrative mapping from source Budget
WP3_S03 | RUSI - Programme/Project Lead (existing staff, DA) @GrE/14 | WP3 | Directly Allocated | Staff | Directly Allocated Staff | 80% | No | Approved staff-time/allocation basis | Illustrative mapping from source Budget
WP3_TRAVEL | RUSI - London-team and Latin America stakeholder travel/subsistence | WP3 | Directly Incurred | Travel & Subsistence | Travel & Subsistence | 80% | Yes | Invoice, expense or contract evidence | Illustrative mapping from source Budget
WP3_CONSULT | RUSI - Latin America-based regional network broker consultant | WP3 | Directly Incurred | Other Directly Incurred | Regional Consultancy | 80% | Yes | Invoice, expense or contract evidence | Illustrative mapping from source Budget
WP3_CONF | RUSI - five-day Latin America hub conference (hub to be confirmed) | WP3 | Directly Incurred | Other Directly Incurred | Conferences | 80% | Yes | Invoice, expense or contract evidence | Illustrative mapping from source Budget
WP3_WORKSHOP | RUSI - Latin America practitioner-policy-academic workshops | WP3 | Directly Incurred | Other Directly Incurred | Workshops | 80% | Yes | Invoice, expense or contract evidence | Illustrative mapping from source Budget
WP3_COMMS | RUSI - Spanish/Portuguese materials and regional communications | WP3 | Directly Incurred | Other Directly Incurred | Communications & Knowledge Products | 80% | Yes | Invoice, expense or contract evidence | Illustrative mapping from source Budget
WP3_IND | RUSI - indirect allocation (dispensation proxy × eligible staff FTE) | WP3 | Indirect | Indirect | Indirect Costs | 80% | No | Approved indirect allocation basis | Illustrative mapping from source Budget
WP3_EST | RUSI - non-laboratory estate allocation (dispensation proxy × eligible staff FTE) | WP3 | Directly Allocated | Estates | Estate Costs | 80% | No | Approved estate allocation basis | Illustrative mapping from source Budget

## 14) Model Calc (hidden)
Model calculations
Control | Value |  | Helper columns for storing various slicer values, KPIs, charts and reconciliations
Reporting cut-off | 2026-08-31
Period view | Cumulative
Funding basis | 100% fEC
Work Package | All
fEC Heading | Directly Incurred
fEC Subheading | All
Selected period start | 2026-04-01
Selected period end | 2026-08-31
Selected-period phased Budget | 12805.5583
Selected-period recognised cost | 13751.2
Variance to phased | -945.6417
Cumulative phased Budget | 12805.5583
Cumulative recognised cost | 13751.2
Cumulative simple pro-rata | 21416.6694
Full approved Budget | 154200.02
Open commitments | 27200
Forecast at Completion | 157100.02
Forecast variance | -2900
Confirmed DI Costs | 13751.2
Approved DI Budget | 154200.02
Remaining DI Budget | 140448.82
DI Budget consumed | 8.918%
Model status | PASS
Last refresh | 2026-09-01 09:00
Month | Cumulative phased Budget | Cumulative recognised cost | Simple pro-rata
2026-04-30 | 2561.1117 | 1412.4 | 4283.3339
2026-05-31 | 5122.2233 | 4370.6 | 8566.6678
2026-06-30 | 7683.335 | 7459.2 | 12850.0017
2026-07-31 | 10244.4467 | 10426.2 | 17133.3356
2026-08-31 | 12805.5583 | 13751.2 | 21416.6694
2026-09-30 | 30366.67 | #N/A | 25700.0033
2026-10-31 | 32927.7817 | #N/A | 29983.3372
2026-11-30 | 35488.8933 | #N/A | 34266.6711
2026-12-31 | 38050.005 | #N/A | 38550.005
2027-01-31 | 40611.1167 | #N/A | 42833.3389
2027-02-28 | 43172.2283 | #N/A | 47116.6728
2027-03-31 | 45733.34 | #N/A | 51400.0067
2027-04-30 | 48294.4517 | #N/A | 55683.3406
2027-05-31 | 50855.5633 | #N/A | 59966.6744
2027-06-30 | 53416.675 | #N/A | 64250.0083
2027-07-31 | 55977.7867 | #N/A | 68533.3422
2027-08-31 | 58538.8983 | #N/A | 72816.6761
2027-09-30 | 61100.01 | #N/A | 77100.01
2027-10-31 | 63661.1217 | #N/A | 81383.3439
2027-11-30 | 66222.2333 | #N/A | 85666.6778
2027-12-31 | 68783.345 | #N/A | 89950.0117
2028-01-31 | 71344.4567 | #N/A | 94233.3456
2028-02-29 | 89905.5683 | #N/A | 98516.6794
2028-03-31 | 92466.68 | #N/A | 102800.0133
2028-04-30 | 95027.7917 | #N/A | 107083.3472
2028-05-31 | 97588.9033 | #N/A | 111366.6811
2028-06-30 | 100150.015 | #N/A | 115650.015
2028-07-31 | 102711.1267 | #N/A | 119933.3489
2028-08-31 | 105272.2383 | #N/A | 124216.6828
2028-09-30 | 107833.35 | #N/A | 128500.0167
2028-10-31 | 125394.4617 | #N/A | 132783.3506
2028-11-30 | 127955.5733 | #N/A | 137066.6844
2028-12-31 | 130516.685 | #N/A | 141350.0183
2029-01-31 | 149077.7967 | #N/A | 145633.3522
2029-02-28 | 151638.9083 | #N/A | 149916.6861
2029-03-31 | 154200.02 | #N/A | 154200.02
DI Budget status | Amount
Confirmed DI Costs | 13751.2
Remaining DI Budget | 140448.82
Work Package | Selected-period Budget | Recognised cost | Variance | Open commitments | Forecast at Completion | Full approved Budget | fEC Heading | Selected-period Budget | Recognised cost | Variance | Open commitments | Forecast at Completion | Full approved Budget
WP1 | 15804.2708 | 16853.15 | -1048.8792 | 16350 | 153817.23 | 152117.23 | Directly Allocated | 10948.2833 | 10882.64 | 65.6433 | 0 | 82553.88 | 82553.88
WP2 | 8401.3125 | 8380.3 | 21.0125 | 5300 | 76939.45 | 76489.45 | Directly Incurred | 12805.5583 | 13751.2 | -945.6417 | 27200 | 157100.02 | 154200.02
WP3 | 10569.6667 | 10355.67 | 213.9967 | 5550 | 92851.6 | 92101.6 | Indirect | 11021.4083 | 10955.28 | 66.1283 | 0 | 83954.38 | 83954.38
Total | 34775.25 | 35589.12 | -813.87 | 27200 | 323608.28 | 320708.28 | Total | 34775.25 | 35589.12 | -813.87 | 27200 | 323608.28 | 320708.28